## Submittal
Submittal Log
View: | Export View
Project Number: | S590.
Project Name: | ST. GEORGE TEMPLE
Number |  | Rev | Spec Section | Priority | Package | Type | Title | Description | Reference | Due on Site By | State | Response | Assigned To | Assigned To Organization | Due Date | Subcontractor | Submitter Organization | Westland Reviewer | Reviewer Organization | Architect/Engineer | Approver Organization | Lead Days | Due to Subcontractor | Due from Subcontractor | Due to Architect/Engineer | Due from A/E | Assigned to Sub On | Sent to GC On | Design Review On | Reviewed On | Rejected/Revise On | Closed On | Created Date | Additional Reviewers | Additional Approvers
1 |  | 0 | 000000 | Medium |  | Shop Drawing | Font Shop Drawings |  |  |  | Closed | Make Corrections Noted |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 05/15/2020 | 05/09/2020 | 05/27/2020 |  | 05/07/2020 | 05/07/2020 | 06/05/2020 |  | 06/09/2020 | 05/07/2020
3 |  | 0 | 000000 | Medium |  | Submittal | Vinyl Wall Coverings GHID | Product Data & Samples |  |  | Assigned to Sub |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | 08/01/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  |  |  | 0 |  | 08/01/2021 | 07/10/2020 | 07/20/2020 | 06/30/2020 | [5 empty] | 06/30/2020
2 |  | 1 | 000000 | High |  | Submittal | Consolidated East Stone Wall Penetrations Levels 3-5 Review | Penetrations in the stone wall near Grid HB for review. |  |  | Closed | No Exception Taken |  |  |  | Jason Fullmer | Westland Construction, Inc. | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 07/02/2020 | 08/06/2020 | 08/14/2020 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/24/2020 |  | 08/24/2020 | 08/04/2020
5 |  | 0 | 000000 | High |  | Submittal | Generator Pad Penetrations | Per Note E.3 on the S001 we are submitting these concrete penetrations for structural review. |  |  | Closed | Approved As Noted |  |  |  | Trask Johnson | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 09/02/2020 | 09/04/2020 | 09/06/2020 |  | 08/25/2020 | 08/27/2020 | 09/08/2020 |  | 09/10/2020 | 08/25/2020
7 |  | 0 | 000000 | High |  | Submittal | Font Penetration Drawing |  |  |  | Closed | No Exception Taken |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 10/27/2020 | 10/29/2020 | 10/29/2020 | 10/19/2020 |  | 10/19/2020 | 10/27/2020 |  | 10/28/2020 | 10/19/2020
8 |  | 0 | 000000 | High |  | Submittal | SGU North Addition - Precast Penetrations |  |  |  | Closed | Make Corrections Noted |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 10/27/2020 | 10/29/2020 | 10/29/2020 | 10/19/2020 |  | 10/19/2020 | 11/09/2020 |  | 11/10/2020 | 10/19/2020
6 |  | 1 | 000000 | High |  | Submittal | Spiral Stair Case Penetration Drawings |  |  |  | Closed | No Exception Taken |  |  |  | Justun Bylund | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 10/27/2020 | 10/29/2020 | 01/15/2021 | 10/29/2020 |  | 01/05/2021 | 02/08/2021 |  | 02/09/2021 | 10/29/2020
9 |  | 1 | 000000 | High |  | Submittal | North Addition - Precast Penetrations - Plumbing/Mech. |  |  |  | Closed | No Exception Taken |  |  |  | Justun Bylund | US Mechanical LLC | CRSA ARCHITECTURE |  | Kyle Welch | CRSA ARCHITECTURE | 0 |  | 10/27/2020 | 10/29/2020 | 11/20/2020 | 10/29/2020 |  | 11/10/2020 | 11/11/2020 |  | 12/01/2020 | 10/29/2020
10 |  | 0 | 000000 | Medium | DWGS - Shop Drawings | Submittal | Tower Signage Bronze Letters |  |  |  | Closed | Make Corrections Noted |  |  |  | Steve Brown | Historical Arts & Casting Inc. | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 12/02/2020 | 12/04/2020 | 12/05/2020 | 11/25/2020 |  | 11/25/2020 | 12/10/2020 |  | 12/11/2020 | 11/25/2020
4 |  | 1 | 000000 | High | Samples | Submittal | Font Color Samples |  |  |  | Closed | No Exception Taken |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/14/2020 | 07/08/2020 | 12/24/2020 |  |  | 12/15/2020 | 12/17/2020 |  | 12/18/2020 | 12/15/2020
11 |  | 0 | 000000 | Medium |  | Submittal | Font Landing Access Cover |  |  |  | Closed | No Exception Taken |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 06/30/2021 | 07/02/2021 | 07/12/2021 |  | 06/22/2021 | 06/22/2021 | 06/22/2021 |  | 06/22/2021 | 06/22/2021
1 |  | 0 | 015000 | Medium |  | Shop Drawing | TEMPORARY FACILITIES AND CONTROLS |  |  |  | Closed | Approved |  |  |  | Justun Bylund | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  | 0 |  | 11/07/2019 | 11/02/2019 | 11/10/2019 | 10/31/2019 | 10/31/2019 | 10/31/2019 | 11/14/2019 |  | 11/14/2019 | 10/31/2019
1 |  | 0 | 024119 | Medium |  | Product Data | SELECTIVE DEMOLITION | Warranty and demolition plan. |  |  | Closed | Approved |  |  |  | Bryce Christensen | Grant Mackay Co. Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 12/27/2019 | 12/21/2019 | 12/29/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/07/2020 |  | 01/08/2020 | 12/19/2019
2 |  | 0 | 024296 | Low |  | Product Data | HISTORIC REMOVAL AND DISMANTLING (TID) | A. Qualification Data: For historic removal and dismantling specialist. B. Preconstruction Documentation: Show preexisting conditions of adjoining construction and site improvements, including finish surfaces, that might be misconstrued as damage caused by Contractor's removal and dismantling operations. C. Removal and Dismantling Historic Treatment Program: Submit 30 days before work begins. |  |  | Closed | No Exception Taken |  |  |  | Travis Keenan | TID, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/24/2020 | 12/19/2019 | 12/19/2019 | 01/02/2020 | 01/14/2020 |  | 01/15/2020 | 12/18/2019
3 |  | 0 | 024296 | Medium |  | Product Data | HISTORIC REMOVAL AND DISMANTLING (Grant Mackey) |  |  |  | Closed | No Exception Taken |  |  |  | Bryce Christensen | Grant Mackay Co. Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 12/27/2019 | 12/21/2019 | 12/29/2019 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/07/2020 |  | 01/08/2020 | 12/19/2019
2 |  | 0 | 030130 | Low |  | Shop Drawing | FIBER REINFORCED POLYMER | 2. Working drawings shall detail the types, locations, dimensions, number of layers, splice details and orientation of all FRP materials and coatings to be installed. |  |  | Closed | See Other |  |  |  | Dave Andreas | CDC Restoration & Construction | Westland PE’s | [5 empty] | 12/05/2019 |  |  | 12/19/2019 | 12/30/2019 |  |  |  | 01/29/2020 | 12/18/2019
1 |  | 1 | 030130 | High |  | Product Data | FIBER REINFORCED POLYMER | This is a resubmittal to formalize conversations between CDC's structural engineer and ARW. 1. Submit product data indicating product standards, physical and chemical characteristics, technical specifications, limitations, installation instructions, and general recommendations regarding each individual material. 4. Submit a list of completed surface bonded FRP composite strengthening projects completed with the manufacturer's FRP composite system in the past 3 years. The list should include at a minimum 25 projects with proposed FRP system, the dates of work, type, description and amount of work performed. 1. Stamped and signed structural calculations and drawings by a professional Civil or Structural Engineer. Design shall be based on the clearly written performance criteria defined on the structural drawings. 3. A list of two different independent testing laboratories that can perform the required ASTM D7565 and/or ASTM D3039 tests as per Section 3.3 of this specification. 2. Properties of the composite materials as determined by independent laboratory testing in accordance with ASTM D7565 and/or ASTM D3039 (tensile modulus, stress and strain). 3. Large-scale structural testing results of the proposed composite system from independent laboratories on similar structural sections. 4. Installation procedures and general recommendations regarding each material to be used. 5. FRP manufacturer’s Material Safety Data Sheets (MSDS) for all materials to be used. 6. FRP manufacturer’s product data sheet indicating physical, mechanical and chemical characteristics of all materials used in the FRP system. 7. Written verification from the manufacturer that their applicator has received the required certifications and training. 8. Certification by the FRP manufacturer that supplied products comply with local regulations controlling use of volatile organic compounds (VOC’s). Products that require the use of respirators do not comply with local regulations controlling use of VOC’s and shall not be allowed. 2. Working drawings shall detail the types, locations, dimensions, number of layers, splice details and orientation of all FRP materials and coatings to be installed. |  |  | Closed | Make Corrections Noted |  |  |  | Dave Andreas | CDC Restoration & Construction | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/12/2020 |  | 02/28/2020 |  | 02/24/2020 | 02/24/2020 | 02/26/2020 |  | 02/26/2020 | 02/24/2020
4 |  | 0 | 030130 | Medium |  | Product Data | FIBER REINFORCED POLYMER - CCD 37 CHANGE |  |  |  | Closed | See Other |  |  |  | Dave Andreas | CDC Restoration & Construction | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 04/01/2020 | 03/26/2020 | 04/04/2020 | 03/24/2020 | 03/24/2020 | 03/25/2020 | 04/02/2020 |  | 04/06/2020 | 03/24/2020
1 |  | 0 | 031000 | Low |  | Product Data | CONCRETE FORMING AND ACCESSORIES | A. Product Data: For each of the following: 1. Exposed surface form-facing material. 2. Concealed surface form-facing material. 3. Form ties. 4. Waterstops and Groutable Hose Waterstop systems. 5. Form-release agent. |  |  | Closed | Make Corrections Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/17/2020 | 12/19/2019 | 12/30/2019 | 12/31/2019 | 01/06/2020 |  | 01/06/2020 | 12/18/2019
3 |  | 0 | 031000 | Low | Samples | Submittal | CONCRETE FORMING AND ACCESSORIES | C. Samples: 1. For waterstops. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/23/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 01/21/2020 |  | 01/23/2020 | 12/18/2019 |  | Structural Engineers
4 |  | 0 | 031000 | Low |  | Closeout | CONCRETE FORMING AND ACCESSORIES | A. Qualification Data: For testing and inspection agency. B. Field quality-control reports. |  |  | Closed | Not Applicable |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s | [5 empty] | 06/05/2021 |  |  | 12/19/2019 | 12/31/2019 |  |  |  | 12/31/2019 | 12/18/2019
5 |  | 0 | 031000 | High | Samples | Submittal | CONCRETE FORMING AND ACCESSORIES | C. Samples: 1. For waterstops. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/21/2020 | 04/15/2020 | 04/24/2020 | 04/13/2020 | 04/13/2020 | 04/14/2020 | 04/15/2020 |  | 04/16/2020 | 04/13/2020
1 |  | 0 | 032000 | Low |  | Product Data | CONCRETE REINFORCING | A. Product Data: For the following: 1. Each type of steel reinforcement. 2. Epoxy repair coating. 3. Zinc repair material. 4. Bar supports. 5. Mechanical splice couplers. 6. Structural thermal break insulated connection system. A. Qualification Statements: For delegated-design engineer. B. Delegated-Design Engineer Qualifications: Include the following: 1. Experience providing delegated-design engineering services of the type indicated. 2. Documentation that delegated-design engineer is licensed in the jurisdiction state in which Project is located. C. Welding certificates. 1. Reinforcement To Be Welded: Welding procedure specification in accordance with AWS D1.4/D1.4M D. Material Certificates: For each of the following, signed by manufacturers: 1. Epoxy-Coated Reinforcement: CRSI's "Epoxy Coating Plant Certification." 2. Dual-Coated Reinforcement: CRSI's "Epoxy Coating Plant Certification." E. Material Test Reports: For the following, from a qualified testing agency: 1. Steel Reinforcement: a. For reinforcement to be welded, mill test analysis for chemical composition and carbon equivalent of the steel in accordance with ASTM A706/A706M. 2. Mechanical splice couplers. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  |  | 12/19/2019 | 02/06/2020 | 02/24/2020 | 02/26/2020 |  | 02/26/2020 | 12/18/2019
2 |  | 0 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (mat foot elev 79 & 85) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/24/2020 | 12/19/2019 | 01/09/2020 | 01/09/2020 | 01/24/2020 |  | 01/28/2020 | 12/18/2019
4 |  | 0 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (Annex Wall) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Approved As Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | CRSA ARCHITECTURE |  | Structural Engineers | [5 empty] | 03/13/2020 | 03/09/2020 | 03/09/2020 | 03/09/2020 | 03/13/2020 |  | 03/20/2020 | 03/09/2020
7 |  | 0 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (West Historic Elev. 79-100) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Make Corrections Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Camron Walker | Westland Construction, Inc. |  |  | 03/20/2020 | 08/05/2020 | 08/20/2020 | 03/12/2020 | 08/03/2020 | 08/10/2020 | 08/27/2020 |  | 08/27/2020 | 03/12/2020
8 |  | 0 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (Site) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Approved As Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Structural Engineers |  |  |  | 03/20/2020 | 03/22/2020 | 10/10/2020 | 03/12/2020 | 09/25/2020 | 09/30/2020 | 10/07/2020 |  | 10/12/2020 | 03/12/2020 | CRSA ARCHITECTURE
9 |  | 0 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (Annex Lvl 1 SoD) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | See Other |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/20/2020 | 03/22/2020 | 04/06/2020 | 03/12/2020 | 03/20/2020 | 03/27/2020 | 04/06/2020 |  | 04/09/2020 | 03/12/2020
6 |  | 1 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (Historic Jacket Walls) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Make Corrections Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Structural Engineers |  |  |  | 04/24/2020 | 06/21/2020 | 07/20/2020 | 04/16/2020 | 06/19/2020 | 07/10/2020 | 07/10/2020 |  | 07/10/2020 | 04/16/2020 | CRSA ARCHITECTURE
5 |  | 1 | 032000 | High |  | Shop Drawing | CONCRETE REINFORCING (Historic Bapt) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Approved As Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Structural Engineers |  |  |  | 03/20/2020 | 05/16/2020 | 05/24/2020 |  | 05/14/2020 | 05/14/2020 | 05/19/2020 |  | 05/19/2020 | 05/14/2020
10 |  | 0 | 032000 | High |  | Submittal | CONCRETE REINFORCING (Annex Shear Wall Grid A1) |  |  |  | Closed | Make Corrections Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Structural Engineers |  | 0 |  | 06/16/2020 | 06/10/2020 | 06/20/2020 | 06/08/2020 | 06/08/2020 |  | 06/09/2020 |  | 06/09/2020 | 06/08/2020
11 |  | 0 | 032000 | Medium |  | Shop Drawing | CONCRETE REINFORCING (Annex Elev 90 Mat Footing) | B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 06/18/2020 | 06/12/2020 | 06/24/2020 | 06/10/2020 | 06/10/2020 | 06/10/2020 | 06/23/2020 |  | 06/24/2020 | 06/10/2020
12 |  | 0 | 032000 | Low |  | Submittal | CONCRETE REINFORCING | Dui Dag Bar |  |  | Closed | No Exception Taken |  |  |  | David Adams | Westland Construction, Inc. | Westland PE’s |  | Structural Engineers |  |  |  | 07/01/2020 | 06/25/2020 | 07/03/2020 | 06/23/2020 | 06/23/2020 | 06/23/2020 | 06/25/2020 |  | 06/29/2020 | 06/23/2020
13 |  | 0 | 032000 | Medium |  | Shop Drawing | CONCRETE REINFORCING (west hist suspended 88-9 to 100) | west historic suspended slabs 88-9 to 100 B. Shop Drawings: Comply with ACI SP-066: 1. Include placing drawings that detail fabrication, bending, and placement. 2. Include bar sizes, lengths, materials, grades, bar schedules, stirrup spacing, bent bar diagrams, bar arrangement, location of splices, lengths of lap splices, details of mechanical splice couplers, details of welding splices, tie spacing, hoop spacing, and supports for concrete reinforcement. 3. For structural thermal break insulated connection system, indicate general configuration, insulation dimensions, tension bars, compression pads, shear bars, and dimensions. C. Construction Joint Layout: Indicate proposed construction joints required to build the structure. 1. Location of construction joints is subject to approval of the Architect. |  |  | Closed | Approved As Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 08/26/2020 | 08/28/2020 | 08/29/2020 | 08/18/2020 | 08/18/2020 | 08/19/2020 | 08/29/2020 |  | 08/31/2020 | 08/18/2020 | CRSA ARCHITECTURE
14 |  | 0 | 032000 | High |  | Submittal | Concrete Reinforcing - Column Installation Sequence |  |  |  | Closed | See Other |  |  |  | Judd Bundy | Innovative Concrete LLC | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 09/02/2020 | 09/04/2020 | 09/10/2020 | 08/25/2020 | 08/27/2020 | 08/31/2020 | 09/02/2020 |  | 09/08/2020 | 08/25/2020
15 |  | 0 | 032000 | High |  | Submittal | Historic East Tower CCD 45r4 |  |  |  | Closed | Approved |  |  |  | Judd Bundy | Innovative Concrete LLC | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 10/13/2020 | 10/15/2020 | 10/15/2020 | 10/05/2020 | 10/05/2020 | 10/05/2020 | 10/19/2020 |  | 10/28/2020 | 10/05/2020
16 |  | 0 | 032000 | Medium | DWGS - Shop Drawings | Submittal | Landscaper Shed Reinforcing CCD_66 |  |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 11/14/2020 | 11/16/2020 | 11/23/2020 | 11/06/2020 | 11/06/2020 | 11/13/2020 | 11/24/2020 |  | 12/03/2020 | 11/06/2020
17 |  | 0 | 032000 | Medium | DWGS - Shop Drawings | Submittal | Historic 0.5 Slab Reinforcing RFI_715 |  |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 11/14/2020 | 11/16/2020 | 11/23/2020 | 11/06/2020 | 11/06/2020 | 11/13/2020 | 11/24/2020 |  | 12/03/2020 | 11/06/2020
19 |  | 0 | 032000 | High | DWGS - Shop Drawings | Submittal | S-W Slabs Level 2 to Level 5 |  |  |  | Closed | Approved As Noted |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 12/01/2020 | 12/03/2020 | 12/03/2020 | 11/23/2020 | 11/23/2020 | 11/23/2020 | 12/02/2020 |  | 12/03/2020 | 11/23/2020
20 |  | 0 | 032000 | High | DWGS - Shop Drawings | Submittal | S-W Shear-wall Bar Level 1 to Top |  |  |  | Closed | Approved As Noted |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 12/01/2020 | 12/03/2020 | 12/03/2020 | 11/23/2020 | 11/23/2020 | 11/23/2020 | 12/02/2020 |  | 12/03/2020 | 11/23/2020
18 |  | 1 | 032000 | High | DWGS - Shop Drawings | Submittal | Dock Screen Wall Reinforcing ASI_54 |  |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 11/14/2020 | 11/16/2020 | 12/13/2020 |  | 12/03/2020 | 12/03/2020 | 12/10/2020 |  | 12/10/2020 | 12/03/2020
21 |  | 0 | 032000 | Medium |  | Submittal | Jacket Wall Through Bolts |  |  |  | Closed | No Exception Taken |  |  |  | Melissa Carlisle | Innovative Concrete, LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 01/20/2021 | 01/22/2021 | 01/22/2021 |  | 01/12/2021 | 01/12/2021 | 01/15/2021 |  | 02/09/2021 | 01/12/2021
1 |  | 0 | 033000 | Low | Mock-up - Mock-ups use this package. | Mock-Up | CAST-IN-PLACE | D. Color Pigment: Add color pigment to concrete mixture in accordance with manufacturer's written instructions and to result in hardened concrete color consistent with approved mockup. |  |  | Closed | Not Applicable |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s | [5 empty] | 01/29/2020 |  |  | 12/19/2019 | 03/12/2020 |  |  |  | 04/01/2020 | 12/18/2019
2 |  | 0 | 033000 | Low |  | Product Data | CAST-IN-PLACE CONCRETE | A. Product Data: For each of the following. 1. Portland cement. 2. Fly ash. 3. Slag cement. 4. Blended hydraulic cement. 5. Silica fume. 6. Performance-based hydraulic cement 7. Aggregates. 8. Admixtures: a. Include limitations of use, including restrictions on cementitious materials, supplementary cementitious materials, air entrainment, aggregates, temperature at time of concrete placement, relative humidity at time of concrete placement, curing conditions, and use of other admixtures. 9. Color pigments. 10. Fiber reinforcement. 11. Vapor retarders. 12. Floor and slab treatments. 13. Liquid floor treatments. 14. Curing materials. a. Include documentation from color pigment manufacturer, indicating that proposed methods of curing are recommended by color pigment manufacturer. 15. Joint fillers. 16. Repair materials. B. Design Mixtures: For each concrete mixture, include the following: 1. Mixture identification. 2. Minimum 28-day compressive strength. 3. Durability exposure class. 4. Maximum w/cm. 5. Calculated equilibrium unit weight, for lightweight concrete. 6. Slump limit. 7. Air content. 8. Nominal maximum aggregate size. 9. Steel-fiber reinforcement content. 10. Synthetic micro-fiber content. 11. Indicate amounts of mixing water to be withheld for later addition at Project site if permitted. 12. Include manufacturer's certification that permeability-reducing admixture is compatible with mix design. 13. Include certification that dosage rate for permeability-reducing admixture matches dosage rate used in performance compliance test. 14. Intended placement method. 15. Submit alternate design mixtures when characteristics of materials, Project conditions, weather, test results, or other circumstances warrant adjustments. D. Concrete Schedule: For each location of each Class of concrete indicated in "Concrete Mixtures" Article, including the following: 1. Concrete Class designation. 2. Location within Project. 3. Exposure Class designation. 4. Formed Surface Finish designation and final finish. 5. Final finish for floors. 6. Curing process. 7. Floor treatment if any. A. Material Certificates: For each of the following, signed by manufacturers: 1. Cementitious materials. 2. Admixtures. 3. Fiber reinforcement. 4. Curing compounds. 5. Floor and slab treatments. 6. Bonding agents. 7. Adhesives. 8. Vapor retarders. 9. Semirigid joint filler. 10. Joint-filler strips. 11. Repair materials. B. Material Test Reports: For the following, from a qualified testing agency: 1. Portland cement. 2. Fly ash. 3. Slag cement. 4. Blended hydraulic cement. 5. Silica fume. 6. Performance-based hydraulic cement. 7. Aggregates. 8. Admixtures: a. Permeability-Reducing Admixture: Include independent test reports, indicating compliance with specified requirements, including dosage rate used in test. D. Research Reports: 1. For concrete admixtures in accordance with ICC's Acceptance Criteria AC198. 's Acceptance Criteria AC198. C. Shop Drawings: 1. Construction Joint Layout: Indicate proposed construction joints required to construct the structure. a. Location of construction joints is subject to approval of the Architect and Structural Engineer. |  |  | Closed | Make Corrections Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/17/2020 | 12/19/2019 | 12/31/2019 | 01/23/2020 | 01/29/2020 |  | 01/29/2020 | 12/18/2019
3 |  | 0 | 033000 | Low |  | Shop Drawing | CAST-IN-PLACE CONCRETE | C. Shop Drawings: 1. Construction Joint Layout: Indicate proposed construction joints required to construct the structure. a. Location of construction joints is subject to approval of the Architect and Structural Engineer. |  |  | Closed | See Other |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s | [5 empty] | 12/05/2019 |  |  | 12/19/2019 |  |  |  |  | 12/31/2019 | 12/18/2019
5 |  | 0 | 033000 | Low |  | Product Data | CAST-IN-PLACE CONCRETE | Submit per submittal 2 review: Please provide strength tests for SCC mix Provide fiber mix design per page 4 |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/16/2020 | 01/19/2020 | 02/03/2020 | 01/08/2020 | 01/17/2020 | 01/24/2020 | 02/03/2020 |  | 02/05/2020 | 01/08/2020
6 |  | 0 | 033000 | Medium |  | Submittal | Stair Pan Mix Design |  |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 11/14/2020 | 11/16/2020 | 11/23/2020 | 11/06/2020 | 11/06/2020 | 11/13/2020 | 11/24/2020 |  | 12/03/2020 | 11/06/2020
7 |  | 0 | 033000 | High |  | Submittal | CAST-IN-PLACE - .5 Level in Historical | This was suggested by the Structural Engineer for placement on the .5 floor. |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bolli | Innovative Concrete LLC | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 11/24/2020 | 11/26/2020 | 11/26/2020 | 11/16/2020 |  | 11/16/2020 | 11/24/2020 |  | 12/10/2020 | 11/16/2020
8 |  | 0 | 033000 | High |  | Submittal | CAST-IN-PLACE - High Early |  |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 02/26/2021 | 02/28/2021 | 02/28/2021 | 02/18/2021 | 02/18/2021 | 02/18/2021 | 02/19/2021 |  | 02/19/2021 | 02/18/2021
9 |  | 0 | 033000 | High |  | Submittal | CAST-IN-PLACE - City Curb and Gutter | City-approved curb and gutter mix design. |  |  | Closed | Approved As Noted |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Civil Engineers |  | 0 |  | 02/23/2021 | 02/23/2021 | 03/05/2021 | 02/18/2021 | 02/23/2021 | 02/23/2021 | 02/24/2021 |  | 03/23/2021 | 02/23/2021
1 |  | 0 | 033010 | Low |  | Product Data | SITE CAST-IN-PLACE CONCRETE | A. Product Data: Submit manufacturer's technical product data and installation instructions for concrete materials and products. |  |  | Closed | Approved As Noted |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Paul Mogle | HORROCKS ENGINEERS, INC. |  |  | 12/05/2019 |  | 01/17/2020 | 12/19/2019 | 12/31/2019 | 01/06/2020 | 01/13/2020 |  | 01/13/2020 | 12/18/2019
1 |  | 0 | 033713 | Low |  | Product Data | Shotcrete | A. Action Submittals: 1. Product Data: a. Manufacturer materials and products including reinforcement and forming accessories, shotcrete materials, admixtures, and curing compounds. b. Manufacturer’s Material Safety Data Sheets. 2. Shop Drawings: a. Details of fabrication, bending, and placing reinforcement. Include support and anchor details, number and location of splices, and special reinforcement required for openings through shotcrete structures. 3. Samples: a. Provide reinforcement anchors: 1) Full size of each type used. B. Informational Submittals: 1. Certificates: a. Material Certificates: 1) Each material item, signed by Manufacturers. b. Provide certificates with supporting testing reports verifying compliance with Contract Document requirements and that materials provided are from single source for following: 1) Cement. 2) Aggregate. 3) Fly Ash. 2. Design Mixes: a. Provide each shotcrete mix. 3. Test Reports. a. Manufacturer’s test reports. 4. Source Quality Control Submittals: a. Concrete mix design: Submit mix designs to meet following requirements: 5. Qualification Statements: a. Installer: Certifying installers comply with requirements specified under Quality Assurance Article of this Section. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/28/2020 | 12/19/2019 | 01/13/2020 | 01/13/2020 | 01/29/2020 |  | 01/29/2020 | 12/18/2019
1 |  | 0 | 034100 | Low |  | Product Data | PRECAST STRUCTURAL CONCRETE | A. Product Data: For each type of product. |  |  | Closed | Pending Approval |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [6 empty] | 10/07/2019 | 10/18/2019 | 10/25/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019
2 |  | 0 | 034100 | Low |  | Submittal Register | PRECAST STRUCTURAL CONCRETE | B. Design Mixtures: For each precast concrete mixture. Include compressive strength and, if required, water-absorption tests. |  |  | Closed | Defer To Consultant |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 11/01/2019 | 10/07/2019 | 10/16/2019 | 10/21/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019 | Jay Webster | Structural Engineers
3 |  | 0 | 034100 | High |  | Shop Drawing | PRECAST STRUCTURAL CONCRETE | C. Shop Drawings: 1. Include member locations, plans, elevations, dimensions, shapes and sections, openings, support conditions, and types of reinforcement, including special reinforcement. 2. Detail fabrication and installation of precast structural concrete units, including connections at member ends and to adjoining construction. 3. Indicate joints, reveals, drips, chamfers, and extent and location of each surface finish. 4. Indicate separate face and backup mixture locations and thicknesses. 5. Indicate type, size, and length of welded connections by AWS standard symbols. 6. Detail loose and cast-in hardware, lifting and erection inserts, connections, and joints. 7. Indicate locations, tolerances, and details of anchorage devices to be embedded in or attached to structure or other construction. 8. Include and locate openings larger than 10 inches (250 mm). Where additional structural support is required, include header design. 9. Indicate location of each precast structural concrete unit by same identification mark placed on panel. 10. Indicate relationship of precast structural concrete units to adjacent materials. 11. Indicate shim sizes and grouting sequence. 12. If design modifications are proposed to meet performance requirements and field conditions, submit design calculations and Shop Drawings. Do not adversely affect the appearance, durability, or strength of units when modifying details or materials and maintain the general design concept. 13. Shop Drawings shall clearly illustrate all aspects of the Architectural Precast Concrete cladding including: a. The relationship of the Work to the building structure, mechanical systems, roofs, and other related and adjoining work; b. The arrangements of components; c. The sequence and details of fabrication, assembly and erection; d. Full size details, including isometric drawings of sealing, flashing, and jointing; all dimensions and thicknesses, materials and finishes; material, type, size, location, and spacing of screws, bolts, welds, anchoring devices, and accessories. 14. Include details of connections to contiguous work as approved by the Subcontractor for the adjacent work, and shall include all assumptions regarding the tolerances of that work. 15. Clearly indicate all revisions to shop drawings on resubmissions. 16. Complete information essential to proper fabrication and installation of precast units. Show each type of precast unit required. Show unit shapes and dimensions; elevations and sections; location of actual joints and false joints; location, size and type of reinforcement, including special reinforcement and lifting devices; fabrication tolerances and details of anchorage devices and supports that are embedded in or attached to structure or other construction. 17. Include sequence of erection, and a list and numbering system that identifies each precast concrete unit and its position on the building. 18. Clearly indicate on shop drawings proposed deviations or changes from Contract Drawings. Approval of the Owner’s Representative is required for any proposed deviation or change. Any such deviation or change shall not alter visual appearance. 19. Indicate locations and details of brick units and joint treatment. 20. Indicate locations and details of rigid insulation at interior side of precast panels. |  |  | Closed | Approved As Noted |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 10/29/2019 | 10/07/2019 | 10/07/2019 | 03/09/2020 | 03/18/2020 |  | 03/25/2020 | 09/10/2019 |  | Structural Engineers
4 |  | 0 | 034100 | Low |  | Shop Drawing | PRECAST STRUCTURAL CONCRETE | D. Coordination Drawings: Provide coordination drawings showing relation of precast anchors and channel supports for attachment to supporting structure in related section. Clearly indicated tolerance required for mounting components to structure and relation to fire –protection materials. Verify size and location of blockouts for related trades, i.e., light and plumbing fixture and fire protection equipment. |  |  | Closed | Pending Approval |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [6 empty] | 10/07/2019 | 10/15/2019 | 10/25/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019
5 |  | 0 | 034100 | Low |  | Submittal Register | PRECAST STRUCTURAL CONCRETE | E. Delegated-Design Submittal: For precast structural concrete indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. 1. Show precast structural concrete unit types, connections, types of reinforcement, including special reinforcement, and concrete cover on reinforcement. Indicate location, type, magnitude, and direction of loads imposed on the building structural frame from precast structural concrete. |  |  | Closed | Pending Approval |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [6 empty] | 10/15/2019 | 10/15/2019 | 10/25/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019
6 |  | 0 | 034100 | Low |  | Submittal Register | PRECAST STRUCTURAL CONCRETE | A. Qualification Data: For Installer, fabricator, and testing agency. |  |  | Closed | Defer To Consultant |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 10/29/2019 | 10/07/2019 | 10/08/2019 | 10/15/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019 |  | Structural Engineers
7 |  | 0 | 034100 | Low |  | Submittal Certificate | PRECAST STRUCTURAL CONCRETE | B. Welding certificates. |  |  | Closed | Defer To Consultant |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 10/29/2019 | 10/07/2019 | 10/08/2019 | 10/15/2019 | 10/28/2019 |  | 10/28/2019 | 09/10/2019 |  | Structural Engineers
8 |  | 0 | 034100 | Low | Mock-up - Mock-ups use this package. | Mock-Up | PRECAST STRUCT CONC | G. Mockups: After sample panel approval but before production of precast structural concrete units with architectural finish, construct full-sized mockups to verify selections made under Sample submittals and to demonstrate aesthetic effects and to set quality standards for materials and execution. 1. Build mockup as indicated on Drawings including sealants and precast structural concrete units with an architectural finish complete with anchors, connections, flashings, and joint fillers. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Closed | See Other |  |  |  | Brent Klopfer | Forterra Structural Precast | Westland PE’s | [5 empty] | 12/05/2019 |  |  | 12/19/2019 | 01/02/2020 |  |  |  | 01/02/2020 | 12/18/2019
51 |  | 0 | 034500 | Medium |  | Submittal | Site Arch Precast |  |  |  | Design Review |  | Landscape Architects |  | 07/20/2021 | Bob Durrant | IMS Masonry Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  | 0 |  |  |  | 07/20/2021 |  | 07/06/2021 | 07/06/2021 |  |  |  | 07/06/2021
1 |  | 0 | 034900 | Low | Mock-up - Mock-ups use this package. | Mock-Up | CONCRETE (GFRC) | D. Mockups: Build mockups to demonstrate aesthetic effects and to set quality standards for fabrication and installation. 1. Build mockup of typical wall area as shown on Drawings. a. Include typical components, attachments to building structure, and methods of installation. b. Include window opening with GFRC returns. c. Include sealant-filled joint complying with requirements in Section 079200 "Joint Sealants." 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. Exposed faces shall be free of joint marks, grain, and other obvious defects. Corners, including false joints, shall be uniform, straight, and sharp. Finish exposed-face surfaces of GFRC to match approved mockups and as follows: 1. As-Cast-Surface Finish: Provide surfaces to match approved sample for acceptable surface, air voids, sand streaks, and honeycomb, with uniform color and texture. |  |  | Assigned to Sub |  | Aaron Bowers | Pete King Commercial | 12/16/2019 | Aaron Bowers | Pete King Commercial | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 034900 | Low |  | Product Data | GLASS-FIBER-REINFORCED CONCRETE (GFRC) | A. Product Data: For each type of product. Include GFRC design mixes. D. Delegated-Design Submittal: For GFRC panels, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. A. Qualification Data: For manufacturer. B. Welding certificates. C. Steel Sheet Certificates: For steel sheet used in cold-formed steel panel framing, mill certificates signed by manufacturers of steel sheet, or test reports from a qualified testing agency, indicating that steel sheet used in cold-formed metal panel framing complies with requirements including uncoated steel thickness, yield strength, tensile strength, total elongation, chemical requirements, and galvanized-coating thickness. D. Mill Certificates: For structural-steel shapes and hollow structural sections used in panel framing. E. Source Quality-Control Program: For GFRC manufacturer. F. Source Quality-Control Test Reports: For GFRC, inserts, and anchors. |  |  | Assigned to Sub |  | Aaron Bowers | Pete King Commercial | 12/16/2019 | Aaron Bowers | Pete King Commercial | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 034900 | Low | Samples | Submittal | GLASS-FIBER-REINFORCED CONCRETE (GFRC) | C. Samples for Verification: For each type of finish indicated on exposed GFRC surfaces, representative of finish, color, and texture variations expected, approximately 12 by 12 inches (305 by 305 mm) by actual thickness. |  |  | Assigned to Sub |  | Dustin Williams | Unlimited Designs Inc. | 12/16/2019 | Dustin Williams | Unlimited Designs Inc. | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 1 | 034900 | High |  | Shop Drawing | GLASS-FIBER-REINFORCED CONCRETE (GFRC) | B. Shop Drawings: Show fabrication and installation details for GFRC panels including the following: 1. Panel elevations, sections, and dimensions. 2. Thickness of facing mix, GFRC backing, and bonding pads for typical panels. 3. Finishes. 4. Joint and connection details. 5. Erection details. 6. Panel frame details for typical panels including sizes, spacings, thicknesses, and yield strengths of various members. 7. Locations and details of connection hardware attached to structure. 8. Sizes, locations, and details of flex, gravity, and seismic anchors for typical panels. 9. Other items sprayed into panels. 10. Erection sequence for special conditions. 11. Relationship to adjacent materials. 12. Description of loose, cast-in, and field hardware. |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 | 12/17/2020 | 12/27/2020 |  |  | 12/17/2020 | 12/22/2020 |  | 12/22/2020 | 12/17/2020
50 |  | 1 | 034900 | High |  | Submittal | GLASS-FIBER-REINFORCED CONCRETE– Buttress |  |  |  | Assigned to Sub |  | Dustin Williams | Unlimited Designs Inc. | 07/09/2021 | Dustin Williams | Unlimited Designs Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/09/2021 | 05/27/2021 | 05/31/2021 | 07/07/2021 | [5 empty] | 07/07/2021 | CRSA ARCHITECTURE
1 |  | 0 | 035416 | Low |  | Product Data | HYDRAULIC CEMENT UNDERLAYMENT | A. Product Data: For each type of product. A. Qualification Data: For Installer. |  |  | Draft |  |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/05/2019 |  |  | 12/19/2019 | 12/30/2019 |  |  |  |  | 12/18/2019
2 |  | 0 | 035416 | Low |  | Shop Drawing | HYDRAULIC CEMENT UNDERLAYMENT | B. Shop Drawings: Include plans indicating substrates, locations, and average depths of underlayment based on survey of substrate conditions. |  |  | Draft |  |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/05/2019 |  |  | 12/19/2019 | 12/30/2019 |  |  |  |  | 12/18/2019
1 |  | 0 | 042000 | Low |  | Product Data | UNIT MASONRY | A. Product Data: For each type of product. B. Qualification Data: For testing agencyC. Material Certificates: For each type and size of the following: 1. Masonry units. a. Include material test reports substantiating compliance with requirements. b. For masonry units used in structural masonry, include data and calculations establishing average net-area compressive strength of units. 2. Integral water repellent used in CMUs. 3. Cementitious materials. Include name of manufacturer, brand name, and type. 4. Mortar admixtures. 5. Preblended, dry mortar mixes. Include description of type and proportions of ingredients. 6. Grout mixes. Include description of type and proportions of ingredients. 7. Reinforcing bars. 8. Joint reinforcement. 9. Anchors, ties, and metal accessories.D. Mix Designs: For each type of mortar and grout. Include description of type and proportions of ingredients. 1. Include test reports for mortar mixes required to comply with property specification. Test according to ASTM C109/C109M for compressive strength, ASTM C1506 for water retention, and ASTM C91/C91M for air content. 2. Include test reports, according to ASTM C1019, for grout mixes required to comply with compressive strength requirement. E. Statement of Compressive Strength of Masonry: For each combination of masonry unit type and mortar type, provide statement of average net-area compressive strength of masonry units, mortar type, and resulting net-area compressive strength of masonry determined according to TMS 602/ACI 530.1/ASCE 6. F. Cold-Weather and Hot-Weather Procedures: Detailed description of methods, materials, and equipment to be used to comply with requirements |  |  | Closed | No Exception Taken |  |  |  | Jason Curtis | C & C Masonry Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/24/2020 | 12/19/2019 | 01/06/2020 | 01/09/2020 | 01/10/2020 |  | 01/13/2020 | 12/18/2019
2 |  | 0 | 042000 | Low |  | Shop Drawing | UNIT MASONRY | B. Shop Drawings: For the following: 1. Masonry Units: Show sizes, profiles, coursing, and locations of special shapes. 2. Reinforcing Steel: Detail bending, lap lengths, and placement of unit masonry reinforcing bars. Comply with ACI 315. |  |  | Closed | See Other |  |  |  | Jason Curtis | C & C Masonry Inc | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
3 |  | 0 | 042000 | High |  | Product Data | UNIT MASONRY | Masonry Grout Mix Design A. Product Data: For each type of product. B. Qualification Data: For testing agencyC. Material Certificates: For each type and size of the following: 1. Masonry units. a. Include material test reports substantiating compliance with requirements. b. For masonry units used in structural masonry, include data and calculations establishing average net-area compressive strength of units. 2. Integral water repellent used in CMUs. 3. Cementitious materials. Include name of manufacturer, brand name, and type. 4. Mortar admixtures. 5. Preblended, dry mortar mixes. Include description of type and proportions of ingredients. 6. Grout mixes. Include description of type and proportions of ingredients. 7. Reinforcing bars. 8. Joint reinforcement. 9. Anchors, ties, and metal accessories.D. Mix Designs: For each type of mortar and grout. Include description of type and proportions of ingredients. 1. Include test reports for mortar mixes required to comply with property specification. Test according to ASTM C109/C109M for compressive strength, ASTM C1506 for water retention, and ASTM C91/C91M for air content. 2. Include test reports, according to ASTM C1019, for grout mixes required to comply with compressive strength requirement. E. Statement of Compressive Strength of Masonry: For each combination of masonry unit type and mortar type, provide statement of average net-area compressive strength of masonry units, mortar type, and resulting net-area compressive strength of masonry determined according to TMS 602/ACI 530.1/ASCE 6. F. Cold-Weather and Hot-Weather Procedures: Detailed description of methods, materials, and equipment to be used to comply with requirements |  |  | Closed | No Exception Taken |  |  |  | Jason Curtis | C & C Masonry Inc | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/23/2020 | 04/17/2020 | 04/25/2020 | 12/19/2019 | 04/15/2020 | 04/15/2020 | 04/28/2020 |  | 04/30/2020 | 04/15/2020
2 |  | 0 | 044200 | Low |  | Product Data | STONE CLADDING | B. Product Data: Contractor shall submit product tests and data as required herein |  |  | Closed | Approved As Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 12/16/2019 |  | 07/10/2020 | 06/24/2020 | 06/24/2020 | 06/24/2020 | 08/04/2020 |  | 08/11/2020 | 12/18/2019
3 |  | 0 | 044200 | Low | Mock-up - Mock-ups use this package. | Mock-Up | STONE CLADDING | A. Anchored Stone Masonry: Mockup of an area 5’ by 6’ minimum shall be submitted and approved prior to construction. Landscape architect shall approve stonework mockup prior to continuing work. |  |  | Assigned to Sub |  | Bob Durrant | IMS Masonry Inc. |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [8 empty] | 06/24/2020 | [5 empty] | 12/18/2019
4 |  | 1 | 044200 | Low |  | Submittal | STONE CLADDING | Shop Drawings for Historic Stairs |  |  | Closed | See Other |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 09/03/2020 | 06/26/2020 | 07/10/2020 | 08/27/2020 | 10/16/2020 |  |  |  | 10/28/2020 | 08/27/2020
1 |  | 2 | 044200 | High | Samples | Submittal | STONE CLADDING - Stair Samples | A. Samples: Contractor shall submit stone veneer samples. Notes: 1 - Provide samples of walking surface stone with light sandblast finish for slip resistance. 2 - Ensure all vertical faces of stair tread nosing maintain same direction of vein cut. 3 - Ensure all horizontal faces of stair treads maintain similar direction/movement of Fleuri cut. 4 - Provide carborundum mockup for approval. Use base epoxy mix color matching as closely as possible the Laticrete grout color 59 Espresso. |  |  | Assigned to Sub |  | Bob Durrant | IMS Masonry Inc. | 02/25/2021 | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 02/25/2021 |  | 12/15/2020 | 02/18/2021 | [5 empty] | 02/18/2021
1 |  | 0 | 050000 | High |  | Product Data | Flat Jacks |  |  |  | Closed | Approved As Noted |  |  |  | Camron Walker | Westland Construction, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  |  |  | 12/30/2019 |  |  | 12/30/2019 | 12/30/2019 |  | 12/31/2019 | 12/30/2019
2 |  | 0 | 050000 | Medium |  | Product Data | Flat Jacks | Additional information requested in Submittal 1's review. Plan view indicating all locations where the contractor intends to use this product Narrative explaining how the product is used, i.e. what systems are required to expand the plates and engage loads. How will the contractor utilize the systems to transfer loads from the existing conditions to the temporary foundations and back? What is the process to transition from temporary to permanent loading condition where this is required. |  |  | Closed | No Exception Taken |  |  |  | Camron Walker | Westland Construction, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 01/08/2020 | 01/02/2020 | 01/10/2020 | 12/31/2019 | 12/31/2019 | 12/31/2019 | 01/06/2020 |  | 01/06/2020 | 12/31/2019
1 |  | 0 | 051200 | Low |  | Product Data | STRUCTURAL STEEL FRAMING | A. Product Data: 1. Structural-steel materials. 2. High-strength, bolt-nut-washer assemblies. 3. Shear stud connectors. 4. Anchor rods. 5. Threaded rods. 6. Forged-steel hardware. 7. Slide bearings. 8. Prefabricated building columns. 9. Shop primer. 10. Galvanized-steel primer. 11. Etching cleaner. 12. Galvanized repair paint. 13. Shrinkage-resistant grout. C. Welding Procedure Specifications (WPSs) and Procedure Qualification Records (PQRs): Provide in accordance with AWS D1.1/D1.1M for each welded joint whether prequalified or qualified by testing, including the following: 1. Power source (constant current or constant voltage). 2. Electrode manufacturer and trade name, for demand-critical welds. D. Delegated-Design Submittal: For structural-steel connections indicated on Drawings to comply with design loads, include analysis data signed and sealed by the qualified professional engineer responsible for their preparation. A. Qualification Data: For Installer fabricator shop-painting applicators professional engineer testing agency. B. Welding certificates. C. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers, certifying that shop primers are compatible with topcoats. D. Mill test reports for structural-steel materials, including chemical and physical properties. E. Product Test Reports: For the following: 1. Bolts, nuts, and washers, including mechanical properties and chemical analysis. 2. Direct-tension indicators. 3. Tension-control, high-strength, bolt-nut-washer assemblies. 4. Shear stud connectors. F. Survey of existing conditions. G. Source quality-control reports. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | 01/22/2020 |  |  |  |  | 12/18/2019
2 |  | 0 | 051200 | Low |  | Shop Drawing | STRUCTURAL STEEL FRAMING | B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/02/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 01/02/2020 |  | 01/02/2020 | 12/18/2019
4 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (Annex) | (Annex Structural Steel Submittal) B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/01/2020 | 01/26/2020 | 02/03/2020 | 01/24/2020 | 01/24/2020 | 01/24/2020 | 02/03/2020 |  | 02/04/2020 | 01/24/2020
5 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (Historic Lvl 2) | Historic Level 2 B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/06/2020 | 01/31/2020 | 02/07/2020 | 01/29/2020 | 01/29/2020 | 01/29/2020 | 01/29/2020 |  | 01/29/2020 | 01/29/2020
6 |  | 0 | 051200 | High |  | Shop Drawing | Structural Steel - Level 2-4 Historical |  |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 03/24/2020 | 03/26/2020 | 03/26/2020 | 03/16/2020 |  | 03/16/2020 | 03/23/2020 |  | 04/01/2020 | 03/16/2020 |  | Structural Engineers
7 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (Annex) - Updated | (Annex Structural Steel Submittal Updated from Submittal 4) B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/09/2020 | 04/03/2020 | 04/19/2020 | 01/24/2020 | 04/01/2020 | 04/09/2020 | 04/09/2020 |  | 04/16/2020 | 04/01/2020
8 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (Historic Lvl 2) | Historic Level 2 - Quatrefoil Columns B. Shop Drawings |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/22/2020 | 04/16/2020 | 04/24/2020 | 01/29/2020 | 04/14/2020 | 04/14/2020 | 04/15/2020 |  | 04/16/2020 | 04/14/2020
9 |  | 0 | 051200 | Low |  | Shop Drawing | STRUCTURAL STEEL FRAMING | Battlement Brackets B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 05/16/2020 | 05/10/2020 | 05/28/2020 | 12/19/2019 | 05/08/2020 | 05/08/2020 | 05/08/2020 |  | 05/11/2020 | 05/08/2020
10 |  | 0 | 051200 | High | DWGS - Shop Drawings | Submittal | STRUCTURAL STEEL FRAMING (Annex Tower - Updated) | (Annex Structural Steel Submittal Updated Annex Tower) B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Approved As Noted |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 10/06/2020 | 10/08/2020 | 10/08/2020 | 09/28/2020 | 09/28/2020 | 09/28/2020 | 09/30/2020 |  | 10/01/2020 | 09/28/2020 | CRSA ARCHITECTURE
11 |  | 0 | 051200 | High |  | Submittal | Structural Steel Framing - Level 4 Floor I-Beam |  |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/01/2020 | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 12/01/2020 | 12/03/2020 | 12/13/2020 | 11/23/2020 | [5 empty] | 11/23/2020
12 |  | 0 | 051200 | High |  | Submittal | STRUCTURAL STEEL FRAMING - Landscape Shed |  |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | Structural Engineers |  | 0 |  | 12/31/2020 | 12/31/2020 | 01/10/2021 | 12/31/2020 |  | 12/31/2020 | 12/31/2020 |  | 01/04/2021 | 12/31/2020
13 |  | 0 | 051200 | High |  | Submittal | STRUCTURAL STEEL FRAMING - Barrel Ceiling |  |  |  | Closed | Approved As Noted |  |  |  | Brett Glassey | Glassey Steel Works | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 02/19/2021 | 02/21/2021 | 02/21/2021 | 02/11/2021 | 02/11/2021 | 02/11/2021 | 02/24/2021 |  | 02/24/2021 | 02/11/2021
14 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (Historic North Stair) | North Stair Historic B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 03/08/2021 | 03/04/2021 | 03/08/2021 | 02/22/2021 | 02/22/2021 | 02/22/2021 | 03/16/2021 |  | 03/22/2021 | 02/22/2021
15 |  | 0 | 051200 | High |  | Shop Drawing | STRUCTURAL STEEL FRAMING (West Stair Tower) | West Stair Tower B. Shop Drawings: Show fabrication of structural-steel components. 1. Include details of cuts, connections, splices, camber, holes, and other pertinent data. 2. Include embedment Drawings. 3. Indicate welds by standard AWS symbols, distinguishing between shop and field welds, and show size, length, and type of each weld. Show backing bars that are to be removed and supplemental fillet welds where backing bars are to remain. 4. Indicate type, size, and length of bolts, distinguishing between shop and field bolts. Identify pretensioned and slip-critical, high-strength bolted connections. 5. Identify members and connections of the seismic-load-resisting system. 6. Indicate locations and dimensions of protected zones. 7. Identify demand-critical welds. 8. Identify members not to be shop primed. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 03/02/2021 | 03/04/2021 | 03/04/2021 | 02/22/2021 | 02/22/2021 | 02/22/2021 | 03/11/2021 |  | 03/16/2021 | 02/22/2021 | CRSA ARCHITECTURE
1 |  | 0 | 052100 | Low |  | Product Data | STEEL JOIST FRAMING | A. Product Data: For each type of joist, accessory, and product. A. Qualification Data: For manufacturer and professional engineer. B. Welding certificates. C. Manufacturer certificates. D. Mill Certificates: For each type of bolt. E. Comprehensive engineering analysis of special joists signed and sealed by the qualified professional engineer responsible for its preparation. |  |  | Closed |  |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/06/2020 | 12/20/2019 | 12/19/2019 | 12/20/2019 |  |  | 03/19/2021 | 12/18/2019
2 |  | 1 | 052100 | High |  | Shop Drawing | STEEL JOIST FRAMING | B. Shop Drawings: 1. Include layout, designation, number, type, location, and spacing of joists. 2. Include joining and anchorage details; bracing, bridging, and joist accessories; splice and connection locations and details; and attachments to other construction. 3. Indicate locations and details of bearing plates to be embedded in other construction. |  |  | Closed | No Exception Taken |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 03/27/2020 |  | 03/23/2020 | 03/23/2020 | 03/27/2020 |  | 03/30/2020 | 03/23/2020 |  | Structural Engineers
1 |  | 0 | 053100 | Low |  | Product Data | STEEL DECKING | A. Product Data: For each type of deck, accessory, and product indicated. A. Welding certificates. B. Product Certificates: For each type of steel deck. C. Product Test Reports: For tests performed by a qualified testing agency, indicating that each of the following complies with requirements: 1. Power-actuated mechanical fasteners. 2. Acoustical roof deck. D. Evaluation Reports: For steel deck, from ICC-ES. |  |  | Closed | Approved As Noted |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | Structural Engineers |  |  |  | 12/16/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/02/2020 |  | 01/06/2020 | 12/18/2019
2 |  | 1 | 053100 | High |  | Shop Drawing | STEEL DECKING | B. Shop Drawings: 1. Include layout and types of deck panels, anchorage details, reinforcing channels, pans, cut deck openings, special jointing, accessories, and attachments to other construction. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 | 03/25/2020 | 03/27/2020 |  | 03/23/2020 | 03/23/2020 | 03/27/2020 |  | 03/30/2020 | 03/23/2020 |  | Structural Engineers
1 |  | 0 | 054000 | Low |  | Product Data | COLD-FORMED METAL FRAMING | A. Product Data: For each type of product. A. Qualification Data: For testing agency. B. Welding certificates. C. Product Certificates: For each type of code-compliance certification for studs and tracks. D. Product Test Reports: For each listed product, for tests performed by manufacturer and witnessed by a qualified testing agency. 1. Steel sheet. 2. Expansion anchors. 3. Power-actuated anchors. 4. Mechanical fasteners. 5. Vertical deflection clips. 6. Horizontal drift deflection clips 7. Miscellaneous structural clips and accessories. E. Evaluation Reports: For nonstandard cold-formed steel framing post-installed anchors and power-actuated fasteners, from ICC-ES or other qualified testing agency acceptable to authorities having jurisdiction. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 04/17/2020 | 12/19/2019 | 03/23/2020 | 04/01/2020 | 04/15/2020 |  | 04/16/2020 | 12/18/2019
2 |  | 0 | 054000 | Low |  | Shop Drawing | COLD-FORMED METAL FRAMING | B. Shop Drawings: 1. Include layout, spacings, sizes, thicknesses, and types of cold-formed steel framing; fabrication; and fastening and anchorage details, including mechanical fasteners. 2. Indicate reinforcing channels, opening framing, supplemental framing, strapping, bracing, bridging, splices, accessories, connection details, and attachment to adjoining work. C. Delegated-Design Submittal: For cold-formed steel framing. |  |  | Closed | See Other |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 03/06/2020 | 12/19/2019 | 02/11/2020 | 02/24/2020 |  |  | 02/24/2020 | 12/18/2019
1 |  | 0 | 055000 | Low |  | Product Data | METAL FABRICATIONS | A. Product Data: For the following: 1. Nonslip aggregates and nonslip-aggregate surface finishes. 2. Fasteners. 3. Shop primers. 4. Shrinkage-resisting grout. 5. Slotted channel framing. 6. Manufactured metal ladders. 7. Ladder safety cages. 8. Metal ships' ladders and pipe crossovers. 9. Metal bollards. A. Qualification Data: For professional engineer's experience with providing delegated-design engineering services of the kind indicated, including documentation that engineer is licensed in the jurisdiction in which Project is located. B. Mill Certificates: Signed by stainless steel manufacturers, certifying that products furnished comply with requirements. C. Welding certificates. D. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers, certifying that shop primers are compatible with topcoats. E. Research Reports: For post-installed anchors. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 055000 | Low |  | Shop Drawing | METAL FABRICATIONS | B. Shop Drawings: Show fabrication and installation details. Include plans, elevations, sections, and details of metal fabrications and their connections. Show anchorage and accessory items. Provide Shop Drawings for the following: 1. Steel framing and supports for overhead doors. 2. Steel framing and supports for countertops. 3. Steel tube reinforcement for low partitions. 4. Steel framing and supports for mechanical and electrical equipment. 5. Steel framing and supports for applications where framing and supports are not specified in other Sections. 6. Elevator machine beams, hoist beams, and divider beams. 7. Steel shapes for supporting elevator door sills. 8. Steel girders for supporting wood frame construction. 9. Steel pipe columns for supporting wood frame construction. 10. Prefabricated building columns. 11. Shelf angles. 12. Metal ladders. 13. Ladder safety cages. 14. Metal ships' ladders and pipe crossovers. 15. Metal floor plate and supports. 16. Elevator pit sump covers. 17. Miscellaneous steel trim including loading-dock edge angles. 18. Metal bollards. 19. Loose steel lintels. C. Delegated-Design Submittal: For ladders, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 055113 | Low |  | Product Data | METAL PAN STAIRS | A. Product Data: For metal pan stairs and the following: 1. Shop primer products. 2. Handrail wall brackets. 3. Grout. A. Qualification Data: For professional engineer's experience with providing delegated-design engineering services of the kind indicated, including documentation that engineer is licensed in the State in which Project is located. B. Welding certificatesC. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers, certifying that shop primers are compatible with topcoats. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 055113 | High |  | Shop Drawing | METAL PAN STAIRS | B. Shop Drawings: 1. Include plans, elevations, sections, details, and attachments to other work. 2. Indicate sizes of metal sections, thickness of metals, profiles, holes, and field joints. 3. Include plan at each level. 4. Indicate locations of anchors, weld plates, and blocking for attachment of wall-mounted handrails. 5. Indicate profile and dimensions of precast terrazzo treads. 6. Indicate profile and dimensions of epoxy-resin-filled treads. D. Delegated-Design Submittal: For stairs, railings and guards,, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 08/18/2020 | 12/19/2019 | 08/02/2020 | 08/11/2020 | 08/17/2020 |  | 08/17/2020 | 12/18/2019
3 |  | 0 | 055113 | Low | Samples | Submittal | METAL PAN STAIRS | C. Samples for Verification: For each type and finish of nosing. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 055113 | High |  | Submittal | Stairs 4, 6 & 10 - Shop Drawings |  |  |  | Closed | Note Markings |  |  |  | Brett Glassey | Glassey Steel Works | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 07/02/2021 | 07/04/2021 | 07/09/2021 |  | 06/24/2021 | 06/24/2021 | 07/13/2021 |  | 07/14/2021 | 06/24/2021
1 |  | 0 | 055119 | Low |  | Product Data | METAL GRATING STAIRS | A. Product Data: For metal grating stairs and the following: 1. Gratings. 2. Shop primer products. 3. Grout. A. Qualification Data: For professional engineer's experience with providing delegated-design engineering services of the kind indicated, including documentation that engineer is licensed in the [jurisdiction] [State] in which Project is located. B. Welding certificatesC. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers, certifying that shop primers are compatible with topcoats. |  |  | Closed | See Other |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
2 |  | 0 | 055119 | Low |  | Shop Drawing | METAL GRATING STAIRS | B. Shop Drawings: 1. Include plans, elevations, sections, details, and attachment to other work. 2. Indicate sizes of metal sections, thickness of metals, profiles, holes, and field joints. 3. Include plan at each level. 4. Indicate locations of anchors, weld plates, and blocking for attachment of wall-mounted handrails. C. Delegated-Design Submittal: For stairs[, railings, and guards], including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Closed | See Other |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
1 |  | 0 | 055213 | Low |  | Product Data | PIPE AND TUBE RAILINGS | A. Product Data: For the following: 1. Manufacturer's product lines of mechanically connected railings. 2. Railing brackets. 3. Grout, anchoring cement, and paint products. A. Qualification Data: For testing agency. B. Welding certificates. C. Mill Certificates: Signed by manufacturers of stainless-steel products certifying that products furnished comply with requirements. D. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers certifying that shop primers are compatible with topcoats. E. Product Test Reports: For pipe and tube railings, for tests performed by a qualified testing agency, according to ASTM E894 and ASTM E935. F. Evaluation Reports: For post-installed anchors, from ICC-ES. |  |  | Closed | See Other |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
2 |  | 0 | 055213 | Low |  | Shop Drawing | PIPE AND TUBE RAILINGS | B. Shop Drawings: Include plans, elevations, sections, details, and attachments to other work. D. Delegated-Design Submittal: For railings, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Closed | See Other |  |  |  | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
3 |  | 0 | 055213 | Low | Samples | Submittal | PIPE AND TUBE RAILINGS | C. Samples: For each type of exposed finish required. 1. Sections of each distinctly different linear railing member, including handrails, top rails, posts, and balusters, including finish. 2. Fittings and brackets. 3. Assembled Sample of railing system, made from full-size components, including top rail, post, handrail, and infill. Sample need not be full height. a. Show method of connecting and finishing members at intersections. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 055313 | Low |  | Product Data | BAR GRATINGS | A. Product Data: For the following: 1. Clips and anchorage devices for gratings. 2. Paint products. B. Sustainable Design Submittals: A. Mill Certificates: Signed by manufacturers of stainless steel certifying that products furnished comply with requirements. B. Welding certificates. C. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers certifying that shop primers are compatible with topcoats. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 055313 | Low |  | Shop Drawing | BAR GRATINGS | C. Shop Drawings: Include plans, sections, details, and attachments to other work. D. Delegated-Design Submittal: For gratings, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Assigned to Sub |  | Brett Glassey | Glassey Steel Works | 12/16/2019 | Brett Glassey | Glassey Steel Works | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 057000 | Low | Mock-up - Mock-ups use this package. | Mock-Up | DECORATIVE METAL | F. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for fabrication and installation. 1. Build mockups for the following types of decorative metal: a. Bronze casting samples of each type.. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. E. Samples for Verification: For each type of exposed finish. 1. Sections of linear shapes. 2. Full-size Samples of castings and forgings. a. For custom castings, submit finished Samples showing ability to reproduce detail, cast-metal color, and quality of finish. 3. Samples of welded and brazed joints showing quality of workmanship and color matching of materials. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 057000 | Low |  | Product Data | DECORATIVE METAL | A. Product Data: For each type of product, including finishing materials. C. Patterns, Models, or Plaster Castings: Made from proposed patterns for each design of custom casting requiredA. Qualification Data: For fabricator organic-coating applicator. B. Mill Certificates: Signed by manufacturers of stainless steel certifying that products furnished comply with requirements. C. Welding certificates. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 057000 | Low |  | Shop Drawing | DECORATIVE METAL - Veil Frame Stainless Steel Arm | B. Shop Drawings: Show fabrication and installation details for decorative metal. 1. Include plans, elevations, component details, and attachment details. 2. Indicate materials and profiles of each decorative metal member, fittings, joinery, finishes, fasteners, anchorages, and accessory items. |  |  | Closed | Approved As Noted |  |  |  | Jeremy Drake | Ducworks Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/16/2020 |  |  | 12/19/2019 |  | 10/14/2020 | 12/03/2020 |  | 12/07/2020 | 12/18/2019
4 |  | 0 | 057000 | Low | Samples | Submittal | DECORATIVE METAL | D. Samples for Initial Selection: For products involving selection of color, texture, or design including mechanical finishes. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 057000 | Medium | DWGS - Shop Drawings | Submittal | Decorative Metal Bracket - Finish Selection | Please submit a Shop Drawing for the decorative countertop bracket. |  |  | Closed | Make Corrections Noted |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Westland PE’s |  | Interior Designer |  | 0 |  | 04/15/2021 | 04/17/2021 | 04/27/2021 | 04/07/2021 | 05/13/2021 | 05/13/2021 | 05/25/2021 |  | 06/02/2021 | 04/07/2021
1 |  | 0 | 057100 | Low |  | Product Data | DECORATIVE METAL STAIRS | A. Product Data: For metal stairs A. Qualification Data: For professional engineer's experience with providing delegated-design engineering services of the kind indicated, including documentation that the engineer is licensed in the State in which Project is located. B. Welding certificates. C. Paint Compatibility Certificates: From manufacturers of topcoats applied over shop primers, certifying that shop primers are compatible with topcoats. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 057100 | Low |  | Shop Drawing | DECORATIVE METAL STAIRS | B. Shop Drawings: 1. Include plans, elevations, sections, details, and attachments to other work. 2. Indicate sizes of metal sections, thickness of metals, profiles, holes, and field joints. 3. Include plan at each level. D. Delegated-Design Submittal: For stairs, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 057100 | Low | Samples | Submittal | DECORATIVE METAL STAIRS | C. Samples for Verification: For each type and finish of tread. |  |  | Draft | [6 empty] | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 057300 | Low | Mock-up - Mock-ups use this package. | Mock-Up | DECORATIVE METAL RAILINGS | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for fabrication and installation. 1. Build mockups as shown on Drawings. 2. Build mockups for each form and finish of railing consisting of two posts, top rail, infill area, and anchorage system components that are full height and are not less than 24 inches (600 mm) in length. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. D. Samples for Verification: For each type of exposed finish required. 1. Sections of each distinctly different linear railing member, including handrails, top rails, posts, and balusters. 2. Fittings and brackets. 3. Welded connections. 4. Brazed connections. 5. Assembled Samples of railing systems, made from full-size components, including top rail, post, handrail, and infill. Show method of finishing members at intersections. Samples need not be full height. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. | 01/16/2020 | Jeremy Drake | Ducworks Inc. | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 057300 | Low |  | Product Data | DECORATIVE METAL RAILINGS | A. Product Data: For the following: 1. Manufacturer's product lines of railings assembled from standard components. 2. Grout, anchoring cement, and paint products. A. Qualification Data: For professional engineer. B. Mill Certificates: Signed by manufacturers of stainless steel products certifying that products furnished comply with requirements. C. Welding certificates. D. Product Test Reports: Based on evaluation of comprehensive tests performed by a qualified testing agency, according to ASTM E894 and ASTM E935. E. Preconstruction test reports. F. Evaluation Reports: For post-installed anchors, from ICC-ES. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. | 01/16/2020 | Jeremy Drake | Ducworks Inc. | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 057300 | Low |  | Shop Drawing | DECORATIVE METAL RAILINGS | B. Shop Drawings: Include plans, elevations, sections, and attachment details. 1. For illuminated railings, include wiring diagrams and roughing-in details. E. Delegated-Design Submittal: For installed products indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. | 01/16/2020 | Jeremy Drake | Ducworks Inc. | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 057300 | Low | Samples | Submittal | DECORATIVE METAL RAILINGS | C. Samples for Initial Selection: For products involving selection of color, texture, or design, including mechanical finishes. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. | 01/16/2020 | Jeremy Drake | Ducworks Inc. | Westland PE’s | [5 empty] | 01/16/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 061000 | Low |  | Product Data | ROUGH CARPENTRY | A. Product Data: For each type of process and factory-fabricated product. Indicate component materials and dimensions and include construction and application details. 1. Include data for wood-preservative treatment from chemical treatment manufacturer and certification by treating plant that treated materials comply with requirements. Indicate type of preservative used and net amount of preservative retained. 2. Include data for fire-retardant treatment from chemical treatment manufacturer and certification by treating plant that treated materials comply with requirements. Include physical properties of treated materials based on testing by a qualified independent testing agency. 3. For fire-retardant treatments, include physical properties of treated lumber both before and after exposure to elevated temperatures, based on testing by a qualified independent testing agency according to ASTM D5664. 4. For products receiving a waterborne treatment, include statement that moisture content of treated materials was reduced to levels specified before shipment to Project site. A. Material Certificates: For dimension lumber specified to comply with minimum allowable unit stresses. Indicate species and grade selected for each use and design values approved by the ALSC Board of Review. B. Evaluation Reports: For the following, from ICC-ES: 1. Wood-preservative-treated wood. 2. Fire-retardant-treated wood. 3. Engineered wood products. 4. Shear panels. 5. Power-driven fasteners. 6. Post-installed anchors. 7. Metal framing anchors. |  |  | Closed | No Exception Taken |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/31/2020 |  |  | 11/30/2020 |  |  |  |  | 04/22/2021 | 12/18/2019
2 |  | 0 | 061000 | Low |  | Shop Drawing | ROUGH CARPENTRY | B. Fastener Patterns: Full-size templates for fasteners in exposed framing. |  |  | Closed | No Exception Taken |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/31/2020 |  |  | 11/30/2020 |  |  |  |  | 04/22/2021 | 12/18/2019
1 |  | 0 | 061600 | Low |  | Product Data | SHEATHING | A. Product Data: For each type of process and factory-fabricated product. Indicate component materials and dimensions and include construction and application details. 1. Include data for wood-preservative treatment from chemical treatment manufacturer and certification by treating plant that treated plywood complies with requirements. Indicate type of preservative used and net amount of preservative retained. 2. Include data for fire-retardant treatment from chemical treatment manufacturer and certification by treating plant that treated plywood complies with requirements. Include physical properties of treated materials. 3. For fire-retardant treatments, include physical properties of treated plywood both before and after exposure to elevated temperatures, based on testing by a qualified independent testing agency according to ASTM D5516. 4. For products receiving waterborne treatment, include statement that moisture content of treated materials was reduced to levels specified before shipment to Project site. 5. For air-barrier and water-resistant glass-mat gypsum sheathing, include manufacturer's technical data and tested physical and performance properties of products. A. Product Certificates: From air-barrier and water-resistant glass-mat gypsum sheathing manufacturer, certifying compatibility of sheathing accessory materials with Project materials that connect to or that come in contact with the sheathing. B. Product Test Reports: For each air-barrier and water-resistant glass-mat gypsum sheathing assembly, indicating compliance with specified requirements, for tests performed by a qualified testing agency. C. Evaluation Reports: For the following, from ICC-ES: 1. Wood-preservative-treated plywood. 2. Air-barrier and water-resistant glass-mat gypsum sheathing. |  |  | Closed | No Exception Taken |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/31/2020 |  |  | 11/30/2020 |  |  |  |  | 04/22/2021 | 12/18/2019
2 |  | 0 | 061600 | Low |  | Shop Drawing | SHEATHING | B. Shop Drawings: For air-barrier and water-resistant glass-mat gypsum sheathing assemblies. 1. Show locations and extent of sheathing, accessories, and assemblies specific to Project conditions. 2. Include details for sheathing joints and cracks, counterflashing strips, penetrations, inside and outside corners, terminations, and tie-ins with adjoining construction. 3. Include details of interfaces with other materials that form part of air barrier. |  |  | Closed | No Exception Taken |  |  |  | Westland PE’s |  | Westland PE’s | [5 empty] | 12/31/2020 |  |  | 11/30/2020 |  |  |  |  | 04/22/2021 | 12/18/2019
2 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 1) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 05/31/2020 | 12/19/2019 | 04/01/2020 | 04/28/2020 | 08/20/2020 |  | 08/20/2020 | 12/18/2019 |  | Interior Designer
4 |  | 0 | 064023 | Medium | Mock-up - Mock-ups use this package. | Mock-Up | INTERIOR ARCHITECTURAL WOODWORK - Alter End (Fetz# 10) | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Build mockups of typical interior architectural woodwork as shown on Drawings May be built in place in place. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Owner specifically approves such deviations by Change Order. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. E. Samples for Verification: For the following: 1. Lumber for Transparent Finish: Not less than 5 inches (125 mm) wide by 12 inches (300 mm) long, for each species and cut, finished on one side and one edge. 2. Veneer Leaves: Representative of and selected from flitches to be used for transparent-finished interior architectural woodwork. 3. Lumber and Panel Products with Shop-Applied Opaque Finish: 5 inches (125 mm) wide by 12 inches (300 mm) long for lumber and 8 by 10 inches (200 by 250 mm) for panels, for each finish system and color. a. Finish entire exposed surface. |  |  | Closed | No Exception Taken |  |  |  | Paul Burningham | Fetzer`s Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  |  | 12/19/2019 |  | 11/11/2020 | 11/23/2020 |  | 11/30/2020 | 12/18/2019
6 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 2) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/03/2020 | 04/24/2020 | 05/31/2020 | 03/26/2020 | 04/22/2020 | 04/28/2020 | 08/20/2020 |  | 08/20/2020 | 03/26/2020 |  | Interior Designer
7 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 3) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/03/2020 | 05/13/2020 | 05/31/2020 | 03/26/2020 | 05/11/2020 | 05/12/2020 | 08/20/2020 |  | 08/20/2020 | 03/26/2020
8 |  | 0 | 064023 | High |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 4) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | See Other |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 04/25/2020 | 05/13/2020 | 05/31/2020 | 04/17/2020 | 05/11/2020 | 05/12/2020 | 01/07/2021 |  | 01/07/2021 | 04/17/2020
9 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 5) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/25/2020 | 05/30/2020 | 07/09/2020 | 04/17/2020 | 05/28/2020 | 06/23/2020 | 08/25/2020 |  | 08/26/2020 | 04/17/2020
10 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 6) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/25/2020 | 07/04/2020 | 07/23/2020 | 04/17/2020 | 07/02/2020 | 07/09/2020 | 09/16/2020 |  | 09/18/2020 | 04/17/2020
11 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 7) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Approved As Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/25/2020 | 08/12/2020 | 10/31/2020 | 08/11/2020 | 09/30/2020 | 10/15/2020 | 12/02/2020 |  | 12/02/2020 | 04/17/2020
12 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 8) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed |  |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/25/2020 | 04/27/2020 | 11/07/2020 | 04/17/2020 | 10/07/2020 | 10/28/2020 | 12/02/2020 |  | 12/02/2020 | 04/17/2020
13 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 9) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Approved As Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/25/2020 | 04/27/2020 | 11/07/2020 | 04/17/2020 | 10/24/2020 | 10/28/2020 | 12/02/2020 |  | 12/02/2020 | 04/17/2020
15 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 11) | These woodwork Shop Drawings will be incrementally submitted as they become available. B. Shop Drawings: 1. Include the following: a. Dimensioned plans, elevations, and sections. b. Attachment details. 2. Show large-scale details. 3. Show locations and sizes of furring, blocking, and hanging strips, including blocking and reinforcement concealed by construction and specified in other Sections. 4. Apply AWI Quality Certification or WI Certified Compliance Program label to Shop Drawings. |  |  | Closed | Approved As Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 11/29/2020 | 12/01/2020 | 12/03/2020 | 11/22/2020 | 11/23/2020 | 11/23/2020 | 12/02/2020 |  | 12/02/2020 | 11/22/2020
16 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (Fetz# 12) | Man door mockup |  |  | Closed | No Exception Taken |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 11/29/2020 | 12/01/2020 | 12/17/2020 | 11/22/2020 | 12/03/2020 | 12/07/2020 | 12/15/2020 |  | 12/18/2020 | 11/22/2020
17 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (Fetz 13) | Product Data for Glues Screws and Fasteners |  |  | Closed | No Exception Taken |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 11/29/2020 | 12/01/2020 | 02/19/2021 | 11/22/2020 | 12/10/2020 | 02/09/2021 | 03/05/2021 |  | 03/11/2021 | 11/22/2020
18 |  | 0 | 064023 | Low |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (Fetz #14 Admin Area Handle) | Handle in the Admin Area |  |  | Closed | Approved |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 11/29/2020 | 12/01/2020 | 01/18/2021 | 11/22/2020 | 12/31/2020 | 01/08/2021 | 02/24/2021 |  | 03/05/2021 | 11/22/2020
19 |  | 0 | 064023 | Medium |  | Submittal | Color Samples (Fetz_15) GHID |  |  |  | Closed | Approved |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 11/29/2020 | 12/01/2020 | 01/28/2021 | 11/22/2020 | 01/13/2021 | 01/18/2021 | 03/10/2021 |  | 03/11/2021 | 11/22/2020
20 |  | 0 | 064023 | High |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK (DWG SUB 16) |  |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 02/10/2021 | 02/12/2021 | 02/12/2021 | 02/02/2021 | 02/02/2021 | 02/02/2021 | 03/02/2021 |  | 03/11/2021 | 02/02/2021
21 |  | 1 | 064023 | Medium |  | Submittal | INTERIOR ARCHITECTURAL WOODWORK – Stair Tread |  |  |  | Assigned to Sub |  | Paul Burningham | Fetzer`s Inc. | 05/05/2021 | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 05/05/2021 | 05/07/2021 | 05/17/2021 | 06/02/2021 | [5 empty] | 06/02/2021
22 |  | 0 | 064023 | Medium |  | Submittal | Stair Balusters (Fetz 21a) |  |  |  | Closed | No Exception Taken |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/02/2021 | 07/04/2021 | 07/14/2021 |  | 06/24/2021 | 07/08/2021 | 07/08/2021 |  | 07/09/2021 | 06/24/2021
23 |  | 0 | 064023 | Medium |  | Submittal | Handrail Bracket (Fetz 21b) |  |  |  | Closed | No Exception Taken |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/03/2021 | 07/05/2021 | 07/02/2021 |  | 06/25/2021 | 06/25/2021 | 07/07/2021 |  | 07/08/2021 | 06/25/2021
24 |  | 0 | 064023 | Medium |  | Submittal | Level 3 & 5 Arched Openings - Shop Drawings |  |  |  | Assigned to Sub |  | Paul Burningham | Fetzer`s Inc. | 07/16/2021 | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/16/2021 | 07/18/2021 | 07/28/2021 | 07/08/2021 | [5 empty] | 07/08/2021
25 |  | 0 | 064023 | Medium |  | Submittal | Fire Rated Doors Near West Stair - Shop Drawings |  |  |  | Assigned to Sub |  | Paul Burningham | Fetzer`s Inc. | 07/16/2021 | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/16/2021 | 07/18/2021 | 07/28/2021 | 07/08/2021 | [5 empty] | 07/08/2021
1 |  | 1 | 064113 | Low | Mock-up - Mock-ups use this package. | Mock-Up | ARCHITECTURAL CABINETS (Fetz 17) GHID | C. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Build mockups of typical architectural cabinets as shown on Drawings Including a drawer and cabinet and adjustable shelf 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Paul Burningham | Fetzer`s Inc. | 12/16/2019 | Paul Burningham | Fetzer`s Inc. | Westland PE’s |  | Interior Designer |  |  |  | 12/16/2019 |  | 03/04/2021 | 03/10/2021 | [5 empty] | 03/10/2021
2 |  | 0 | 064113 | High | DWGS - Shop Drawings | Mock-Up | ARCHITECTURAL CABINETS - Graining Plan |  |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE | [5 empty] | 04/09/2021 | 03/10/2021 | 04/02/2021 | 04/02/2021 | 04/06/2021 |  | 04/09/2021 | 04/02/2021
3 |  | 0 | 064113 | High | DWGS - Shop Drawings | Mock-Up | ARCHITECTURAL CABINETS - Color Samples |  |  |  | Closed | Approved |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 04/22/2021 | 04/24/2021 | 04/24/2021 | 04/14/2021 | 04/02/2021 | 04/14/2021 | 04/21/2021 |  | 04/22/2021 | 04/14/2021
4 |  | 0 | 064113 | Medium |  | Submittal | Lock Samples Brass, Bronze, Black, & Old English (Fetz 22) |  |  |  | Closed | Make Corrections Noted |  |  |  | Paul Burningham | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/14/2021 | 07/16/2021 | 07/26/2021 |  | 07/06/2021 | 07/13/2021 | 07/13/2021 |  | 07/14/2021 | 07/06/2021
1 |  | 0 | 070150 | Low |  | Product Data | PREPARATION FOR REROOFING | A. Product Data: For each type of product. B. Temporary Roofing Submittal: Product data and description of temporary roofing system. 1. If temporary roof remains in place, include surface preparation requirements needed to receive permanent roof, and submit a letter from roofing manufacturer stating acceptance of the temporary roof and that its inclusion does not adversely affect the new roofing system's resistance to fire and wind. |  |  | Closed | Not Applicable |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 07/01/2020 | 12/18/2019
1 |  | 0 | 071326 | Low | Mock-up - Mock-ups use this package. | Mock-Up | SELF-ADHERING SHEET | B. Mockups: Build mockups to verify selections made under Sample submittals and to set quality standards for installation. 1. Build for each typical waterproofing installation including[ pavers and] accessories to demonstrate surface preparation, crack and joint treatments, inside and outside corner treatments, and protection. a. Size: [100 sq. ft. in area] [As indicated on Drawings]. b. Description: Each type of [wall] [deck] [and] [plaza] installation. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Zann Call | Specialty Systems Incorporated | 12/01/2020 | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
4 |  | 0 | 071326 | Low | Samples | Submittal | SELF-ADHERING SHEET WATERPROOFING | D. Samples: For each exposed product and for each color and texture specified, including the following products: 1. 8-by-8-inch square of waterproofing and flashing sheet. 2. 4-by-4-inch square of drainage panel. 1. 12-by-12-inch filter fabric materials. 2. 12-by-12-inch drainage layer materials. 3. 12-by-12-inch molded drainage panel. 4. Plaza-deck paver, [full sized], in each color and texture required. 5. Paver pedestal assembly. |  |  | Closed | Not Submitted |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s | [5 empty] | 05/22/2020 |  |  | 05/20/2020 |  |  |  |  | 07/22/2020 | 12/18/2019
2 |  | 1 | 071326 | High |  | Product Data | SELF-ADHERING SHEET WATERPROOFING | A. Product Data: For each type of product, including membrane, adhesives, sealant and accessories 1. Include construction details, material descriptions, and tested physical and performance properties of waterproofing. 2. Include manufacturer's written instructions for evaluating, preparing, and treating substrate. A. Qualification Data: For Installer. B. Research Reports: For modified bituminous sheet waterproofing/termite barrier, showing compliance with ICC AC380. C. Field quality-control reports. D. Sample Warranties: For special warranties. |  |  | Closed | No Exception Taken |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 03/13/2020 |  | 03/10/2020 | 03/10/2020 | 03/12/2020 |  | 03/12/2020 | 03/09/2020
3 |  | 1 | 071326 | High |  | Shop Drawing | SELF-ADHERING SHEET WATERPROOFING | Underslab Waterproofing C. Shop Drawings: Show locations and extent of waterproofing and details of substrate joints and cracks, expansion joints, sheet flashings, penetrations, inside and outside corners, tie-ins with adjoining waterproofing, and other termination conditions. 1. Include setting drawings showing layout, sizes, sections, profiles, and joint details of pedestal-supported concrete pavers. |  |  | Closed |  |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 04/10/2020 |  | 03/26/2020 | 04/01/2020 |  |  | 04/23/2020 | 03/26/2020
5 |  | 0 | 071326 | High |  | Shop Drawing | SELF-ADHERING SHEET WATERPROOFING | Exterior Foundation Waterproofing C. Shop Drawings: Show locations and extent of waterproofing and details of substrate joints and cracks, expansion joints, sheet flashings, penetrations, inside and outside corners, tie-ins with adjoining waterproofing, and other termination conditions. 1. Include setting drawings showing layout, sizes, sections, profiles, and joint details of pedestal-supported concrete pavers. |  |  | Closed | Approved |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 07/01/2020 | 06/25/2020 | 07/03/2020 | 06/23/2020 | 06/23/2020 | 06/23/2020 | 07/07/2020 |  | 07/09/2020 | 06/23/2020
1 |  | 0 | 071353 | Low |  | Submittal | ELASTOMERIC SHEET WATERPROOFING | B. Product Data: Submit manufacturer’s product data, including surface preparation, application, and curing. D. Applicator’s Project References: Submit list of completed project references. E. Certification of Applicator’s Supervisor: Submit for applicator’s supervisor a certificate indicating completion of manufacture’s contractor training program. |  |  | Assigned to Sub |  | Grant Christlieb | Specialty Systems Inc. | 05/22/2020 | Grant Christlieb | Specialty Systems Inc. | Westland PE’s | [5 empty] | 05/22/2020 |  |  | 05/20/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 071353 | Low | Samples | Submittal | ELASTOMERIC SHEET WATERPROOFING | C. Samples: Submit 2-inch by 2-inch samples for approval by the Engineer. 1. Cured high-performance coating, 60 mils thick. |  |  | Assigned to Sub |  | Grant Christlieb | Specialty Systems Inc. | 05/22/2020 | Grant Christlieb | Specialty Systems Inc. | Westland PE’s | [5 empty] | 05/22/2020 |  |  | 05/20/2020 | [5 empty] | 12/18/2019
1 |  | 0 | 071413 | Low | Mock-up - Mock-ups use this package. | Submittal | RUBBERIZED ASPHALT WATERPROOFING | C. Mockups: Install waterproofing to 100 sq. ft. (9.3 sq. m) of deck wall to demonstrate surface preparation, crack and joint treatment, corner treatment, thickness, texture, and execution quality. 1. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. |  |  | Closed | Not Applicable |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s | [5 empty] | 05/22/2020 |  |  | 05/20/2020 |  |  |  |  | 07/29/2020 | 12/18/2019
2 |  | 1 | 071413 | High |  | Submittal | RUBBERIZED ASPHALT WATERPROOFING | A. Product Data: For each type of product. Include manufacturer's written instructions for evaluating, preparing, and treating substrate, technical data, and tested physical and performance properties of waterproofing. A. Qualification Data: For Installer. C. Sample Warranties: For special warranties. |  |  | Closed | No Exception Taken |  |  |  | Grant Christlieb | Specialty Systems Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 05/22/2020 |  | 07/06/2020 | 05/20/2020 | 06/23/2020 | 06/23/2020 | 07/21/2020 |  | 07/22/2020 | 03/09/2020
1 |  | 0 | 071620 | High |  | Submittal | FOUNTAIN CRYSTALLINE WATERPROOFING | B. Product Data: Manufacturer's printed data sheet, for specified products. C. Test Reports: Certified test reports showing compliance with specified performance characteristics and physical properties. 1. Testing Agency: Independent laboratory meeting the requirements of ASTM E 329 and certified by the United States Bureau of Standards. D. Certificates: Product certificates signed by manufacturer certifying that: 1. Materials comply with specified performance characteristics and physical requirements. 2. Installer is qualified and approved by manufacturer.E. Manufacturer's installation instructions. |  |  | Closed | See Other |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [5 empty] | 07/31/2020 |  |  | 05/20/2020 |  |  |  |  | 07/27/2020 | 12/18/2019
1 |  | 0 | 072100 | Low |  | Product Data | THERMAL INSULATION | A. Product Data: For each type of product. A. Product Test Reports: For each product, for tests performed by a qualified testing agency. B. Evaluation Reports: For foam-plastic insulation, from ICC-ES. |  |  | Closed | No Exception Taken |  |  |  | Gary Tonks | Tonks Insulation, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/07/2019 |  | 02/14/2020 | 12/19/2019 | 01/17/2020 | 01/29/2020 | 03/18/2020 |  | 03/26/2020 | 12/18/2019
2 |  | 0 | 072100 | Low |  | Product Data | THERMAL INSULATION | Batt Insulation per Scott's note on Submittal 1. |  |  | Closed | No Exception Taken |  |  |  | Gary Tonks | Tonks Insulation, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 04/03/2020 | 03/28/2020 | 04/11/2020 | 03/26/2020 | 03/26/2020 | 04/01/2020 | 05/26/2020 |  | 06/09/2020 | 03/26/2020
1 |  | 0 | 072119 | Low |  | Product Data | FOAMED-IN-PLACE INSULATION | A. Product Data: For each type of product. A. Qualification Data: For Installer. B. Installation instructions: Manufacturer’s installation instructions for project applications and substrates, include surface preparation. C. Product Test Reports: For each product, for tests performed by a qualified testing agency. D. Evaluation Reports: For spray-applied polyurethane foam-plastic insulation, from ICC-ES. |  |  | Closed | No Exception Taken |  |  |  | Gary Tonks | Tonks Insulation, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/07/2019 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
1 |  | 0 | 072600 | Low |  | Product Data | VAPOR RETARDERS - Concrete | A. Product Data: For each type of product. A. Product Test Reports: For each product, for tests performed by a qualified testing agency. |  |  | Closed | No Exception Taken |  |  |  | Stormy Carlisle | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/01/2020 |  | 12/22/2020 | 11/30/2020 | 12/02/2020 | 12/08/2020 | 12/10/2020 |  | 12/11/2020 | 12/18/2019
2 |  | 0 | 072600 | Low |  | Product Data | VAPOR RETARDERS - EIFS | A. Product Data: For each type of product. A. Product Test Reports: For each product, for tests performed by a qualified testing agency. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 12/08/2020 | Clinton Phillips | R. Phillips Plastering LLC | Camron Walker | Westland Construction, Inc. |  |  |  |  | 12/08/2020 | 12/10/2020 | 12/20/2020 | 11/30/2020 | [5 empty] | 11/30/2020
1 |  | 0 | 072726 | Low | Mock-up - Mock-ups use this package. | Mock-Up | FLUID-APPLIED MEMBRANE AIR BARRIERS | A. Preinstallation Conference: Conduct conference at Project site. 1. Review air-barrier requirements and installation, special details, mockups, air-leakageand bond testing, air-barrier protection, and work scheduling that covers air barriers. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Miguel Brito | Waterproofing West | 11/02/2020 | Miguel Brito | Waterproofing West | Westland PE’s | [5 empty] | 11/02/2020 |  |  | 10/29/2020 | 10/29/2020 |  |  |  |  | 12/18/2019
2 |  | 0 | 072726 | High |  | Product Data | FLUID-APPLIED MEMBRANE AIR BARRIERS | A. Product Data: For each type of product. 1. Include manufacturer's written instructions for evaluating, preparing, and treating substrate; technical data; and tested physical and performance properties of productsA. Qualification Data: For Installer. Include list of ABAA-certified installers and supervisors employed by the Installer, who work on Project. C. Product Test Reports: For each air-barrier assembly, for tests performed by a qualified testing agency. B. Product Certificates: From air-barrier manufacturer, certifying compatibility of air barriers and accessory materials with Project materials that connect to or that come in contact with the barrier. |  |  | Closed | No Exception Taken |  |  |  | Miguel Brito | Waterproofing West | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 11/02/2020 |  | 11/11/2020 | 10/28/2020 | 10/28/2020 | 10/28/2020 | 11/12/2020 |  | 11/13/2020 | 12/18/2019
3 |  | 0 | 072726 | Low |  | Shop Drawing | FLUID-APPLIED MEMBRANE AIR BARRIERS | B. Shop Drawings: Project specific shop drawings for air-barrier assemblies. 1. Show locations and extent of air barrier. Include details for substrate joints and cracks, counterflashing strips, penetrations, inside and outside corners, terminations, and tie-ins with adjoining construction. 2. Include details of interfaces with other materials that form part of air barrier. |  |  | Assigned to Sub |  | Miguel Brito | Waterproofing West | 11/02/2020 | Miguel Brito | Waterproofing West | Westland PE’s | [5 empty] | 11/02/2020 |  |  | 10/29/2020 | 10/29/2020 |  |  |  |  | 12/18/2019
1 |  | 0 | 075419 | High |  | Product Data | POLYVINYL-CHLORIDE ROOFING- PVC | 1. Product Data: a. Manufacturer's literature or cut sheet for each element of system. b. Manufacturer’s preparation and installation instructions and recommendations. 1. Certificates: a. Installer’s signed certificate stating roofing system complies with Contract Documents performance requirements and work only performed by trained and authorized personnel in those procedures. b. Manufactures signed certificate that roof system has been inspected by Technical Service Representative and stating no deviation from system specified or approved shop drawings without written approval by Owner Representative and Manufacturer. d. Provide recycling certificate. 2. Test And Evaluation Reports: Submit evidence that roof system has been tested and approved or listed as follows: a. Submit evidence that roof system has been tested and approved or listed to meet Factory Mutual Research Corporation (FM) Classification required for this Project. b. Submit evidence that roof system has been tested to meet UL Class requirement required for fire-resistance rating for this Project. a) Submit Notice of Acceptance (NOA) documentation to show compliance. 3. Manufacturer Instructions: a. Two (2) copies of Roofing Manufacturer's published instructions for Architect and maintain one (1) at job-site. 4. Special Procedure Submittals: a. Installer to fill out 'Roof Manufacturer' Installer Workmanship Warranty' and 'Manufacturer System Warranty' from information provided in the Attachment 'Roofing Manufacturer’s Information For Architect' from Manufacturer and from Architect. Warranties are to be included in Closeout Submittals. |  |  | Closed | No Exception Taken |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 05/26/2020 | 12/19/2019 | 04/14/2020 | 05/12/2020 | 05/26/2020 |  | 06/09/2020 | 12/18/2019
3 |  | 0 | 075419 | High | Samples | Submittal | POLYVINYL-CHLORIDE ROOFING: PVC | Walk-off Mat Sample |  |  | Closed | Make Corrections Noted |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 07/10/2020 | 12/19/2019 | 06/24/2020 | 06/24/2020 | 06/29/2020 |  | 06/29/2020 | 12/18/2019
4 |  | 0 | 075419 | High |  | Submittal | POLYVINYL-CHLORIDE ROOFING: PVC | Walk-off Mat Product Data |  |  | Closed | No Exception Taken |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 07/07/2020 | 07/02/2020 | 07/19/2020 | 06/29/2020 | 06/30/2020 | 06/30/2020 | 07/07/2020 |  | 07/09/2020 | 06/29/2020
2 |  | 0 | 076200 | High |  | Submittal | SHEET METAL FLASHING AND TRIM | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for each manufactured product and accessory. A. Qualification Data: For fabricator. B. Product Certificates: For each type of coping and roof edge flashing that is SPRI ES-1 tested and FM Approvals approved. C. Product Test Reports: For each product, for tests performed by a qualified testing agency. D. Sample Warranty: For special warranty. B. Shop Drawings: For sheet metal flashing and trim. 1. Include plans, elevations, sections, and attachment details. 2. Detail fabrication and installation layouts, expansion-joint locations, and keyed details. Distinguish between shop- and field-assembled work. 3. Include identification of material, thickness, weight, and finish for each item and location in Project. 4. Include details for forming, including profiles, shapes, seams, and dimensions. 5. Include details for joining, supporting, and securing, including layout and spacing of fasteners, cleats, clips, and other attachments. Include pattern of seams. 6. Include details of termination points and assemblies. 7. Include details of expansion joints and expansion-joint covers, including showing direction of expansion and contraction from fixed points. 8. Include details of roof-penetration flashing. 9. Include details of edge conditions, including eaves, ridges, valleys, rakes, crickets, and counterflashings as applicable. 10. Include details of special conditions. 11. Include details of connections to adjoining work. 12. Detail formed flashing and trim at scale of not less than 1-1/2 inches per 12 inches (1:10). |  |  | Closed | No Exception Taken |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 11/05/2020 | 12/19/2019 | 10/22/2020 | 10/22/2020 | 11/04/2020 |  | 11/04/2020 | 12/18/2019
1 |  | 0 | 078100 | Low | Mock-up - Mock-ups use this package. | Mock-Up | APPLIED FIREPROOFING | B. Mockups: Build mockups to verify selections made under Sample submittals and to demonstrate aesthetic effects to set quality standards for materials and execution and for preconstruction testing. 1. Build mockup of each type of fireproofing and different substrate as shown on Drawings. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. J. Provide a uniform finish complying with description indicated for each type of fireproofing material and matching finish approved for required mockups. |  |  | Assigned to Sub |  | Zann Call | Specialty Systems Incorporated | 03/03/2020 | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 03/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 078100 | Low |  | Product Data | APPLIED FIREPROOFING | A. Product Data: For each type of product. (may have been submitted previously)A. Qualification Data: For Installer and testing agency. B. Product Certificates: For each type of fireproofing. C. Evaluation Reports: For fireproofing, from ICC-ES. D. Preconstruction Test Reports: For fireproofing. |  |  | Closed | No Exception Taken |  |  |  | Zann Call | Specialty Systems Incorporated | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/24/2019 |  | 01/17/2020 | 12/19/2019 | 12/31/2019 | 01/01/2020 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
3 |  | 0 | 078100 | Low |  | Shop Drawing | APPLIED FIREPROOFING | B. Shop Drawings: Framing plans or schedules, or both, indicating the following: 1. Extent of fireproofing for each construction and fire-resistance rating. 2. Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3. Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4. Treatment of fireproofing after application. |  |  | Closed | No Exception Taken |  |  |  | Zann Call | Specialty Systems Incorporated | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/24/2019 |  | 01/17/2020 | 12/19/2019 | 12/31/2019 | 01/01/2020 | 03/18/2020 |  | 03/26/2020 | 12/18/2019
4 |  | 0 | 078100 | Low | Samples | Submittal | APPLIED FIREPROOFING | C. Samples: For each exposed product and for each color and texture specified, in manufacturer's standard dimensions in size. |  |  | Assigned to Sub |  | Zann Call | Specialty Systems Incorporated | 12/24/2019 | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 12/24/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 078100 | High |  | Submittal | APPLIED FIREPROOFING - Product Data | Submitting another specified product for approval. The factory for the previously submitted product is shutdown until October. A. Product Data: For each type of product. (may have been submitted previously)A. Qualification Data: For Installer and testing agency. B. Product Certificates: For each type of fireproofing. C. Evaluation Reports: For fireproofing, from ICC-ES. D. Preconstruction Test Reports: For fireproofing. |  |  | Closed | No Exception Taken |  |  |  | Zann Call | Specialty Systems Incorporated | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 08/04/2020 | 07/29/2020 | 08/06/2020 | 07/27/2020 | 07/27/2020 | 07/27/2020 | 07/28/2020 |  | 07/29/2020 | 07/27/2020
1 |  | 0 | 078123 | Low | Mock-up - Mock-ups use this package. | Mock-Up | INTUMESCENT FIREPROOFING | B. Mockups: Build mockups to verify selections made under Sample submittals and to demonstrate aesthetic effects and to set quality standards for materials and execution. 1. Build mockup of each type of fireproofing and different substrate and each required finish as shown on Drawings. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. H. Provide a uniform finish complying with description indicated for each type of fireproofing material and matching finish approved for required mockups. |  |  | Assigned to Sub |  | Zann Call | Specialty Systems Incorporated | 03/03/2020 | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 03/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 078123 | Low |  | Product Data | INTUMESCENT FIREPROOFING | A. Product Data: For each type of product. A. Qualification Data: For Installer and testing agency. B. Product Certificates: For each type of fireproofing. C. Evaluation Reports: For fireproofing, from ICC-ES. |  |  | Closed | No Exception Taken |  |  |  | Zann Call | Specialty Systems Incorporated | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/19/2019 |  | 01/17/2020 | 12/19/2019 | 12/31/2019 | 01/01/2020 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
3 |  | 0 | 078123 | Low |  | Shop Drawing | INTUMESCENT FIREPROOFING | B. Shop Drawings: Framing plans or schedules, or both, indicating the following: 1. Extent of fireproofing for each construction and fire-resistance rating. 2. Applicable fire-resistance design designations of a qualified testing and inspecting agency acceptable to authorities having jurisdiction. 3. Minimum fireproofing thicknesses needed to achieve required fire-resistance rating of each structural component and assembly. 4. Treatment of fireproofing after application. |  |  | Closed |  |  |  |  | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 12/19/2019 |  |  | 12/19/2019 |  |  |  |  | 12/31/2019 | 12/18/2019
4 |  | 0 | 078123 | Low | Samples | Submittal | INTUMESCENT FIREPROOFING | C. Samples: For each exposed product and for each color and texture specified, in manufacturer's standard dimensions in size. |  |  | Closed | See Other |  |  |  | Zann Call | Specialty Systems Incorporated | Westland PE’s | [5 empty] | 12/19/2019 |  |  | 12/19/2019 |  |  |  |  | 07/22/2020 | 12/18/2019
5 |  | 0 | 078123 | High |  | Product Data | INTUMESCENT FIREPROOFING | A. Product Data: For each type of product. A. Qualification Data: For Installer and testing agency. B. Product Certificates: For each type of fireproofing. C. Evaluation Reports: For fireproofing, from ICC-ES. |  |  | Closed | No Exception Taken |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 02/09/2021 | 02/11/2021 | 02/15/2021 | 02/02/2021 | 02/02/2021 | 02/02/2021 | 03/17/2021 |  | 03/23/2021 | 02/02/2021
1 |  | 0 | 078400 | Low |  | Product Data | Firestopping |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers | [5 empty] | 03/09/2020 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 03/14/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 0 | 079213 | Low | Mock-up - Mock-ups use this package. | Mock-Up | Elastomeric Joint Sealants | C. Mockups: 1. Provide mockups including sealant and joint accessories to illustrate installation quality and color if requested by Architect or Project Manager. a. Incorporate accepted mockup as part of Work. C. Samples for Verification: For each kind and color of acoustical joint sealant required, provide Samples with joint sealants in 1/2-inch- (13-mm-) wide joints formed between two 6-inch- (150-mm-) long strips of material matching the appearance of exposed surfaces adjacent to joint sealants. |  |  | Assigned to Sub |  | Miguel Brito | Waterproofing West | 11/02/2020 | Miguel Brito | Waterproofing West | Westland PE’s | [5 empty] | 11/02/2020 |  |  | 10/29/2020 | 10/29/2020 |  |  |  |  | 12/18/2019
2 |  | 0 | 079213 | High |  | Submittal | Elastomeric Joint Sealants | Product Data / Color Samples A. Action Submittals: 1. Product Data: a. Manufacturer's specifications and other data needed to prove compliance with the specified requirements. b. Manufacturer's literature for each Product. c. Schedule showing joints requiring sealants. Show also backing and primer to be used. a. Manufacturer's Certificate: 1) Certify products are suitable for intended use and products meet or exceed specified requirements. 2) Certificate from Manufacturer indicating date of manufacture. 2. Manufacturers’ Instructions: a. Manufacturer's installation recommendations for each Product. b. Manufacturer's installation for completing sealant intersections when different materials are joined. A. Product Data: For each acoustical joint sealant. D. Acoustical-Joint-Sealant Schedule: Include the following information: 1. Joint-sealant application, joint location, and designation. 2. Joint-sealant manufacturer and product name. 3. Joint-sealant formulation. 4. Joint-sealant color. |  |  | Closed | No Exception Taken |  |  |  | Miguel Brito | Waterproofing West | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 11/02/2020 |  | 11/11/2020 | 10/28/2020 | 10/28/2020 | 12/08/2020 | 12/10/2020 |  | 12/11/2020 | 12/18/2019
3 |  | 0 | 079213 | High |  | Submittal | Elastomeric Joint Sealants (Paintable) | Paintable caulk for the precast as requested. |  |  | Closed | No Exception Taken |  |  |  | Miguel Brito | Waterproofing West | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE | [5 empty] | 04/05/2021 | 10/28/2020 | 04/02/2021 | 04/02/2021 | 04/02/2021 |  | 04/02/2021 | 04/02/2021
2 |  | 0 | 079219 | Low | Samples | Submittal | ACOUSTICAL JOINT SEALANTS | B. Samples for Initial Selection: Manufacturer's color charts consisting of strips of cured sealants showing the full range of colors available for each product exposed to view. |  |  | Assigned to Sub |  | Aaron Bowers | Pete King Commercial | 12/04/2020 | Aaron Bowers | Pete King Commercial | Westland PE’s | [5 empty] | 12/04/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
3 |  | 0 | 079219 | Low |  | Product Data | ACOUSTICAL JOINT SEALANTS |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/03/2020 | 02/26/2020 | 03/09/2020 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 03/18/2020 |  | 03/26/2020 | 02/24/2020
1 |  | 0 | 079513 | Low |  | Product Data | EXTERIOR EXPANSION JOINT COVER ASSEMBLIES | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for expansion joint cover assemblies. F. Expansion Joint Cover Assembly Schedule: Prepared by or under the supervision of the supplier. Include the following information in tabular form: 1. Manufacturer and model number for each expansion joint cover assembly. 2. Expansion joint cover assembly location cross-referenced to Drawings. 3. Nominal, minimum, and maximum joint width. 4. Movement direction. 5. Materials, colors, and finishes. 6. Product options. 7. Fire-resistance ratings. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
2 |  | 0 | 079513 | Low |  | Shop Drawing | EXTERIOR EXPANSION JOINT COVER ASSEMBLIES | B. Shop Drawings: For each expansion joint cover assembly. 1. Include plans, elevations, sections, details, splices, block-out requirement, attachments to other work, and line diagrams showing entire route of each expansion joint. 2. Where expansion joint cover assemblies change planes, provide isometric or clearly detailed drawing depicting how components interconnect. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
3 |  | 0 | 079513 | Low | Samples | Submittal | EXTERIOR EXPANSION JOINT COVER ASSEMBLIES | C. Samples: For each exposed expansion joint cover assembly and for each color and texture specified, full width by 6 inches (150 mm) long in size. D. Samples for Initial Selection: For each type of exposed finish. 1. Include manufacturer's color charts showing the full range of colors and finishes available for each exposed metal and elastomeric seal material. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
4 |  | 0 | 079513 | Low | Samples | Submittal | EXTERIOR EXPANSION JOINT COVER ASSEMBLIES | E. Samples for Verification: For each type of expansion joint cover assembly, full width by 6 inches (150 mm) long in size. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
1 |  | 0 | 079513.16 | Low | Mock-up - Mock-ups use this package. | Mock-Up | EXTERIOR EXPANSION JOINT COVER ASSEMBLIES | A. Mockups: Build mockups to demonstrate aesthetic effects and to set quality standards for materials and execution. 1. Build mockup of typical expansion joint cover assembly as shown on Drawings. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
1 |  | 0 | 081113 | High |  | Product Data | HOLLOW METAL DOORS AND FRAMES | A. Product Data: For each type of product. 1. Include construction details, material descriptions, core descriptions, fire-resistance ratings, and finishes. F. Product Schedule: For hollow-metal doors and frames, prepared by or under the supervision of supplier, using same reference numbers for details and openings as those on Drawings. Coordinate with final door hardware schedule. A. Qualification Data: For door inspector. 1. Fire-Rated Door Inspector: Submit documentation of compliance with NFPA 80, Section 5.2.3.1. 2. Egress Door Inspector: Submit documentation of compliance with NFPA 101, Section 7.2.1.15.4. 3. Submit copy of DHI Fire and Egress Door Assembly Inspector (FDAI) certificate. B. Product Test Reports: For each type of fire-rated hollow-metal door and frame assembly] fire-rated borrowed-lite and transom assembly for tests performed by a qualified testing agency indicating compliance with performance requirements. C. Oversize Construction Certification: For assemblies required to be fire-rated and exceeding limitations of labeled assemblies. D. Field quality control reports. C. Shop Drawings: Include the following: 1. Elevations of each door type. 2. Details of doors, including vertical- and horizontal-edge details and metal thicknesses. 3. Frame details for each frame type, including dimensioned profiles and metal thicknesses. 4. Locations of reinforcement and preparations for hardware. 5. Details of each different wall opening condition. 6. Details of electrical raceway and preparation for electrified hardware, access control systems, and security systems. 7. Details of anchorages, joints, field splices, and connections. 8. Details of accessories. 9. Details of moldings, removable stops, and glazing. |  |  | Closed | Approved As Noted |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/24/2020 | 12/19/2019 | 01/09/2020 | 01/09/2020 | 02/12/2020 |  | 02/19/2020 | 12/18/2019
2 |  | 0 | 081113 | Low |  | Shop Drawing | HOLLOW METAL DOORS AND FRAMES | C. Shop Drawings: Include the following: 1. Elevations of each door type. 2. Details of doors, including vertical- and horizontal-edge details and metal thicknesses. 3. Frame details for each frame type, including dimensioned profiles and metal thicknesses. 4. Locations of reinforcement and preparations for hardware. 5. Details of each different wall opening condition. 6. Details of electrical raceway and preparation for electrified hardware, access control systems, and security systems. 7. Details of anchorages, joints, field splices, and connections. 8. Details of accessories. 9. Details of moldings, removable stops, and glazing. |  |  | Closed | See Other |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 01/09/2020 | 12/18/2019
3 |  | 0 | 081113 | Low | Samples | Submittal | HOLLOW METAL DOORS AND FRAMES | D. Samples for Initial Selection: For hollow-metal doors and frames with factory-applied color finishes. |  |  | Closed | See Other |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 11/20/2020 | 12/18/2019
4 |  | 0 | 081113 | Low | Samples | Submittal | HOLLOW METAL DOORS AND FRAMES | E. Samples for Verification: 1. Finishes: For each type of exposed finish required, prepared on Samples of not less than 3 by 5 inches (75 by 127 mm). 2. Fabrication: Prepare Samples approximately [12 by 12 inches (305 by 305 mm)] to demonstrate compliance with requirements for quality of materials and construction: a. Doors: Show vertical-edge, top, and bottom construction; core construction; and hinge and other applied hardware reinforcement. Include separate section showing glazing if applicable. b. Frames: Show profile, corner joint, floor and wall anchors, and silencers. Include separate section showing fixed hollow-metal panels and glazing if applicable. |  |  | Closed | See Other |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 11/20/2020 | 12/18/2019
1 |  | 0 | 083100 | Medium |  | Submittal | CCD_67 Added FSD Access Doors |  |  |  | Design Review |  | CRSA ARCHITECTURE |  | 07/20/2021 | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  |  |  | 07/20/2021 |  | 07/06/2021 | 07/06/2021 |  |  |  | 07/06/2021 |  | Mechanical Engineers
1 |  | 0 | 083483 | Low |  | Product Data | FLOOR DOORS | A. Product Data: For each type of product. 1. Include construction details, fire ratings, materials, individual components and profiles, and finishes. B. Product Schedule: For floor doors. A. Qualification Data: For testing and inspecting agency. 1. Fire-Rated Door Inspector: Submit documentation of compliance with NFPA 80, Section 5.2.3.1. 2. Submit copy of DHI Fire and Egress Door Assembly Inspector (FDAI) certificate. |  |  | Closed | See Other | [5 empty] | Westland PE’s | [13 empty] | 11/30/2020 | 12/18/2019
2 |  | 0 | 083483 | Medium |  | Submittal | FLOOR DOORS - Access Doors and Frames | Section 083113 "Access Doors and Frames" for wall- and ceiling-mounted access doors and frames |  |  | Closed | No Exception Taken |  |  |  | Westland PE’s |  | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 08/12/2020 | 08/14/2020 | 08/22/2020 | 08/12/2020 | 08/12/2020 | 08/12/2020 | 08/24/2020 |  | 08/27/2020 | 08/12/2020
2 |  | 0 | 083613 | Low |  | Shop Drawing | SECTIONAL DOORS | B. Shop Drawings: For each installation and for special components not dimensioned or detailed in manufacturer's product data. 1. Include plans, elevations, sections, and mounting details. 2. Include details of equipment assemblies. Indicate dimensions, required clearances, method of field assembly, components, and location and size of each field connection. 3. Include points of attachment and their corresponding static and dynamic loads imposed on structure. 4. Include diagrams for power, signal, and control wiring. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 01/06/2020 | 12/18/2019
3 |  | 0 | 083613 | Low | Samples | Submittal | SECTIONAL DOORS | C. Samples for Initial Selection: For units with factory-applied finishes. 1. Include Samples of accessories involving color selection. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 01/06/2020 | 12/18/2019
4 |  | 0 | 083613 | Low | Samples | Submittal | SECTIONAL DOORS | D. Samples for Verification: For each type of exposed finish on the following components, in manufacturer's standard sizes: |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 01/06/2020 | 12/18/2019
1 |  | 1 | 083613 | Low |  | Product Data | SECTIONAL DOORS | Resubmittal Note: Looks like the only thing wrong with the REV 0 submittal was the door heights. Please see the attached revised door heights for your review. They submitted a sample as part of REV 0 so please make sure that sample is also reviewed as part of this resubmittal. Let me know if you have any questions (801.875.2600). A. Product Data: For each type and size of sectional door and accessory. 1. Include construction details, material descriptions, dimensions of individual components, profile door sections, and finishes. 2. Include rated capacities, operating characteristics, electrical characteristics, and furnished accessories. A. Qualification Data: For Installer. B. Sample Warranties: For special warranties. B. Shop Drawings: For each installation and for special components not dimensioned or detailed in manufacturer's product data. 1. Include plans, elevations, sections, and mounting details. 2. Include details of equipment assemblies. Indicate dimensions, required clearances, method of field assembly, components, and location and size of each field connection. 3. Include points of attachment and their corresponding static and dynamic loads imposed on structure. 4. Include diagrams for power, signal, and control wiring. C. Samples for Initial Selection: For units with factory-applied finishes. 1. Include Samples of accessories involving color selection. D. Samples for Verification: For each type of exposed finish on the following components, in manufacturer's standard sizes: |  |  | Closed | No Exception Taken |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/10/2020 |  | 08/10/2020 | 01/08/2020 | 05/07/2020 | 07/29/2020 | 08/17/2020 |  | 08/17/2020 | 01/08/2020
1 |  | 0 | 085200 | Low |  | Product Data | WOOD WINDOWS (ALUMINUM CLAD) | A. Product Data: For each type of product. 1. Include construction details, material descriptions, glazing and fabrication methods, dimensions of individual components and profiles, hardware, and finishes for wood windows. E. Product Schedule: For wood windows. Use same designations indicated on Drawings. A. Qualification Data: For Installer. B. Product Test Reports: For each type of wood window, for tests performed by a qualified testing agency. C. Field quality-control reports. D. Sample Warranties: For manufacturer's warranties. |  |  | Closed | See Other |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 04/01/2020 | 12/18/2019
2 |  | 0 | 085200 | Low |  | Shop Drawing | WOOD WINDOWS (ALUMINUM CLAD) | B. Shop Drawings: For wood windows. 1. Include plans, elevations, sections, hardware, accessories, insect screens, operational clearances, and details of installation, including anchor, flashing, and sealant installation. |  |  | Closed | See Other |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 04/01/2020 | 12/18/2019
3 |  | 0 | 085200 | Low | Samples | Submittal | WOOD WINDOWS (ALUMINUM CLAD) | C. Samples: For each exposed product and for each color specified, 2 by 4 inches (50 by 100 mm) in size. D. Samples for Initial Selection: For units with factory-applied finishes. 1. Include Samples of hardware and accessories involving color selection. |  |  | Closed | See Other |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 04/01/2020 | 12/18/2019
4 |  | 0 | 085200 | Low |  | Closeout | WOOD WINDOWS (ALUMINUM CLAD) | 1.7 WARRANTY A. Manufacturer's Warranty: Manufacturer agrees to repair or replace wood windows that fail in materials or workmanship within specified warranty period. 1. Failures include, but are not limited to, the following: a. Failure to meet performance requirements. b. Structural failures including excessive deflection, water leakage, and air infiltration. c. Faulty operation of movable sash and hardware. d. Deterioration of materials and finishes beyond normal weathering. e. Failure of insulating glass. 2. Warranty Period: a. Window: [10] years from date of Substantial Completion. b. Glazing Units: [10] years from date of Substantial Completion. c. Aluminum-Cladding Finish: 30 years from date of Substantial Completion. |  |  | Closed | See Other |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s | [5 empty] | 06/05/2021 |  |  | 12/19/2019 |  |  |  |  | 04/01/2020 | 12/18/2019
1 |  | 0 | 085200.01 | High | Mock-up - Mock-ups use this package. | Mock-Up | WOOD WINDOWS (Historic) | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Build mockup of typical wall area as shown on Drawings. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. E. Samples for Verification: For wood windows and components required, prepared on Samples of size indicated below: 1. Exposed Finishes: 2 by 4 inches (50 by 100 mm). 2. Exposed Hardware: Full-size units. |  |  | Closed | Rejected |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 05/07/2020 | 12/19/2019 | 04/27/2020 | 04/27/2020 |  | 04/29/2020 | 04/30/2020 | 12/18/2019
2 |  | 0 | 085200.01 | Low |  | Product Data | WOOD WINDOWS (Historic) | A. Product Data: For each type of product. 1. Include construction details, material descriptions, glazing and fabrication methods, dimensions of individual components and profiles, hardware, and finishes for wood windows. F. Product Schedule: For wood windows. Use same designations indicated on Drawings. A. Qualification Data: For Installer. B. Product Test Reports: For each type of wood window, for tests performed by a qualified testing agency. C. Field quality-control reports. D. Sample Warranties: For manufacturer's warranties. |  |  | Closed | Make Corrections Noted |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/02/2020 |  | 01/08/2020 | 12/18/2019
3 |  | 0 | 085200.01 | High |  | Shop Drawing | WOOD WINDOWS (Historic) | Annex Shop Drawings B. Shop Drawings: For wood windows. 1. Include plans, elevations, sections, hardware, accessories, insect screens, operational clearances, and details of installation, including anchor, flashing, and sealant installation |  |  | Closed | No Exception Taken |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 04/17/2020 | 12/19/2019 | 04/01/2020 | 04/01/2020 | 04/22/2020 |  | 04/28/2020 | 12/18/2019
4 |  | 0 | 085200.01 | High | Samples | Submittal | WOOD WINDOWS (Historic) | C. Samples: For each exposed product and for each color specified, 2 by 4 inches (50 by 100 mm) in size. D. Samples for Initial Selection: For units with factory-applied finishes. 1. Include Samples of hardware and accessories involving color selection. |  |  | Closed | Approved |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 07/21/2020 | 04/01/2020 | 07/07/2020 | 07/07/2020 | 07/09/2020 |  | 07/09/2020 | 12/18/2019
6 |  | 0 | 085200.01 | Medium |  | Shop Drawing | WOOD WINDOWS (Historic) | Historic Shop Drawings B. Shop Drawings: For wood windows. 1. Include plans, elevations, sections, hardware, accessories, insect screens, operational clearances, and details of installation, including anchor, flashing, and sealant installation |  |  | Closed | Make Corrections Noted |  |  |  | Todd Maxwell | Re-View Windows, Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/23/2020 | 04/17/2020 | 05/27/2020 | 12/19/2019 | 04/15/2020 | 05/11/2020 | 05/11/2020 |  | 05/14/2020 | 04/15/2020
1 |  | 0 | 086300 | Low | Mock-up - Mock-ups use this package. | Submittal | BRIDES ROOM SKYLIGHT MOCKUP |  |  |  | Assigned to Sub |  | Addition Mockups |  | 07/01/2021 | Addition Mockups |  | Westland PE’s | [5 empty] | 07/01/2021 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 086300 | Low |  | Shop Drawing | METAL-FRAMED SKYLIGHTS | B. Shop Drawings: For metal-framed skylights. 1. Include plans, elevations, sections, and attachment details. 2. Indicate structural loadings and reactions to be transmitted to supporting curbs. 3. Include details of provisions for assembly expansion and contraction and for draining moisture within the assembly to the exterior. 4. Include full-size isometric details of each vertical-to-horizontal intersection of assembly, showing the following: a. Joinery including concealed welds. b. Anchorage. c. Expansion provisions. d. Glazing. e. Flashing and drainage. F. Delegated-Design Submittal: For metal-framed skylights indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 | 01/29/2020 |  |  |  | 01/29/2020 | 12/18/2019
6 |  | 0 | 086300 | Low | Samples | Submittal | METAL-FRAMED SKYLIGHTS | E. Fabrication Sample: Of each framing intersection of assemblies, made from 12-inch (305-mm) lengths of full-size components and showing details of the following: 1. Joinery including concealed welds. 2. Anchorage. 3. Expansion provisions. 4. Glazing. 5. Flashing and drainage. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 10/06/2020 | 12/18/2019
2 |  | 1 | 086300 | Medium |  | Product Data | METAL-FRAMED SKYLIGHTS | 1.5.E. Sample Warranties: For special warranties. |  |  | Closed | No Exception Taken |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 04/01/2020 |  | 09/08/2020 | 03/26/2020 | 08/24/2020 | 08/24/2020 | 08/25/2020 |  | 08/25/2020 | 03/26/2020
4 |  | 1 | 086300 | Low | Samples | Submittal | METAL-FRAMED SKYLIGHTS | C. Samples for Initial Selection: For units with factory-applied finishes. D. Samples for Verification: For each type of exposed finish required, in manufacturer's standard sizes. E. Fabrication Sample: Of each framing intersection of assemblies, made from 12-inch (305-mm) lengths of full-size components and showing details of the following: 1. Joinery including concealed welds. 2. Anchorage. 3. Expansion provisions. 4. Glazing. 5. Flashing and drainage. |  |  | Closed | No Exception Taken |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 05/22/2020 |  | 10/20/2020 | 05/14/2020 | 10/06/2020 | 10/06/2020 | 10/26/2020 |  | 10/26/2020 | 05/14/2020 |  | Gloria Kummer
2 |  | 0 | 087100 | Low | Samples | Submittal | DOOR HARDWARE | Wax Molds for Custom Hardware |  |  | Closed | No Exception Taken |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  |  | 12/19/2019 | 10/05/2020 | 10/05/2020 | 10/05/2020 |  | 10/15/2020 | 12/18/2019
3 |  | 0 | 087100 | Low |  | Shop Drawing | DOOR HARDWARE - Custom Hardware | C. Shop Drawings: Details of electrified door hardware, indicating the following: 1. Wiring Diagrams: Power, signal, and control wiring. Include the following: a. System schematic. b. Point-to-point wiring diagram. c. Riser diagram. d. Elevation of each door. 2. Detail interface between electrified door hardware and fire alarm, access control, security, building control system. 3. Operation Narrative: Describe the operation of doors controlled by electrified door hardware. |  |  | Closed | No Exception Taken |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 12/15/2020 | 12/19/2019 | 11/30/2020 | 11/30/2020 | 12/03/2020 |  | 12/03/2020 | 12/18/2019
1 |  | 1 | 087100 | High |  | Product Data | DOOR HARDWARE - CCD 104 | A. Product Data: Include construction and installation details, material descriptions, dimensions of individual components and profiles, and finishes. D. Qualification Data: For Installer H. Door Hardware Sets: Prepared by or under the supervision of Architectural Hardware Consultant, detailing fabrication and assembly of door hardware, as well as procedures and diagrams. Coordinate the final door hardware sets with doors, frames, and related work to ensure proper size, thickness, hand, function, and finish of door hardware. 1. Format: Use same scheduling sequence and format and use same door numbers as in the Contract Documents. 2. Content: Include the following information: a. Identification number, location, hand, fire rating, and material of each door and frame. b. Type, style, function, size, quantity, and finish of each door hardware item. c. Complete designations of every item required for each door or opening including name and manufacturer. d. Fastenings and other pertinent information. e. Location of each door hardware set, cross-referenced to Drawings, both on floor plans and in door and frame schedule. f. Explanation of abbreviations, symbols, and codes contained in schedule. g. Mounting locations for door hardware. h. Door and frame sizes and materials. i. Description of each electrified door hardware function, including location, sequence of operation, and interface with other building control systems. j. Sequence of Operation: Include description of component functions that occur in the following situations: authorized person wants to enter; authorized person k. List of related door devices specified in other Sections for each door and frame. 3. Submittal Sequence: Submit the final door hardware sets at earliest possible date, particularly where approval of the door hardware sets must precede fabrication of other work that is critical in Project construction schedule. Include Product Data, Samples, Shop Drawings of other work affected by door hardware, and other information essential to the coordinated review of the door hardware sets. |  |  | Closed | Make Corrections Noted |  |  |  | Russ Farley | Architectural Building Sup | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 05/01/2020 |  |  | 11/20/2020 | 12/17/2020 |  | 12/22/2020 | 11/20/2020
5 |  | 0 | 087100 | Low | Samples | Submittal | DOOR HARDWARE (Finished HW Sample) |  |  |  | Assigned to Sub |  | Russ Farley | Architectural Building Sup | 03/31/2021 | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 03/31/2021 | 04/02/2021 | 04/12/2021 | 03/23/2021 | 10/05/2020 | 10/05/2020 | 10/05/2020 |  | 10/15/2020 | 03/23/2021
6 |  | 0 | 087100 | Low |  | Submittal | DOOR HARDWARE (Door Keying Schedule) |  |  |  | Closed | No Exception Taken |  |  |  | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 03/31/2021 | 04/21/2021 | 05/02/2021 | 03/23/2021 | 03/23/2021 | 04/22/2021 | 05/28/2021 |  | 06/01/2021 | 03/23/2021
4 |  | 1 | 087100 | Low | Samples | Submittal | DOOR HARDWARE (Color Samples) |  |  |  | Assigned to Sub |  | Russ Farley | Architectural Building Sup | 03/31/2021 | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 03/31/2021 | 04/02/2021 | 04/02/2021 | 04/22/2021 | [5 empty] | 04/22/2021
7 |  | 1 | 087100 | Medium |  | Submittal | DOOR HARDWARE (Door Closure Cover Color) |  |  |  | Assigned to Sub |  | Russ Farley | Architectural Building Sup | 04/08/2021 | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 04/08/2021 | 04/21/2021 | 05/02/2021 | 05/06/2021 | [5 empty] | 05/06/2021
8 |  | 0 | 087100 | High |  | Submittal | Hardware Schedule Rev 2021-06-18 |  |  |  | Design Review |  | CRSA ARCHITECTURE |  | 07/02/2021 | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 06/26/2021 | 06/28/2021 | 07/02/2021 |  | 06/21/2021 | 06/21/2021 |  |  |  | 06/18/2021
9 |  | 0 | 087100 | Medium |  | Submittal | Custom Hardware Update - 2021-07-02 | This is the update for two-tone finish custom hardware that we need to get the new molds into production. We will submit a second set of updated custom hardware showing the rest of the new profile on the rest of the custom hardware. |  |  | Closed | Make Corrections Noted |  |  |  | Russ Farley | Architectural Building Sup | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/10/2021 | 07/12/2021 | 07/09/2021 |  | 07/02/2021 | 07/12/2021 | 07/12/2021 |  | 07/14/2021 | 07/02/2021
1 |  | 0 | 088000 | Low |  | Product Data | GLAZING - Interior Glass (Font Screen) | A. Product Data: For each type of product. D. Glazing Schedule: List glass types and thicknesses for each size opening and location. Use same designations indicated on Drawings. E. Delegated-Design Submittal: For glass indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. A. Qualification Data: For manufacturers of insulating-glass units with sputter-coated, low-E coatings glass testing agency and sealant testing agency.B. Product Certificates: For glass. C. Product Test Reports: For insulating glass and glazing sealants, for tests performed by a qualified testing agency. 1. For glazing sealants, provide test reports based on testing current sealant formulations within previous 36-month period. D. Preconstruction adhesion and compatibility test report. E. Sample Warranties: For special warranties. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/01/2020 |  |  | 02/24/2021 | 02/24/2021 | 02/24/2021 |  | 03/19/2021 | 03/23/2021 | 12/18/2019
2 |  | 0 | 088000 | Low | Samples | Submittal | GLAZING - Interior Glass | B. Glass Samples: For each type of glass product other than clear monolithic vision glass [the following products]; 12 inches (300 mm) square. 1. Laminated glass. 2. Insulating glass. C. Glazing Accessory Samples: For sealants and colored spacers, in 12-inch (300-mm) lengths. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 |  |  |  |  | 11/30/2020 | 12/18/2019
3 |  | 0 | 088000 | Low |  | Product Data | GLAZING - Exterior Windows | A. Product Data: For each type of product. D. Glazing Schedule: List glass types and thicknesses for each size opening and location. Use same designations indicated on Drawings. E. Delegated-Design Submittal: For glass indicated to comply with performance requirements and design criteria, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation. A. Qualification Data: For manufacturers of insulating-glass units with sputter-coated, low-E coatings glass testing agency and sealant testing agency.B. Product Certificates: For glass. C. Product Test Reports: For insulating glass and glazing sealants, for tests performed by a qualified testing agency. 1. For glazing sealants, provide test reports based on testing current sealant formulations within previous 36-month period. D. Preconstruction adhesion and compatibility test report. E. Sample Warranties: For special warranties. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Camron Walker | Westland Construction, Inc. |  |  |  |  | 12/01/2020 | 12/10/2020 | 12/20/2020 | 11/30/2020 |  |  |  |  | 11/30/2020 | 11/30/2020
4 |  | 0 | 088000 | Low | Samples | Submittal | GLAZING - Exterior Windows | B. Glass Samples: For each type of glass product other than clear monolithic vision glass [the following products]; 12 inches (300 mm) square. 1. Laminated glass. 2. Insulating glass. C. Glazing Accessory Samples: For sealants and colored spacers, in 12-inch (300-mm) lengths. |  |  | Closed | See Other |  |  |  | Doug Moore | Jones Paint & Glass - St. George | Camron Walker | Westland Construction, Inc. |  |  |  |  | 12/01/2020 | 12/10/2020 | 12/20/2020 | 11/30/2020 |  |  |  |  | 11/30/2020 | 11/30/2020
1 |  | 0 | 088113 | Medium |  | Submittal | Brides Skylight Decorative Glass - Product Data |  |  |  | Sent to GC |  | Camron Walker | Westland Construction, Inc. | 07/02/2021 | Tim Bothell | Holdman Studios LLC | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/01/2021 | 07/02/2021 | 07/12/2021 | 06/22/2021 | 07/13/2021 |  |  |  |  | 06/22/2021
2 |  | 0 | 088113 | Medium |  | Submittal | Brides Skylight Decorative Glass - Shop Drawings |  |  |  | Assigned to Sub |  | Tim Bothell | Holdman Studios LLC | 07/01/2021 | Tim Bothell | Holdman Studios LLC | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/01/2021 | 07/02/2021 | 07/12/2021 | 06/22/2021 | [5 empty] | 06/22/2021
3 |  | 0 | 088113 | Medium |  | Submittal | Brides Skylight Decorative Glass - Material Samples |  |  |  | Assigned to Sub |  | Tim Bothell | Holdman Studios LLC | 07/01/2021 | Tim Bothell | Holdman Studios LLC | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/01/2021 | 07/02/2021 | 07/12/2021 | 06/22/2021 | [5 empty] | 06/22/2021
4 |  | 0 | 088113 | Medium |  | Submittal | Brides Skylight Decorative Glass - Glass Samples |  |  |  | Assigned to Sub |  | Tim Bothell | Holdman Studios LLC | 07/01/2021 | Tim Bothell | Holdman Studios LLC | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/01/2021 | 07/02/2021 | 07/12/2021 | 06/22/2021 | [5 empty] | 06/22/2021
5 |  | 0 | 088113 | Medium |  | Submittal | Brides Skylight Decorative Glass - Sample Warranty |  |  |  | Sent to GC |  | Camron Walker | Westland Construction, Inc. | 07/02/2021 | Tim Bothell | Holdman Studios LLC | Camron Walker | Westland Construction, Inc. |  |  | 0 |  | 07/01/2021 | 07/02/2021 | 07/12/2021 | 06/22/2021 | 07/13/2021 |  |  |  |  | 06/22/2021
1 |  | 0 | 088300 | Low |  | Product Data | MIRRORS | A. Product Data: For each type of product. 1. Mirrors. Include description of materials and process used to produce each type of silvered flat glass mirror specified that indicates sources of glass, glass coating components, edge sealer, and quality-control provisions. A. Qualification Data: For Installer. B. Product Certificates: For each type of mirror. C. Preconstruction Test Reports: From mirror manufacturer indicating that mirror mastic was tested for compatibility and adhesion with mirror backing and substrates on which mirrors are installed. D. Sample Warranty: For special warranty. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. | 12/01/2020 | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 088300 | Low |  | Shop Drawing | MIRRORS | B. Shop Drawings: Include mirror elevations, edge details, mirror hardware, and attachment details. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. | 12/01/2020 | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
3 |  | 0 | 088300 | Low | Samples | Submittal | MIRRORS | C. Samples: For each type of the following: 1. Mirrors: 12 inches (300 mm) square, including edge treatment on two adjoining edges. 2. Mirror Clips: Full size. 3. Mirror Trim: 12 inches (300 mm) long. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. | 12/01/2020 | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
1 |  | 0 | 088813 | Low |  | Product Data | FIRE-RESISTANT GLAZING | A. Product Data: For each type of product. C. Glazing Schedule: List glass types and thicknesses for each size opening and location. Use same designations indicated on Drawings. A. Qualification Data: For glass testing agency. B. Product Certificates: For each type of glass and glazing product, from manufacturer. C. Sample Warranties: For special warranties. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 088813 | Low | Samples | Submittal | FIRE-RESISTANT GLAZING | B. Glass Samples: For each type of glass product; 12 inches (300 mm) square. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 1 | 090000 | High |  | Submittal | Global Stone & Tile - Testing Data Thassos GHID |  |  |  | Closed | Approved |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 0 |  | 09/09/2020 | 09/11/2020 | 12/04/2020 | 11/23/2020 | 11/24/2020 | 11/24/2020 | 12/09/2020 |  | 12/10/2020 | 11/16/2020 | CRSA ARCHITECTURE
4 |  | 0 | 090000 | Medium |  | Submittal | Font Pit Stone Changes - CCD_105 |  |  |  | Closed | No Exception Taken |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 12/15/2020 | 12/17/2020 | 12/18/2020 | 12/08/2020 | 12/08/2020 | 12/08/2020 | 12/11/2020 |  | 12/14/2020 | 12/08/2020
1 |  | 2 | 090000 | High |  | Submittal | Global Stone & Tile - Shop Drawings Set 1 GHID - CCD_40R2 CCD_40R3 | CCD_40R1 PR_7R1 CCD_54.4R4 included previously |  | 01/04/2021 | Closed | Make Corrections Noted |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 0 | 12/15/2020 | 12/19/2020 | 12/31/2020 | 01/10/2021 | 12/11/2020 | 12/29/2020 | 12/31/2020 | 01/08/2021 |  | 01/08/2021 | 12/11/2020
1 |  | 0 | 090320 | Low | Mock-up - Mock-ups use this package. | Mock-Up | HISTORIC TREATMENT OF PLASTER | D. Mockups: Prepare mockups of historic treatment processes for each type of plaster repair and reconstruction work to demonstrate aesthetic effects and to set quality standards for materials and execution and for fabrication and installation. 1. Locate mockups on existing surfaces where directed by Architect. 2. Number and Size: Two wall surfaces of at least 100 sq. ft. (9.0 sq. m) or approximately 96 inches (2400 mm) in least dimension to represent surfaces and conditions for application of each type of plaster repair and reconstruction under same conditions as the completed Work. Include at least the following: a. Install 6 linear ft. (2 m) of cast-plaster molding, but not less than two cast units. b. Repair at least 6 linear ft. (2 m) of plaster cracks. c. Reattach at least 100-sq. ft. (9-sq. m) area of delaminated plaster that has not fallen. 3. Simulate finished lighting conditions for review of mockups. 4. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 5. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. F. Install finish-coat plaster and repair material demonstrated in mockup to fill crack to original plaster profile. D. Samples for Verification: For the following products: 1. Cast Plaster: Each type and form of cast-plaster fabrication. a. Patterns for Casting: Before manufacturing cast-plaster fabrications, submit the actual patterns from which molds will be made for casting new units. Package and ship to prevent loss or damage or make patterns available for inspection by Architect at fabrication plant. b. Cast-Plaster Fabrications: Provide one unit of each shape and surface design, suitable and ready for installation. Submit unit samples after acceptance of patterns for casting. 2. Linear Moldings: 24-inch- (610-mm-)long section of each configuration wet-applied molding with finished joint. Show complete pattern and applied nonlinear cast-plaster shapes, if any. 3. Nonlinear Shapes: Full-size unit of each configuration. 4. Wood Lath: 18-inch- (450-mm-)long section. 5. Metal Lath: 18 inches (450 mm)square. 6. Accessories: Each type in manufacturer's standard size. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 090320 | Low |  | Product Data | HISTORIC TREATMENT OF PLASTER | A. Product Data: For each type of product. 1. Include recommendations for product application and use. A. Qualification Data: For qualified historic treatment specialist and cast-plaster manufacturer. |  |  | Closed | No Exception Taken |  |  |  | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/03/2020 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/02/2020 |  | 01/08/2020 | 12/18/2019
3 |  | 0 | 090320 | Low |  | Shop Drawing | HISTORIC TREATMENT OF PLASTER | B. Shop Drawings: For each configuration of new or replicated plaster molding and ornament required for the work. 1. Include plans, elevations, and sections that show locations and extent of work. 2. Show full-size details of configurations, joint locations, and attachments to other work. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 090320 | Low | Samples | Submittal | HISTORIC TREATMENT OF PLASTER | C. Samples for Initial Selection: For each exposed product that will be exposed and not be painted or otherwise finished and for each color and texture specified. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 092116 | Low |  | Product Data | GYPSUM BOARD SHAFT WALL ASSEMBLIES | A. Product Data: For each component of gypsum board shaft wall assembly. |  |  | Closed | Approved As Noted |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/07/2020 |  | 01/08/2020 | 12/18/2019
1 |  | 0 | 092217 | Low |  | Product Data | INTERIOR METAL FRAMING | 1. Product Data: a. Clips and fasteners: 1) List each clip that will be used on Project, including manufacturer name, product number, and associated fastener information. b. Studs: 1) Manufacturer name, product numbers, steel grade, and SSMA designations. 2) Documentation of equivalent performance to 30 mil (20 ga) [0.76 mm] studs for studs thinner than 30 mil (20 ga) [0.76 mm]. c. Ceilings: 1) Provide name of gypsum board suspended ceiling framing system manufacturer, product names and numbers with supporting product data. d. Post installed anchors: 1) List manufacturer and anchor names for screw anchors, expansion anchors, and powder-actuated fasteners. 1. Certificates: a. Welding: 1) Welding procedures complying with AWS D1.3 Structural Welding Code. 2) Welding certificates of each welder. 2. Manufacturer Installation Instructions: a. Screw anchors. b. Expansion anchors. c. Powder-actuated fasteners. d. Gypsum board suspended ceiling framing systems. 3. Manufacturer Reports: a. ICC ES Evaluation Reports: 1) Metal studs. 2) Screw anchors. 3) Expansion anchors. 4) Powder actuated fasteners. 5) Vertical deflection clips. 6) Screws used to connect studs to vertical deflection clips. 7) Gypsum board suspended ceiling framing systems. 4. Qualification Statements: a. Provide letter stating that Installer Training has taken place or that it will take place prior to commencement of metal framing. b. Provide additional letter providing names of installers who were trained by manufacturer’s representative. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/02/2020 |  | 01/08/2020 | 12/18/2019
2 |  | 0 | 092217 | Low |  | Shop Drawing | INTERIOR METAL FRAMING | 2. Shop Drawings: a. Metal studs: 1) Plan view of each floor showing SSMA stud designation being used for every wall. 2) Identify walls extending to structure. . b. Ceilings: 1) Provide a reflected ceiling plan of each floor showing which ceiling framing types will be used in each room (gypsum board suspended ceiling framing systems, hung joist ceiling, or wall supported joist system). 2) Identify areas where Contract Drawings provide only general design intent but do not provide specific framing member sizes or fastening requirements. Request specific direction from Architect. Included in this Submittal: 054000 - COLD-FORMED METAL FRAMING B. Shop Drawings: 1. Include layout, spacings, sizes, thicknesses, and types of cold-formed steel framing; fabrication; and fastening and anchorage details, including mechanical fasteners. 2. Indicate reinforcing channels, opening framing, supplemental framing, strapping, bracing, bridging, splices, accessories, connection details, and attachment to adjoining work. C. Delegated-Design Submittal: For cold-formed steel framing. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 03/09/2020 | 12/19/2019 | 02/11/2020 | 02/24/2020 | 03/23/2020 |  | 03/24/2020 | 12/18/2019 |  | Structural Engineers, Matt McBride, Zach Hansen
3 |  | 0 | 092217 | Medium |  | Shop Drawing | INTERIOR METAL FRAMING | Proposed replacement for typical door headers. |  |  | Closed | Approved As Noted |  |  |  | Aaron Bowers | Pete King Commercial | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 04/22/2020 | 04/16/2020 | 05/08/2020 | 12/19/2019 | 04/14/2020 | 04/14/2020 | 05/22/2020 |  | 06/09/2020 | 04/14/2020
4 |  | 0 | 092217 | Medium |  | Submittal | INTERIOR METAL FRAMING - Barrel Ceiling | b. Ceilings: 1) Provide a reflected ceiling plan of each floor showing which ceiling framing types will be used in each room (gypsum board suspended ceiling framing systems, hung joist ceiling, or wall supported joist system). |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bowers | Pete King Commercial | David Adams | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 07/25/2020 | 07/19/2020 | 07/27/2020 | 07/17/2020 | 07/17/2020 | 07/17/2020 | 07/29/2020 |  | 08/03/2020 | 07/17/2020 | CRSA ARCHITECTURE
1 |  | 0 | 092226 | Low |  | Submittal Certificate | METAL SUSPENSION SYSTEM GYPSUM BOARD | A. Informational Submittals: 1. Certificates: a. Manufacturer's certifications that products comply with specified requirements. b. Installer’s certificates of training. 2. Manufacturer’s Instructions: a. Manufacturer’s details and installation instructions for seismic bracing. If requested, provide copy of code requirements applicable to Project. |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 03/09/2020 | 12/19/2019 | 02/11/2020 | 02/24/2020 | 03/18/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 0 | 092300 | Low | Mock-up - Mock-ups use this package. | Mock-Up | GYPSUM PLASTERING | A. Mockups: Build mockups to demonstrate aesthetic effects and to set quality standards for materials and execution. 1. Build mockups for each substrate and finish texture indicated for gypsum plastering, including accessories. a. Size: 100 sq. ft. (9 sq. m) in surface area. 2. Simulate finished lighting conditions for review of mockups. 3. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 4. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 092300 | Low |  | Product Data | GYPSUM PLASTERING | A. Product Data: For each type of product. |  |  | Closed | No Exception Taken |  |  |  | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/03/2020 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/21/2020 |  | 01/23/2020 | 12/18/2019
3 |  | 0 | 092300 | Low |  | Shop Drawing | GYPSUM PLASTERING | B. Shop Drawings: Show locations and installation of control and expansion joints, including plans, elevations, sections, details of components, and attachments to other work. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 092400 | Low | Mock-up - Mock-ups use this package. | Mock-Up | CEMENT PLASTERING (Stucco) | A. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Build mockups for each substrate and finish texture indicated for cement plastering, including accessories. a. Size: 100 sq. ft. (9 sq. m) in surface area. Adjacent to Precast covered panel surface, that has receive a top coat surface. b. 2. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 3. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial CompletionE. Samples for Verification: For each type of factory-prepared finish coat and for each color and texture specified, 12 by 12 inches (305 by 305 mm), and prepared on rigid backing. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 092400 | Low |  | Product Data | CEMENT PLASTERING (Stucco) | A. Product Data: For each type of product. |  |  | Closed | No Exception Taken |  |  |  | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/03/2020 |  | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/19/2019 | 01/21/2020 |  | 01/23/2020 | 12/18/2019
3 |  | 0 | 092400 | Low |  | Shop Drawing | CEMENT PLASTERING (Stucco) | B. Shop Drawings: Show locations and installation of control and expansion joints, including plans, elevations, sections, details of components, and attachments to other work. 1. Shop drawings shall include |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 092400 | Low | Samples | Submittal | CEMENT PLASTERING (Stucco) | C. Samples: For each type of factory-prepared finish coat and for each color and texture specified.D. Samples for Initial Selection: For each type of factory-prepared finish coat and for each color and texture specified. |  |  | Assigned to Sub |  | Clinton Phillips | R. Phillips Plastering LLC | 02/03/2020 | Clinton Phillips | R. Phillips Plastering LLC | Westland PE’s | [5 empty] | 02/03/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 092400 | High |  | Product Data | EIFS | Product Data: For the EIFS that is currently being substituted on the Annex and may be used in other approved applications. |  |  | Closed | No Exception Taken |  |  |  | Clinton Phillips | R. Phillips Plastering LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 11/25/2020 | 11/27/2020 | 11/28/2020 | 11/18/2020 | 11/18/2020 | 11/18/2020 | 12/01/2020 |  | 12/03/2020 | 11/18/2020
1 |  | 0 | 092713 | Low | Mock-up - Mock-ups use this package. | Mock-Up | GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS | A. Mockups: Build mockups to set quality standards for fabrication and installation. 1. Build mockup of each type of glass-fiber-reinforced gypsum fabrication. 2. Paint mockups to match finish indicated and to comply with requirements specified in Section 099123 "Interior Painting." 3. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 4. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Dustin Williams | Unlimited Designs Inc. | 01/04/2021 | Dustin Williams | Unlimited Designs Inc. | Westland PE’s | [5 empty] | 01/04/2021 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 092713 | Low |  | Product Data | GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS | A. Product Data: For each type of product. 1. Include construction details, material descriptions, weights, dimensions of individual components and profiles, and finishes. |  |  | Assigned to Sub |  | Aaron Bowers | Pete King Commercial | 12/16/2019 | Aaron Bowers | Pete King Commercial | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 092713 | Low | Samples | Submittal | GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS | C. Samples: For each exposed product and for each color and texture specified. 1. Linear Moldings: 24-inch- (600-mm-) long section with finished joint. Show complete pattern. |  |  | Assigned to Sub |  | Dustin Williams | Unlimited Designs Inc. | 12/16/2019 | Dustin Williams | Unlimited Designs Inc. | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 092713 | High |  | Shop Drawing | GFRG FABRICATIONS PER CCD_19R5 UPDATES- Shop Drawings | Please resubmit the areas from the review of the previous GFRG submittal requesting updates to be made per CCD updates. B. Shop Drawings: 1. Include plans, elevations, sections, and attachment details. 2. Detail fabrication and assembly of glass-fiber-reinforced gypsum fabrications. 3. Indicate requirements for joint treatment. 4. Indicate location of control joints. A. Coordination Drawings: Reflected ceiling plans, drawn to scale, on which the following items are shown and coordinated with one another, using input from installers of the items involved: 1. Ceiling suspension system members. 2. Structural members to which glass-fiber-reinforced gypsum fabrications will be attached and method of attachment. 3. Items penetrating finished ceiling including the following: a. Lighting fixtures. b. Air outlets and inlets. c. Speakers. d. Sprinklers. e. Access panels. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 11/20/2020 | 11/22/2020 | 04/11/2021 | 11/12/2020 | 04/01/2021 | 04/01/2021 | 04/02/2021 |  | 04/02/2021 | 11/12/2020
3 |  | 1 | 092713 | High |  | Shop Drawing | GLASS-FIBER-REINFORCED GYPSUM FABRICATIONS - Shop Drawings CCD Updates | B. Shop Drawings: 1. Include plans, elevations, sections, and attachment details. 2. Detail fabrication and assembly of glass-fiber-reinforced gypsum fabrications. 3. Indicate requirements for joint treatment. 4. Indicate location of control joints. A. Coordination Drawings: Reflected ceiling plans, drawn to scale, on which the following items are shown and coordinated with one another, using input from installers of the items involved: 1. Ceiling suspension system members. 2. Structural members to which glass-fiber-reinforced gypsum fabrications will be attached and method of attachment. 3. Items penetrating finished ceiling including the following: a. Lighting fixtures. b. Air outlets and inlets. c. Speakers. d. Sprinklers. e. Access panels. |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 12/23/2020 |  | 12/17/2020 | 03/23/2021 | 03/23/2021 |  | 03/29/2021 | 12/17/2020
6 |  | 0 | 092713 | High |  |  | Glass Fiber Reinforced Gypsum - Windows |  |  |  | Closed | Make Corrections Noted |  |  |  | Dustin Williams | Unlimited Designs Inc. | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 | 01/12/2021 | 12/31/2020 | 01/02/2021 | 01/02/2021 | 12/23/2020 |  | 12/23/2020 | 01/04/2021 |  | 01/04/2021 | 12/23/2020
7 |  | 0 | 092713 | High |  | Submittal | Glass-Fiber Reinforcement Gypsum Fiber Reinforcing |  |  |  | Closed | Make Corrections Noted |  |  |  | Aaron Bowers | Pete King Commercial | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 02/11/2021 | 02/13/2021 | 02/14/2021 | 02/03/2021 | 02/03/2021 | 02/04/2021 | 02/10/2021 |  | 02/11/2021 | 02/03/2021
1 |  | 0 | 092900 | Low | Mock-up - Mock-ups use this package. | Mock-Up | GYPSUM BOARD | A. Mockups: Before beginning gypsum board installation, install mockups of at least 100 sq. ft. (9 sq. m) in surface area to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Install mockups for the following: a. Each level of gypsum board finish indicated for use in exposed locations. b. Each texture finish indicated. 2. Apply or install final decoration indicated, including painting and wallcoverings, on exposed surfaces for review of mockups. 3. Simulate finished lighting conditions for review of mockups. 4. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Aaron Bowers | Pete King Commercial | 06/01/2020 | Aaron Bowers | Pete King Commercial | Westland PE’s | [5 empty] | 06/01/2020 |  |  | 04/07/2020 | 04/06/2020 |  |  |  |  | 12/18/2019
2 |  | 0 | 092900 | Low |  | Product Data | GYPSUM BOARD | A. Product Data: For each type of product. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 01/02/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
3 |  | 0 | 092900 | Low | Samples | Submittal | GYPSUM BOARD | B. Samples: For the following products: 1. Trim Accessories: Full-size Sample in 12-inch- (300-mm-) long length for each trim accessory indicated. |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/16/2019 |  | 04/17/2020 | 12/19/2019 | 03/25/2020 | 04/01/2020 | 05/13/2020 |  | 05/14/2020 | 12/18/2019
4 |  | 0 | 092900 | Low |  | Product Data | GYPSUM BOARD | Missing items from original product data submittal: Mass Loaded Vinyl Sound Barriers Sound attenuation blankets Added Firestop |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/17/2020 | 03/28/2020 | 04/11/2020 | 01/09/2020 | 03/26/2020 | 04/01/2020 | 05/26/2020 |  | 06/09/2020 | 01/09/2020
5 |  | 0 | 092900 | Medium |  | Product Data | Gypsum Board Assemblies - Sill Seal |  |  |  | Closed | No Exception Taken |  |  |  | Aaron Bowers | Pete King Commercial | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 | 04/03/2020 | 03/31/2020 | 04/03/2020 | 04/11/2020 | 04/01/2020 | 04/01/2020 | 04/01/2020 | 04/27/2020 |  | 04/28/2020 | 04/01/2020
3 |  | 0 | 093013 | High | Samples | Submittal | CERAMIC TILING GHID | GST - St. George Temple - Submittal 9 - Keystone D335 Almond Samples and... GST - St. George Temple - Submittal 10 - Schluter Transitions GST - St. George Temple - Submittal 11 - Quarry Tile 0Q84 Red Paver and ... GST - St. George Temple - Submittal 12 - Rittenhouse Square Samples and ... |  | 12/28/2020 | Closed | Approved As Noted |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 28 | 11/10/2020 | 11/18/2020 | 11/20/2020 | 11/30/2020 | 09/17/2020 | 09/17/2020 | 09/17/2020 | 10/29/2020 |  | 11/05/2020 | 09/17/2020 | CRSA ARCHITECTURE
2 |  | 2 | 093013 | High | Samples | Submittal | CERAMIC TILING GHID | 1. Certificates: a. Master grade certificate. 1) Conform to ANSI A137.1. 2. Manufacturer’s Instructions: a. Provide instructions for installation of tile-setting materials. 3. Source Quality Control Submittals: a. Provide Manufacturer documentation indicating proposed materials will satisfy requirements for Manufacturer's Warranty. 4. Qualification Statement. See Section 01 4301 for qualifications: a. Installer: 1) Provide Qualification documentation if requested by Architect or Owner. 1. Samples: a. 24 inch square sample on specified tile backer showing all types of tile, grout, and colors specified in this Section. 1/2 of sample board shall show floor tile and 1/2 shall show wall tile. b. 24 inch square sample on specified tile backer showing all types of tile, grout, and colors specified in this Section. 1/2 of sample board shall show floor tile, 1/4 shall show font tile, and 1/4 shall show wall tile. c. One sample of each type of base tile and trim piece to be used on Project. |  | 12/28/2020 | Closed | Make Corrections Noted |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 28 | 11/10/2020 | 12/12/2020 | 12/23/2020 | 01/01/2021 | 12/04/2020 | 12/21/2020 | 12/22/2020 | 01/20/2021 |  | 01/22/2021 | 12/04/2020
4 |  | 0 | 093013 | High |  | Submittal | Ceramic Tiling (TW1, TW2 & TW3) GHID | Photos of tile for review. No physical samples sent per GHID. |  |  | Closed | Approved As Noted |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  |  |  | 02/03/2021 |  | 01/19/2021 | 01/19/2021 | 02/16/2021 |  | 02/23/2021 | 01/19/2021
3 |  | 0 | 093033 | High | Samples | Submittal | STONE TILING GHID | GST - St. George Temple - Submittal 7 - Setting Materials Product Data a... GST - St. George Temple - Submittal 8 - Quartzitic Sandstone Samples and... |  | 01/18/2021 | Closed | No Exception Taken |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 84 | 10/06/2020 | 10/14/2020 | 10/16/2020 | 12/14/2020 | 09/17/2020 | 09/17/2020 | 12/04/2020 | 12/04/2020 |  | 12/08/2020 | 09/17/2020
1 |  | 1 | 093033 | High | Samples | Submittal | STONE TILING GHID | Product Data: 1. Manufacturer's literature for each component of system. 2. Cleaning and maintenance instructions. 3. Color and type selections. 4. For stone varieties proposed for use on Project, include test data indicating compliance with physical properties required by referenced ASTM standards. Quality Assurance / Control: 1. Source Limitations for Stone: Obtain each variety of stone from one quarry with resources to provide materials of consistent quality in appearance and physical properties. 2. Documentation of Fabricator's qualifications. 3. Provide Certification that stone supplied under this section is from the same source and batch of stone provided under other sections for stone. Samples: 1. Provide two boxes (20 tiles), 900 mm x 900 mm of each type of actual stone to be used on project. a. Samples submitted shall show full range extent for color, texture, grain, etc. Samples shall show finishes polished, honed or other as specified in the finish schedule. 2. Samples shall fairly represent stone to be used and be clearly labeled with name group classification, name of building, and name of subcontractor and fabricator. |  | 01/18/2021 | Closed | Make Corrections Noted |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 84 | 10/06/2020 | 10/14/2020 | 12/03/2020 | 12/14/2020 | 09/23/2020 | 12/01/2020 | 12/04/2020 | 12/16/2020 |  | 12/22/2020 | 09/23/2020
2 |  | 2 | 093033 | High | Samples | Submittal | STONE TILING GHID | Product Data: 1. Manufacturer's literature for each component of system. 2. Cleaning and maintenance instructions. 3. Color and type selections. 4. For stone varieties proposed for use on Project, include test data indicating compliance with physical properties required by referenced ASTM standards. Quality Assurance / Control: 1. Source Limitations for Stone: Obtain each variety of stone from one quarry with resources to provide materials of consistent quality in appearance and physical properties. 2. Documentation of Fabricator's qualifications. 3. Provide Certification that stone supplied under this section is from the same source and batch of stone provided under other sections for stone. Samples: 1. Provide two boxes (20 tiles), 900 mm x 900 mm of each type of actual stone to be used on project. a. Samples submitted shall show full range extent for color, texture, grain, etc. Samples shall show finishes polished, honed or other as specified in the finish schedule. 2. Samples shall fairly represent stone to be used and be clearly labeled with name group classification, name of building, and name of subcontractor and fabricator. |  | 02/08/2021 | Closed | No Exception Taken |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 112 | 09/29/2020 | 12/12/2020 | 12/14/2020 | 12/24/2020 | 12/04/2020 |  |  | 12/04/2020 |  | 12/04/2020 | 12/04/2020
4 |  | 0 | 093033 | High |  | Submittal | STONE TILE - ASHLAR PATTERN |  |  |  | Closed | Approved As Noted |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | David Adams | Westland Construction, Inc. | Interior Designer |  | 0 |  | 04/13/2021 | 04/15/2021 | 04/24/2021 | 04/14/2021 | 04/14/2021 | 04/14/2021 | 04/15/2021 |  | 04/22/2021 | 04/14/2021
1 |  | 0 | 095113 | Low | Mock-up - Mock-ups use this package. | Submittal | ACOUSTICAL PANEL CEILINGS | B. Mockups: Build mockups to verify selections made under sample submittals and to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Build mockup of typical ceiling area as shown on Drawings. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Kris Lindquist | Design West Acoustics | 01/04/2021 | Kris Lindquist | Design West Acoustics | Westland PE’s | [5 empty] | 01/04/2021 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 095113 | Low |  | Product Data | ACOUSTICAL PANEL CEILINGS | A. Product Data: For each type of product.B. Qualification Data: For testing agency. C. Product Test Reports: For each acoustical panel ceiling, for tests performed by manufacturer and witnessed by a qualified testing agency. D. Evaluation Reports: For each acoustical panel ceiling suspension system and anchor and fastener type, from ICC-ES. E. Field quality-control reports. |  |  | Closed | No Exception Taken |  |  |  | Kris Lindquist | Design West Acoustics | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 07/13/2020 | 12/19/2019 | 06/16/2020 | 06/29/2020 | 07/15/2020 |  | 07/16/2020 | 12/18/2019
3 |  | 0 | 095113 | Low | Samples | Submittal | ACOUSTICAL PANEL CEILINGS | B. Samples: For each exposed product and for each color and texture specified, 6 inches in size. C. Samples for Verification: For each component indicated and for each exposed finish required, prepared on Samples of size indicated below. 1. Acoustical Panel: Set of 6-inch- square Samples of each type, color, pattern, and texture. 2. Exposed Suspension-System Members, Moldings, and Trim: Set of 6-inch- long Samples of each type, finish, and color. |  |  | Closed | No Exception Taken |  |  |  | Kris Lindquist | Design West Acoustics | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 07/13/2020 | 12/19/2019 | 06/29/2020 | 07/21/2020 | 07/27/2020 |  | 07/29/2020 | 12/18/2019
4 |  | 0 | 095113 | Low |  | Shop Drawing | ACOUSTICAL PANEL CEILINGS | A. Coordination Drawings: Reflected ceiling plans, drawn to scale, on which the following items are shown and coordinated with each other, using input from installers of the items involved: 1. Suspended ceiling components. 2. Structural members to which suspension systems will be attached. 3. Size and location of initial access modules for acoustical panels. 4. Items penetrating finished ceiling including the following: a. Lighting fixtures. b. Air outlets and inlets. c. Speakers. d. Access panels. 5. Perimeter moldings. |  |  | Closed | See Other |  |  |  | Kris Lindquist | Design West Acoustics | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 11/30/2020 | 12/18/2019
1 |  | 0 | 096400 | Medium | Mock-up - Mock-ups use this package. | Mock-Up | WOOD FLOORING | A. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Design Review |  | Interior Designer |  | 03/23/2021 | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | Westland PE’s |  | Interior Designer | [5 empty] | 03/23/2021 | 12/19/2019 | 03/09/2021 | 03/09/2021 |  |  |  | 12/18/2019
2 |  | 0 | 096400 | High | Samples | Submittal | WOOD FLOORING (Selection Samples) GHID | Color samples for initial selection. |  | 12/09/2020 | Closed | Approved As Noted |  |  |  | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  | 11/19/2020 | 11/27/2020 | 11/29/2020 | 12/09/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020 | 12/04/2020 |  | 12/07/2020 | 09/14/2020
3 |  | 0 | 096400 | Low | Samples | Submittal | WOOD FLOORING (Stained Wood Samples) GHID | Color samples for initial selection. |  |  | Assigned to Sub |  | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | 11/24/2020 | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 11/24/2020 | 11/26/2020 | 12/06/2020 | 11/16/2020 | 09/14/2020 | 09/14/2020 |  |  |  | 11/16/2020
1 |  | 0 | 096513 | Low | Mock-up - Mock-ups use this package. | Mock-Up | RESILIENT BASE AND ACCESSORIES | A. Mockups: Build mockups to verify selections made under Sample submittals and to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Coordinate mockups in this Section with mockups specified in other Sections. |  |  | Assigned to Sub |  | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | 01/03/2020 | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | Westland PE’s | [5 empty] | 01/03/2020 |  |  | 07/29/2020 | [5 empty] | 12/18/2019
3 |  | 2 | 096513 | Medium | Samples | Submittal | RESILIENT BASE AND ACCESSORIES | A. Product Data: For each type of product. E. Product Schedule: For resilient base and accessory products. Use same designations indicated on Drawings. C. Samples for Initial Selection: For each type of product indicated. B. Samples: For each exposed product and for each color and texture specified, not less than 12 inches (300 mm) long. D. Samples for Verification: For each type of product indicated and for each color, texture, and pattern required in manufacturer's standard-size Samples, but not less than 12 inches (300 mm) long. |  |  | Assigned to Sub |  | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | 01/03/2020 | Ian Swinton | CP Build Enterprises LLC dba CP Flooring | Westland PE’s |  | Interior Designer |  |  |  | 01/03/2020 |  | 04/23/2021 | 04/22/2021 | [5 empty] | 04/22/2021
1 |  | 0 | 097500 | High |  | Product Data | STONE FACING AND TRIM GHID - THASSOS WHITE | B. Product Data: 1. Manufacturer's literature for each component of system. 2. Cleaning and maintenance instructions. 3. Color and type selections. 4. For stone varieties proposed for use on Project, include test data indicating compliance with physical properties required by referenced ASTM standards.E. Quality Assurance / Control: 1. Documentation of installer's qualifications, including list of comparable jobs successfully completed in last five years. 2. Documentation certifying that stone for Project is from single quarry. 3. Documentation of Fabricator's qualifications. 4. Provide Certification that stone supplied under this section is from the same source and batch of stone provided under other sections for stone. |  | 01/18/2021 | Closed | Approved |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 84 | 10/06/2020 | 10/14/2020 | 12/03/2020 | 12/21/2020 | 06/23/2020 | 12/01/2020 | 12/11/2020 | 12/11/2020 |  | 12/17/2020 | 12/18/2019
3 |  | 0 | 097500 | High | Samples | Submittal | STONE FACING AND TRIM GHID | D. Samples: 1. Provide two boxes (20 tiles) of each type of actual stone (where not providing slabs) to be used on project. a. Samples submitted shall show full range extent for color, texture, grain, etc. Samples shall show finishes polished, honed or other as specified in the finish schedule. 2. Samples shall fairly represent stone to be used and be clearly labeled with name group classification, name of building, and name of subcontractor and fabricator. 3. Stone shall match Architects sample. Contractor can submit alternate options for Architect to select from. If Architect feels the alternate seems to be a possible match, Contractor can then submit required product data to follow with two boxes (20 tiles) (as described above) for final approval. a. Show full range extent for color, texture, grain, etc. Show stone preparation with kerfs, profiles, finish corners, etc. |  |  | Closed | Make Corrections Noted |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  |  | 12/16/2019 | 12/16/2019 |  | 07/10/2020 | 12/19/2019 | 06/23/2020 | 06/23/2020 | 08/10/2020 |  | 08/10/2020 | 12/18/2019
4 |  | 0 | 097500 | High | DWGS - Shop Drawings | Submittal | STONE BASE | Locations of the base should match Fetzers' shop drawings. |  |  | Closed | Make Corrections Noted |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  | 12/16/2019 | 03/23/2021 | 03/15/2021 | 03/19/2021 | 12/19/2019 | 03/15/2021 | 03/15/2021 | 03/16/2021 |  | 03/16/2021 | 03/15/2021
1 |  | 0 | 099113 | Low | Mock-up - Mock-ups use this package. | Mock-Up | EXTERIOR PAINTING | A. Mockups: Apply mockups of each paint system indicated and each color and finish selected to verify preliminary selections made under Sample submittals and to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Architect will select one surface to represent surfaces and conditions for application of each paint system specified in Part 3. a. Vertical and Horizontal Surfaces: Provide samples of at least 100 sq. ft. (9 sq. m). b. Other Items: Architect will designate items or areas required. 2. Final approval of color selections will be based on mockups. a. If preliminary color selections are not approved, apply additional mockups of additional colors selected by Architect at no added cost to Owner. 3. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 4. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | 08/01/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s | [5 empty] | 08/01/2021 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 099113 | Low |  | Product Data | EXTERIOR PAINTING | A. Product Data: For each type of product. Include preparation requirements and application instructions. D. Product List: For each product indicated, include the following: 1. Cross-reference to paint system and locations of application areas. Use same designations indicated on Drawings and in schedules. 2. Printout of current "MPI Approved Products List" for each product category specified, with the proposed product highlighted. 3. VOC content. |  |  | Closed | No Exception Taken |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 03/11/2020 |  | 03/26/2020 | 12/18/2019
3 |  | 0 | 099113 | Low | Samples | Submittal | EXTERIOR & INTERIOR PAINTING | Drawdowns B. Samples for Initial Selection: For each type of topcoat product. C. Samples for Verification: For each type of paint system and each color and gloss of topcoat. 1. Submit Samples on rigid backing, 8 inches (200 mm) square. 2. Step coats on Samples to show each coat required for system. 3. Label each coat of each Sample. 4. Label each Sample for location and application area. |  |  | Closed | Approved |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  | 03/02/2020 | 03/02/2020 |  | 07/13/2020 | 12/19/2019 | 06/29/2020 | 06/29/2020 | 07/09/2020 |  | 07/09/2020 | 12/18/2019
4 |  | 0 | 099113 | High |  | Submittal | EXTERIOR PAINTING - Paint for Fiber Glass on Tower |  |  |  | Closed | No Exception Taken |  |  |  | Dustin Williams | Unlimited Designs Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 10/16/2020 | 10/18/2020 | 11/08/2020 | 10/08/2020 | 10/08/2020 | 10/29/2020 | 11/02/2020 | 10/22/2020 | 11/10/2020 | 10/08/2020
5 |  | 0 | 099113 | High |  | Submittal | Exterior Painting - Fence Paint |  |  |  | Closed | No Exception Taken |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | David Adams | Westland Construction, Inc. | Landscape Architects |  | 0 |  | 10/23/2020 | 10/25/2020 | 11/26/2020 | 10/15/2020 |  | 11/16/2020 | 11/16/2020 | 11/11/2020 | 11/16/2020 | 10/15/2020
6 |  | 0 | 099113 | High |  | Submittal | EXTERIOR PAINTING – Historic Tower Paint |  |  |  | Closed | Make Corrections Noted |  |  |  | Dustin Williams | Unlimited Designs Inc. | David Adams | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 11/04/2020 | 11/06/2020 | 11/06/2020 | 10/27/2020 |  | 10/27/2020 | 11/03/2020 |  | 11/10/2020 | 10/27/2020
7 |  | 0 | 099113 | Low | Samples | Submittal | EXTERIOR & INTERIOR PAINTING More Drawdowns | More Drawdowns B. Samples for Initial Selection: For each type of topcoat product. C. Samples for Verification: For each type of paint system and each color and gloss of topcoat. 1. Submit Samples on rigid backing, 8 inches (200 mm) square. 2. Step coats on Samples to show each coat required for system. 3. Label each coat of each Sample. 4. Label each Sample for location and application area. |  |  | Closed | Make Corrections Noted |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  | 03/02/2020 | 03/31/2021 | 04/02/2021 | 04/02/2021 | 12/19/2019 | 03/23/2021 | 03/23/2021 | 04/21/2021 |  | 04/22/2021 | 03/23/2021
8 |  | 0 | 099113 | Medium |  | Submittal | Exterior Paint Substitution |  |  |  | Design Review |  | CRSA ARCHITECTURE |  | 07/09/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 07/02/2021 | 07/04/2021 | 07/09/2021 |  | 06/24/2021 | 06/24/2021 |  |  |  | 06/24/2021
1 |  | 0 | 099123 | Low | Mock-up - Mock-ups use this package. | Mock-Up | INTERIOR PAINTING | A. Mockups: Apply mockups of each paint system indicated and each color and finish selected to verify preliminary selections made under Sample submittals and to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Architect will select one surface to represent surfaces and conditions for application of each paint system specified in Part 3. a. Vertical and Horizontal Surfaces: Provide samples of at least 100 sq. ft. (9 sq. m). b. Other Items: Architect will designate items or areas required. 2. Final approval of color selections will be based on mockups. a. If preliminary color selections are not approved, apply additional mockups of additional colors selected by Architect at no added cost to Owner. 3. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 4. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Closed |  |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s | [5 empty] | 01/04/2021 |  |  | 12/19/2019 |  |  |  |  | 07/02/2021 | 12/18/2019
3 |  | 1 | 099123 | Low | Samples | Submittal | INTERIOR PAINTING (P4 & P5) | Drawdowns for P4 & P5 B. Samples for Initial Selection: For each type of topcoat product. C. Samples for Verification: For each type of paint system and in each color and gloss of topcoat. 1. Submit Samples on rigid backing, 8 inches (200 mm) square. 2. Step coats on Samples to show each coat required for system. 3. Label each coat of each Sample. 4. Label each Sample for location and application area. |  |  | Assigned to Sub |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | 08/01/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | Interior Designer |  |  | 03/02/2020 | 08/01/2021 |  | 12/06/2020 | 11/16/2020 | [5 empty] | 11/16/2020 | Scott Gilberg, Eric Jamison, Paul Monson
4 |  | 0 | 099123 | Low |  | Product Data | INTERIOR PAINTING Dryfall | A. Product Data: For each type of product. Include preparation requirements and application instructions. D. Product List: For each product indicated, include the following: 1. Cross-reference to paint system and locations of application areas. Use same designations indicated on Drawings and in schedules. 2. Printout of current "MPI Approved Products List" for each product category specified in Part 2, with the proposed product highlighted. 3. VOC content. |  |  | Closed | Make Corrections Noted |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 01/30/2021 | 02/01/2021 | 02/01/2021 | 12/19/2019 | 01/22/2021 | 01/22/2021 | 03/17/2021 |  | 03/23/2021 | 01/22/2021 |  | Interior Designer
2 |  | 1 | 099123 | High |  | Product Data | INTERIOR PAINTING | A. Product Data: For each type of product. Include preparation requirements and application instructions. D. Product List: For each product indicated, include the following: 1. Cross-reference to paint system and locations of application areas. Use same designations indicated on Drawings and in schedules. 2. Printout of current "MPI Approved Products List" for each product category specified in Part 2, with the proposed product highlighted. 3. VOC content. |  |  | Closed | Make Corrections Noted |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 02/09/2021 | 02/09/2021 | 02/24/2021 | 03/17/2021 |  | 03/23/2021 | 02/09/2021
5 |  | 0 | 099123 | High |  | Submittal | Interior Paint Final White Drawdown P1 |  |  |  | Closed | Approved |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 06/18/2021 | 06/20/2021 | 06/30/2021 |  | 06/10/2021 | 06/10/2021 | 06/14/2021 |  | 06/15/2021 | 06/10/2021
6 |  | 0 | 099123 | High |  | Submittal | Replacement Plaster Wall Primer (Plugger 25) |  |  |  | Design Review |  | CRSA ARCHITECTURE |  | 06/25/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 06/25/2021 | 06/27/2021 | 06/25/2021 |  | 06/17/2021 | 06/17/2021 |  |  |  | 06/17/2021
1 |  | 0 | 099300 | Low | Mock-up - Mock-ups use this package. | Mock-Up | STAINING AND TRANSPARENT FINISHING | A. Mockups: Apply mockups of each finish system indicated and each color selected to verify preliminary selections made under sample submittals and to demonstrate aesthetic effects and set quality standards for materials and execution. 1. Architect will select one surface to represent surfaces and conditions for application of each type of finish system and substrate. a. Vertical and Horizontal Surfaces: Provide samples of at least 100 sq. ft. (9 sq. m). b. Other Items: Architect will designate items or areas required. 2. Final approval of stain color selections will be based on mockups. a. If preliminary stain color selections are not approved, apply additional mockups of additional stain colors selected by Architect at no added cost to Owner |  |  | Assigned to Sub |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | 08/01/2021 | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s | [5 empty] | 08/01/2021 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 099300 | Low |  | Product Data | STAINING AND TRANSPARENT FINISHING | A. Product Data: For each type of product indicated. Include preparation requirements and application instructions. D. Product List: For each product indicated, include the following: 1. Cross-reference to finish system and locations of application areas. Use same designations indicated on Drawings and in schedules. 2. Printout of current "MPI Approved Products List" for each product category specified in Part 2, with the product proposed for use highlighted. 3. VOC content. |  |  | Closed | No Exception Taken |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 03/18/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 1 | 099656 | High |  | Product Data | EPOXY COATINGS | Resubmittal is for the substitution to ArmorSeal 8100 A. Product Data: 1. Manufacturer's data sheets including but not limited to: a. Installation procedures. b. Material Safety Data Sheets (MSDS). c. Maintenance procedures and instructions. d. Color samples. |  |  | Closed | Approved As Noted |  |  |  | Matt Fackrell | Accent Painting and Special Coatings, LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 07/31/2020 | 07/20/2020 | 07/21/2020 | 07/21/2020 | 07/29/2020 |  | 08/11/2020 | 07/20/2020
1 |  | 0 | 101419 | Low |  | Product Data | DIMENSIONAL LETTER SIGNAGE - Monument Sign | A. Product Data: For each type of product. E. Product Schedule: For dimensional letter signs. Use same designations indicated on Drawings or specified. A. Qualification Data: For Installer and manufacturer. B. Sample Warranty: For special warranty. |  |  | Assigned to Sub |  | Bob Durrant | IMS Masonry Inc. | 12/01/2020 | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 101419 | High |  | Shop Drawing | DIMENSIONAL LETTER SIGNAGE - Monument Sign | B. Shop Drawings: For signs. 1. Include fabrication and installation details and attachments to other work. 2. Show sign mounting heights, locations of supplementary supports to be provided by other installers, and accessories. 3. Show message list, typestyles, graphic elements, and layout for each sign at least half size. 4. Show locations of electrical service connections. 5. Include diagrams for power, signal, and control wiring. F. Delegated-Design Submittal: For signs indicated in "Performance Requirements" Article. 1. Include structural analysis calculations for signs indicated to comply with design loads; signed and sealed by the qualified professional engineer responsible for their preparation. |  |  | Closed | Make Corrections Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 12/01/2020 |  |  | 02/01/2021 | 02/01/2021 | 02/02/2021 | 04/29/2021 |  | 04/29/2021 | 12/18/2019
3 |  | 0 | 101419 | Low | Samples | Submittal | DIMENSIONAL LETTER SIGNAGE - Monument Sign | C. Samples for Initial Selection: For each type of sign assembly, exposed component, and exposed finish. 1. Include representative Samples of available typestyles and graphic symbols. |  |  | Assigned to Sub |  | Bob Durrant | IMS Masonry Inc. | 12/01/2020 | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
4 |  | 0 | 101419 | Low | Samples | Submittal | DIMENSIONAL LETTER SIGNAGE - Monument Sign | D. Samples for Verification: For each type of sign assembly showing all components and with the required finish(es), in manufacturer's standard size unless otherwise indicated and as follows: 1. Dimensional Characters: Full-size Sample of each type of dimensional character. 2. Exposed Accessories: Full-size Sample of each accessory type. 3. Full-size Samples, if approved, will be returned to Contractor for use in the Project. |  |  | Assigned to Sub |  | Bob Durrant | IMS Masonry Inc. | 12/01/2020 | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
5 |  | 0 | 101419 | Low |  | Product Data | DIMENSIONAL LETTER SIGNAGE - Cast Metal | A. Product Data: For each type of product. E. Product Schedule: For dimensional letter signs. Use same designations indicated on Drawings or specified. A. Qualification Data: For Installer and manufacturer. B. Sample Warranty: For special warranty. |  |  | Assigned to Sub |  | Steve Brown | Historical Arts & Casting Inc. | 12/01/2020 | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. |  |  |  |  | 12/01/2020 | 12/10/2020 | 12/20/2020 | 11/30/2020 | [5 empty] | 11/30/2020
7 |  | 0 | 101419 | High | Samples | Submittal | DIMENSIONAL LETTER SIGNAGE - Cast Metal | C. Samples for Initial Selection: For each type of sign assembly, exposed component, and exposed finish. 1. Include representative Samples of available typestyles and graphic symbols. D. Samples for Verification: For each type of sign assembly showing all components and with the required finish(es), in manufacturer's standard size unless otherwise indicated and as follows: 1. Dimensional Characters: Full-size Sample of each type of dimensional character. 2. Exposed Accessories: Full-size Sample of each accessory type. 3. Full-size Samples, if approved, will be returned to Contractor for use in the Project. |  |  | Closed | No Exception Taken |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 12/01/2020 | 12/10/2020 | 12/27/2020 | 11/30/2020 | 12/17/2020 | 12/17/2020 | 12/17/2020 |  | 12/18/2020 | 11/30/2020
1 |  | 0 | 102117 | Low |  | Product Data | METAL DRESSING COMPARTMENTS | A. Product Data: For each type of product. B. Source quality-control reports. D. Sample warranty. |  |  | Closed | See Other |  |  |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [8 empty] | 12/19/2019 |  |  |  |  | 02/24/2020 | 12/18/2019
3 |  | 0 | 102117 | Low |  | Shop Drawing | METAL DRESSING COMPARTMENTS | B. Shop Drawings: 1. Include plans, elevations, sections, and mounting attachment details. A. Coordination Drawings: plans and elevation, drawn to scale, and coordinated with each other, using input from installers of the items involved. |  |  | Closed | See Other |  |  |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [8 empty] | 12/19/2019 |  |  |  |  | 02/24/2020 | 12/18/2019
4 |  | 0 | 102117 | Low | Samples | Submittal | METAL DRESSING COMPARTMENTS | C. Samples: For each exposed product and for each color and texture specified. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 102120 | Low |  | Shop Drawing | MARBLE TOILET COMPARTMENTS | A. Shop Drawings: Provide shop drawings showing location, layout and connections for marble toilet partitions. |  |  | Closed | See Other |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Westland PE’s |  |  |  |  | 12/16/2019 | 12/16/2019 |  |  | 12/19/2019 |  |  |  |  | 09/22/2020 | 12/18/2019
1 |  | 1 | 102800 | High |  | Product Data | TOILET, BATH, AND LAUNDRY ACCESSORIES GHID | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes. 2. Include anchoring and mounting requirements, including requirements for cutouts in other work and substrate preparation. 3. Include electrical characteristics. B. Product Schedule: Indicating types, quantities, sizes, and installation locations by room of each accessory required. 1. Identify locations using room designations indicated on plans and listed below. A. Sample Warranty: For manufacturer's special warranty. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s |  | Interior Designer |  |  |  | 12/01/2020 |  | 03/23/2021 | 02/24/2021 | 03/09/2021 | 06/02/2021 | 06/04/2021 |  | 06/18/2021 | 02/24/2021
2 |  | 0 | 102800 | Medium |  | Submittal | TOILET, BATH, AND LAUNDRY ACCESSORIES (Hair Dryers & Mop Holders) | Hair Dryers & Mop Holders A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes. 2. Include anchoring and mounting requirements, including requirements for cutouts in other work and substrate preparation. 3. Include electrical characteristics. B. Product Schedule: Indicating types, quantities, sizes, and installation locations by room of each accessory required. 1. Identify locations using room designations indicated on plans and listed below. A. Sample Warranty: For manufacturer's special warranty. |  |  | Closed | Make Corrections Noted |  |  |  | Westland PE’s |  | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE | [5 empty] | 04/06/2021 | 03/23/2021 | 03/23/2021 | 03/23/2021 | 04/16/2021 |  | 04/22/2021 | 03/23/2021
1 |  | 0 | 104413 | Low |  | Product Data | FIRE PROTECTION CABINETS | A. Product Data: For each type of product. 1. Show door hardware, cabinet type, trim style, and panel style. Include roughing-in dimensions and details showing recessed-, semirecessed-, or surface-mounting method and relationships of box and trim to surrounding construction. 2. Show location of knockouts for hose valves. F. Product Schedule: For fire-protection cabinets. Indicate whether recessed, semirecessed, or surface mounted. Coordinate final fire-protection cabinet schedule with fire-extinguisher schedule to ensure proper fit and function. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 104413 | Low |  | Shop Drawing | FIRE PROTECTION CABINETS | B. Shop Drawings: For fire-protection cabinets. 1. Include plans, elevations, sections, details, and attachments to other work. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
3 |  | 0 | 104413 | Low | Samples | Submittal | FIRE PROTECTION CABINETS | C. Samples: For each type of exposed finish required. D. Samples for Initial Selection: For each type of exposed finish required. E. Samples for Verification: For each type of exposed finish required, prepared on samples 6 by 6 inches (150 by 150 mm) square. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
1 |  | 0 | 104416 | Low |  | Product Data | FIRE EXTINGUISHERS | A. Product Data: For each type of product. Include rating and classification, material descriptions, dimensions of individual components and profiles, and finishes for fire extinguisher[ B. Product Schedule: For fire extinguishers. Coordinate final fire-extinguisher schedule with fire-protection cabinet schedule to ensure proper fit and function. A. Warranty: Sample of special warranty. |  |  | Assigned to Sub |  | Doug Moore | Jones Paint & Glass - St. George | 12/01/2020 | Doug Moore | Jones Paint & Glass - St. George | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 105113 | Low |  | Shop Drawing | METAL LOCKERS | B. Shop Drawings: For metal lockers: 1. Dimensioned drawings including plans, elevations, and sections to show locker locations and interfaces with adjacent substrates.Details of assembly, erection, anchorage and clearance requirements 2. Show locker trim and accessories. 3. Include locker identification system and numbering sequence. |  |  | Closed | See Other |  |  |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 02/24/2020 | 12/18/2019
3 |  | 0 | 105113 | Low | Samples | Submittal | METAL LOCKERS | C. Samples: For each finish product specified, two complete sets of color chips representing manufacturer's available colors and finishes for this product.. D. Samples for Initial Selection: Manufacturer's color charts showing the full range of colors available. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. | 12/20/2019 | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 105113 | Low | Samples | Submittal | METAL LOCKERS | E. Samples for Verification: For the following products, in manufacturer's standard size: 1. Lockers and equipment. |  |  | Assigned to Sub |  | Brett Wardrop | Rex W. Williams & Sons Inc. | 12/20/2019 | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 1 | 105113 | High |  | Product Data | METAL LOCKERS & DRESSING COMPARTMENTS | 105113 - METAL LOCKERS A. Product Data: For each type of product. B. Source quality-control reports. D. Sample warranty. B. Shop Drawings: 1. Include plans, elevations, sections, and mounting attachment details. A. Coordination Drawings: plans and elevation, drawn to scale, and coordinated with each other, using input from installers of the items involved. ﻿ 102117 - METAL DRESSING COMPARTMENTS A. Product Data: For each type of metal locker. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for each type of metal locker and bench. 2. Manufacturer's data sheets on each product to be used, including: a. Preparation instructions and recommendations. b. Storage and handling requirements and recommendations. c. Installation methods. F. Product Schedule: For lockers. Use same designations indicated on Drawings. A. Qualification Data: For Installer. B. Sample Warranty: For special warranty. B. Shop Drawings: For metal lockers: 1. Dimensioned drawings including plans, elevations, and sections to show locker locations and interfaces with adjacent substrates.Details of assembly, erection, anchorage and clearance requirements 2. Show locker trim and accessories. 3. Include locker identification system and numbering sequence. |  |  | Closed | Make Corrections Noted |  |  |  | Brett Wardrop | Rex W. Williams & Sons Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 05/14/2021 |  | 06/30/2021 | 05/10/2021 | 06/18/2021 | 07/09/2021 | 07/09/2021 |  | 07/14/2021 | 05/10/2021
2 |  | 0 | 107516 | Low |  | Shop Drawing | GROUND-SET FLAGPOLES | B. Shop Drawings: For flagpoles. 1. Include plans, elevations, and attachment details. Show general arrangement, jointing, fittings, accessories, grounding, anchoring, and support. 2. Include section, and details of foundation system. D. Delegated-Design Submittal: For flagpoles. |  |  | Closed | Not Submitted |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s | [5 empty] | 01/02/2020 |  |  | 12/19/2019 | 01/07/2020 |  |  |  | 01/08/2020 | 12/18/2019
3 |  | 0 | 107516 | High | Samples | Submittal | GROUND-SET FLAGPOLES | C. Samples for Verification: For each type of exposed finish, in manufacturer's standard sizes. "PROVIDE COLOR SAMPLE OF BOTH POLE AND BALL TOP FOR REVIEW." -Per Submittal 1 Review |  |  | Closed | Final |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 01/02/2020 |  | 04/17/2020 | 12/19/2019 | 03/05/2020 | 04/01/2020 |  | 04/09/2020 | 04/30/2020 | 12/18/2019
1 |  | 1 | 107516 | Low |  | Product Data | GROUND-SET FLAGPOLES | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, operating characteristics, fittings, accessories, and finishes for flagpoles. B. Shop Drawings: For flagpoles. 1. Include plans, elevations, and attachment details. Show general arrangement, jointing, fittings, accessories, grounding, anchoring, and support. 2. Include section, and details of foundation system. D. Delegated-Design Submittal: For flagpoles. |  |  | Closed | No Exception Taken |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/18/2020 |  | 04/17/2020 | 01/08/2020 | 03/24/2020 | 04/01/2020 | 05/27/2020 |  | 06/09/2020 | 01/08/2020 |  | Landscape Architects, Kelly Gillman, Melissa Fryer
1 |  | 0 | 111313 | Low |  | Product Data | LOADING DOCK BUMPERS | A. Product Data: For each type of loading dock bumper. |  |  | Assigned to Sub |  | Denis Devey | Hoj Engineering | 12/01/2020 | Denis Devey | Hoj Engineering | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 111313 | Low |  | Shop Drawing | LOADING DOCK BUMPERS | B. Shop Drawings: For dock bumpers. Include plans, elevations, sections, and attachment details. |  |  | Assigned to Sub |  | Denis Devey | Hoj Engineering | 12/01/2020 | Denis Devey | Hoj Engineering | Westland PE’s | [5 empty] | 12/01/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
2 |  | 0 | 111319 | Low |  | Shop Drawing | STATIONARY LOADING DOCK EQUIPMENT | B. Shop Drawings: For stationary loading dock equipment. 1. Include plans, elevations, sections, and attachment details. 2. Include details of equipment assemblies. Indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of anchors and each field connection. 3. Include diagrams for power, signal, and control wiring. |  |  | Closed | See Other |  |  |  | Denis Devey | Hoj Engineering | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 12/19/2019 | 02/04/2020 |  |  |  | 02/24/2020 | 12/18/2019
1 |  | 2 | 111319 | High |  | Product Data | STATIONARY LOADING DOCK EQUIPMENT | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for stationary loading dock equipment. 2. Include rated capacities, operating characteristics, electrical characteristics, and furnished specialties and accessories. A. Qualification Data: For Installer. B. Welding certificates. D. Sample Warranty: For manufacturer's special warranty. |  |  | Closed | No Exception Taken |  |  |  | Denis Devey | Hoj Engineering | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/29/2021 |  | 02/05/2021 | 01/22/2021 | 01/22/2021 | 01/22/2021 | 03/17/2021 |  | 03/22/2021 | 01/22/2021
2 |  | 0 | 112300 | Low |  | Shop Drawing | COMMERCIAL LAUNDRY & DRY CLEANING EQUIPMENT | C. Shop Drawings: 1. Include plans, elevations, sections, and mounting attachment details. 2. Include details of equipment assemblies. Indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection. 3. Include diagrams for power, signal, and control wiring. |  |  | Closed | See Other |  |  |  | Bob Nosack | Alliance Laundry Equipment | Westland PE’s | [5 empty] | 12/16/2019 |  |  | 04/01/2020 | 04/01/2020 |  |  |  | 05/07/2020 | 12/18/2019
1 |  | 1 | 112300 | Medium |  | Product Data | COMMERCIAL LAUNDRY & DRY CLEANING EQUIPMENT | A. Product Data: For each type of product. B. Catalog sheets before ordering equipment |  |  | Closed | No Exception Taken |  |  |  | Bob Nosack | Alliance Laundry Equipment | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 07/17/2020 |  | 12/11/2020 | 07/09/2020 | 11/21/2020 | 12/07/2020 | 12/15/2020 |  | 12/17/2020 | 07/09/2020 |  | Brian Chandler
1 |  | 0 | 113013 | Low |  | Product Data | POWER MODULE PANEL | A. Product Data: For each type of product. 1. Include installation details, material descriptions, dimensions of individual components, and finishes for each appliance. 2. Include rated capacities, operating characteristics, electrical characteristics, and furnished accessories. B. Product Schedule: For appliances. A. Qualification Data: For manufacturer. B. Product Certificates: For each type of appliance. D. Sample Warranties: For manufacturers' special warranties. |  |  | Closed | See Other | [5 empty] | Westland PE’s | [13 empty] | 11/30/2020 | 12/18/2019
1 |  | 0 | 114000 | Low | Mock-up - Mock-ups use this package. | Mock-Up | FOODSERVICE EQUIPMENT | C. FULL SCALE MOCK UP – Upon Foodservice Consultant’s approval of custom counter shop drawings and prior to fabrication, Contractor shall create a full scale mockup of a typical counter, complete with applicable drop-in unit, food guard post and shield and base. Contractor shall ship mock up to job site for Owner, Foodservice Consultant and Architect review and approval. Review and approval required prior to fabrication of units as specified in Part IV. |  |  | Closed | Not Applicable |  |  |  | David McCoy | Standard Restaurant Equipment Co. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 | 01/20/2020 |  |  |  | 07/29/2020 | 12/18/2019
2 |  | 0 | 114000 | Low |  | Shop Drawing | FOODSERVICE EQUIPMENT | A. Upon award of Contract, furnish the Architect with one electronic copy (PDF) of the following drawings in accordance with the approved project schedule. Reproduced copies of bid documents will not be accepted for this purpose in any fashion. 1. Equipment specified for fabrication shall be detailed and fully dimensioned to a minimum scale of 3/4" = 1'-0" (1:20) for plan and elevation views and 1-1/2" = 1'-0" (1:10) for sections. Show all materials, gauges, and methods of construction. 2. Prepare separate electrical and mechanical dimensioned rough-in drawings at 1/4" = 1'-0" (1:50) showing exact point of penetration of floors, walls and ceilings for all services required to operate the equipment that the Contractor shall furnish, including the requirements for Contractor supplied and installed refrigerant and beverage piping line runs. These drawings shall also show exact locations of final connections to equipment including Owner or Vendor provided as identified in the consultants floor plan and Utility Load Schedule. Indicate floor drains, floor sinks, receptacles, lights and other special conditions related to the equipment known to the Contractor but provided under other Sections. 3. Dimensioned drawings shall be submitted showing the location and size of all bases, depressions, grease interceptors, special height walls, openings in walls for equipment or operations, and critical dimensions, etc. Drawings shall be drawn to a scale of not less than 1/4" = 1'-0" (1:50). |  |  | Closed | Make Corrections Noted |  |  |  | David McCoy | Standard Restaurant Equipment Co. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 01/28/2020 | 12/19/2019 | 01/10/2020 | 01/13/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
3 |  | 0 | 114000 | Low |  | Product Data | FOODSERVICE EQUIPMENT | B. MANUFACTURERS’ LITERATURE - Upon award of contract, submit four bound sets of manufacturers’ specifications and data sheets or one electronic copy (PDF) describing articles and equipment, as specified, for approval. Cut sheets shall be printed originals. 1. Each submittal must contain a page for every item indicating units to be furnished, manufacturer’s number and list optional finish and accessories to be supplied. In addition, show electrical characteristics and BTU rating and indicate if electrical cord and plug will be furnished. 2. Submittals shall be complete, accounting for each specified “buy out” (standard equipment) item. Loose sheets or “piecemeal” submittals shall not be acceptable. If a manufacturer’s catalog sheet is not obtainable, for a specific item, inset a typewritten sheet describing the item giving all of the required information. |  |  | Closed | Make Corrections Noted |  |  |  | David McCoy | Standard Restaurant Equipment Co. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 01/24/2020 | 12/19/2019 | 01/03/2020 | 01/09/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
5 |  | 0 | 114000 | Low |  | Shop Drawing | FOODSERVICE EQUIPMENT | Food Service Rough-In Drawings & Sneeze Guard Drawings A. Upon award of Contract, furnish the Architect with one electronic copy (PDF) of the following drawings in accordance with the approved project schedule. Reproduced copies of bid documents will not be accepted for this purpose in any fashion. 1. Equipment specified for fabrication shall be detailed and fully dimensioned to a minimum scale of 3/4" = 1'-0" (1:20) for plan and elevation views and 1-1/2" = 1'-0" (1:10) for sections. Show all materials, gauges, and methods of construction. 2. Prepare separate electrical and mechanical dimensioned rough-in drawings at 1/4" = 1'-0" (1:50) showing exact point of penetration of floors, walls and ceilings for all services required to operate the equipment that the Contractor shall furnish, including the requirements for Contractor supplied and installed refrigerant and beverage piping line runs. These drawings shall also show exact locations of final connections to equipment including Owner or Vendor provided as identified in the consultants floor plan and Utility Load Schedule. Indicate floor drains, floor sinks, receptacles, lights and other special conditions related to the equipment known to the Contractor but provided under other Sections. 3. Dimensioned drawings shall be submitted showing the location and size of all bases, depressions, grease interceptors, special height walls, openings in walls for equipment or operations, and critical dimensions, etc. Drawings shall be drawn to a scale of not less than 1/4" = 1'-0" (1:50). |  |  | Closed | Revise and Resubmit |  |  |  | David McCoy | Standard Restaurant Equipment Co. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 02/06/2020 | 01/31/2020 | 02/14/2020 | 01/29/2020 | 01/29/2020 | 01/29/2020 | 02/04/2020 |  | 02/05/2020 | 01/29/2020
6 |  | 0 | 114000 | Low |  | Shop Drawing | FOODSERVICE EQUIPMENT | Food Service Rough-In Drawings Resubmittal A. Upon award of Contract, furnish the Architect with one electronic copy (PDF) of the following drawings in accordance with the approved project schedule. Reproduced copies of bid documents will not be accepted for this purpose in any fashion. 1. Equipment specified for fabrication shall be detailed and fully dimensioned to a minimum scale of 3/4" = 1'-0" (1:20) for plan and elevation views and 1-1/2" = 1'-0" (1:10) for sections. Show all materials, gauges, and methods of construction. 2. Prepare separate electrical and mechanical dimensioned rough-in drawings at 1/4" = 1'-0" (1:50) showing exact point of penetration of floors, walls and ceilings for all services required to operate the equipment that the Contractor shall furnish, including the requirements for Contractor supplied and installed refrigerant and beverage piping line runs. These drawings shall also show exact locations of final connections to equipment including Owner or Vendor provided as identified in the consultants floor plan and Utility Load Schedule. Indicate floor drains, floor sinks, receptacles, lights and other special conditions related to the equipment known to the Contractor but provided under other Sections. 3. Dimensioned drawings shall be submitted showing the location and size of all bases, depressions, grease interceptors, special height walls, openings in walls for equipment or operations, and critical dimensions, etc. Drawings shall be drawn to a scale of not less than 1/4" = 1'-0" (1:50). |  |  | Closed | Make Corrections Noted |  |  |  | David McCoy | Standard Restaurant Equipment Co. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/13/2020 | 02/27/2020 | 03/12/2020 | 02/05/2020 | 02/25/2020 | 03/02/2020 | 03/18/2020 |  | 03/26/2020 | 02/05/2020
7 |  | 0 | 114000 | High |  | Product Data | Contractor Office Foodservice Equipment | Submittal RE: RFI 192 |  |  | Closed | Approved As Noted |  |  |  | Camron Walker | Westland Construction, Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  |  |  | 02/19/2020 | 02/12/2020 | 02/12/2020 | 02/12/2020 | 02/13/2020 |  | 03/02/2020 | 02/12/2020
1 |  | 0 | 115214 | Low |  | Product Data | MONITOR LIFT | A. Product Data: For each type of product. B. Sample warranty. A. Installer Qualifications: An authorized representative who is trained and approved by manufacturer. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
2 |  | 0 | 115214 | Low |  | Shop Drawing | MONITOR LIFT | B. Shop Drawings: 1. Include plans, elevations, sections, and mounting details. 2. Include details of equipment assemblies. Indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection. 3. Detail fabrication and assembly of lift mechanism. 4. Include diagrams for power, signal, and control wiring. A. Coordination Drawings: Show unit , drawn to scale, and coordinated with each other, using input from installers of the items involved. |  |  | Draft | [6 empty] | Westland PE’s | [14 empty] | 12/18/2019
1 |  | 0 | 119513 | Low |  | Shop Drawing | CHANDELIER HOIST SYSTEM | A. Shop Drawings: Shop drawings and calculations for hoist system and connection of the hoist system to the building structure shall be prepared and stamped by certified structural engineer. |  |  | Assigned to Sub |  | Dan Lopez | Drive Motorlifts, L.L.C. | 12/20/2019 | Dan Lopez | Drive Motorlifts, L.L.C. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
1 |  | 0 | 121215 | Low | Mock-up - Mock-ups use this package. | Mock-Up | DECORATIVE PAINTING | B. Mockups: Provide mockups for each type of stenciled decoration and substrate, decorative paint and each metallic leaf required to demonstrate aesthetic effects and set quality standards for materials and execution. Duplicate appearance of approved Sample submittals. 1. Installer to submit one sample of each type, style or design in project. Mock up size shall be 8 by 24 inches. Mockup shall show where two corners come together. 2. Approval of mockups does not constitute approval of deviations from the Contract Drawings contained in mockups unless Architect specifically approves such deviations in writing. |  |  | Assigned to Sub |  | Dale Gierisch | Finessed Finishes INC. | 03/02/2020 | Dale Gierisch | Finessed Finishes INC. | Westland PE’s | [5 empty] | 03/02/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 121215 | Low |  | Product Data | DECORATIVE PAINTING | 1. Product Data: For each type of product installed. Include recommendations for application and use. 1. Qualification Data: For qualified stenciled decoration specialist. Installer shall have minimum 5 years of experience.. |  |  | Assigned to Sub |  | Dale Gierisch | Finessed Finishes INC. | 03/02/2020 | Dale Gierisch | Finessed Finishes INC. | Westland PE’s |  |  |  |  | 01/20/2020 | 03/02/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 121215 | Low | Samples | Submittal | DECORATIVE PAINTING | 2. Samples: For each type of stenciled decoration as indicated in Construction Drawings. a. Include stepped Samples showing sizing, decorative paint and metallic leaf. Resubmit until each required sheen, color and texture is achieved. b. Label each Sample for location and application. c. Sample Size: Full width of stenciled decoration and minimum of 18 inches or pattern repeat 1-1/2 times. |  |  | Assigned to Sub |  | Dale Gierisch | Finessed Finishes INC. | 03/02/2020 | Dale Gierisch | Finessed Finishes INC. | Westland PE’s |  |  |  |  | 01/20/2020 | 03/02/2020 |  |  | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 122200 | Low | Mock-up - Mock-ups use this package. | Mock-Up | CURTAINS AND DRAPES GHID | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for fabrication and installation. 1. Build mockup at location and in size shown on Drawings. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  | 02/15/2021 | Assigned to Sub |  | Mark Lawrence | House of Drapery Inc. | 02/03/2021 | Mark Lawrence | House of Drapery Inc. | Westland PE’s |  |  |  | 28 | 01/26/2021 | 02/03/2021 | 02/05/2021 | 02/15/2021 | 12/19/2019 | [5 empty] | 12/18/2019
3 |  | 0 | 122200 | Low |  | Shop Drawing | CURTAINS AND DRAPES | B. Shop Drawings: 1. Drapery Tracks: Show installation and anchorage details and locations of controls. a. Motorized Tracks: Indicate dimensions, weights, and required clearances for track and motor and differentiate between manufacturer-installed and field-installed wiring. 2. Drapes: Show sizes, locations, and details of installation. A. Coordination Drawings: For drapery track installation; reflected ceiling plans drawn to scale and coordinating track installation with openings and ceiling-mounted items, on which the following items are shown: 1. Suspended ceiling components. 2. Structural members to which motors are attached. 3. Size and location of motor access panel. |  |  | Closed | See Other |  |  |  | Mark Lawrence | House of Drapery Inc. | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 | 01/29/2020 |  |  |  | 01/29/2020 | 12/18/2019
4 |  | 0 | 122200 | Low | Samples | Submittal | CURTAINS AND DRAPES GHID | C. Samples: As follows: 1. Drapery Tracks: 18 inches (450 mm) long, with carriers, controls, and accessories. 2. Drapery Fabrics: For each color and pattern indicated, full width by 36 inches (1000 mm) long, from dye lot to be used for the Work and with specified textile treatments applied. Show complete pattern repeat if any. Mark top and face of fabric. 3. Textile Trims: For each color and pattern indicated, 18 inches (450 mm) long. 4. Drape Fabrication: For each heading, fabric, color, and pattern indicated, a complete full-size panel to verify details of fabrication and thread colors. E. Samples for Verification: As follows: 1. Drapery Tracks: 18 inches (450 mm) long, with carriers, controls, and accessories. 2. Drapery Fabrics: For each color and pattern indicated, full width by 36 inches (1000 mm) long, from dye lot to be used for the Work and with specified textile treatments applied. Show complete pattern repeat if any. Mark top and face of fabric. 3. Textile Trims: For each color and pattern indicated, 18 inches (450 mm) long. 4. Drape Fabrication: For each heading, fabric, color, and pattern indicated, a complete full-size panel to verify details of fabrication and thread colors. D. Samples for Initial Selection: For each type of product indicated. |  | 02/15/2021 | Assigned to Sub |  | Interior Designer |  | 02/03/2021 | Interior Designer |  | Westland PE’s |  |  |  | 28 | 01/26/2021 | 02/03/2021 | 02/05/2021 | 02/15/2021 | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 1 | 122200 | Medium |  | Submittal | CURTAINS AND DRAPES GHID | This submittal also includes the Roller Shades. A. Product Data: For the following: 1. Drapery Tracks: Include maximum weights of drapes that can be supported. a. Motorized Tracks: Indicate motor weights, motor-mounting requirements, and electrical requirements. 2. Fabrics. 3. Textile treatments. F. Product Schedule: For drapes and drapery tracks. Use same designations indicated on Drawings. B. Product Certificates: For each drapery fabric treated with flame retardant, signed by fabric supplier and indicating treatment durability and cleaning procedures required to maintain treatment effectiveness. B. Shop Drawings: 1. Drapery Tracks: Show installation and anchorage details and locations of controls. a. Motorized Tracks: Indicate dimensions, weights, and required clearances for track and motor and differentiate between manufacturer-installed and field-installed wiring. 2. Drapes: Show sizes, locations, and details of installation. A. Coordination Drawings: For drapery track installation; reflected ceiling plans drawn to scale and coordinating track installation with openings and ceiling-mounted items, on which the following items are shown: 1. Suspended ceiling components. 2. Structural members to which motors are attached. 3. Size and location of motor access panel. |  | 01/04/2021 | Assigned to Sub |  | Mark Lawrence | House of Drapery Inc. | 12/23/2020 | Mark Lawrence | House of Drapery Inc. | Westland PE’s |  | Interior Designer |  |  | 12/15/2020 | 03/10/2021 | 03/12/2021 | 03/22/2021 | 03/02/2021 | [5 empty] | 03/02/2021
1 |  | 0 | 122413 | Low |  | Product Data | ROLLER WINDOW SHADES | A. Product Data: For each type of product. 1. Include styles, material descriptions, construction details, dimensions of individual components and profiles, features, finishes, and operating instructions for roller shades. A. Qualification Data: For InstallerB. Product Certificates: For each type of shadeband material, signed by product manufacturer. C. Product Test Reports: For each type of shadeband material, for tests performed by manufacturer and witnessed by a qualified testing agency. A. Installer Qualifications: Fabricator of products. |  |  | Closed | See Other |  |  |  | Mark Lawrence | House of Drapery Inc. | Westland PE’s | [5 empty] | 04/13/2020 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
2 |  | 0 | 122413 | Low |  | Shop Drawing | ROLLER WINDOW SHADES | B. Shop Drawings: Show fabrication and installation details for roller shades, including shadeband materials, their orientation to rollers, and their seam and batten locations. 1. Motor-Operated Shades: Include details of installation and diagrams for power, signal, and control wiring. |  |  | Closed | See Other |  |  |  | Mark Lawrence | House of Drapery Inc. | Westland PE’s | [5 empty] | 04/13/2020 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
3 |  | 0 | 122413 | Low | Samples | Submittal | ROLLER WINDOW SHADES GHID | C. Samples: For each exposed product and for each color and texture specified, 10 inches (250 mm) long. E. Samples for Verification: For each type of roller shade. 1. Shadeband Material: Not less than 10 inches (250 mm) square. Mark inside face of material if applicable. D. Samples for Initial Selection: For each type and color of shadeband material. 1. Include Samples of accessories involving color selection. |  | 10/04/2021 | Assigned to Sub |  | Mark Lawrence | House of Drapery Inc. | 12/16/2020 | Mark Lawrence | House of Drapery Inc. | Westland PE’s |  |  |  | 280 | 12/08/2020 | 12/16/2020 | 12/18/2020 | 12/28/2020 | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 122413 | Low | Mock-up - Mock-ups use this package. | Mock-Up | ROLLER WINDOW SHADES GHID | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for materials and execution. 1. Approval of mockups does not constitute approval of deviations from the Contract Documents contained in mockups unless Architect specifically approves such deviations in writing. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. 2. Roller Shade: Full-size operating unit, not less than 16 inches (400 mm) wide by 36 inches (900 mm) long for each type of roller shade indicated. 3. Sample of side and sill channel 4. Installation Accessories: Full-size unit, not less than 10 inches (250 mm) long. |  | 10/04/2021 | Assigned to Sub |  | Mark Lawrence | House of Drapery Inc. | 12/16/2020 | Mark Lawrence | House of Drapery Inc. | Westland PE’s |  |  |  | 280 | 12/08/2020 | 12/16/2020 | 12/18/2020 | 12/28/2020 | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 123619 | Low |  | Submittal | WOOD COUNTERTOPS | A. Product Data: For each type of product, including and finishing materials and processes. A. Woodwork Quality Standard Compliance Certificates: AWI Quality Certification Program certificates. A. Fabricator Qualifications: Shop that employs skilled workers who custom fabricate products similar to those required for this Project and whose products have a record of successful in-service performance. Shop is a certified participant in AWI's Quality Certification Program or Shop is a licensee of WI's Certified Compliance Program. B. Installer Qualifications: Certified participant in AWI's Quality Certification Program. C. Testing Agency Qualifications: For testing agency providing classification marking for fire-retardant-treated material, an inspection agency acceptable to authorities having jurisdiction that periodically performs inspections to verify that the material bearing the classification marking is representative of the material tested. B. Shop Drawings: Show location of each item, dimensioned plans and elevations, large-scale details, attachment devices, and other components. 1. Show locations and sizes of cutouts and holes for plumbing fixtures installed in wood countertops. 2. Apply WI Certified Compliance Program label to Shop Drawings. 3. Apply AWI Quality Certification Program label to Shop Drawings. C. Samples for Initial Selection: For shop-applied transparent finishes. |  |  | Assigned to Sub |  | Camron Walker | Westland Construction, Inc. |  | Camron Walker | Westland Construction, Inc. | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 0 | 123640 | Low | Mock-up - Mock-ups use this package. | Mock-Up | STONE COUNTERTOPS GHID | C. Mockups: Build mockups to demonstrate aesthetic effects and to set quality standards for fabrication and execution. 1. Build mockup of typical countertop as shown on Drawings. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. 6. Finish exposed faces of stone to comply with requirements indicated for finish of each stone type required and to match approved Samples and mockups. Provide matching finish on exposed edges of countertops, splashes, and cutouts. |  | 02/08/2021 | Assigned to Sub |  | Connor Cooper | GLOBAL STONE & TILE LLC | 10/07/2020 | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  |  |  | 112 | 09/29/2020 | 10/07/2020 | 10/09/2020 | 10/19/2020 | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 123640 | Low |  | Product Data | STONE COUNTERTOPS GHID | A. Product Data: For each variety of stone, stone accessory and manufactured product. A. Qualification Data: For fabricator. B. Material Test Reports: 1. Stone Test Reports: For each stone variety proposed for use on Project, by a qualified testing agency, indicating compliance with required physical properties, according to referenced ASTM standards. Base reports on testing done within previous 2 years. 2. Sealant Compatibility and Adhesion Test Report: From sealant manufacturer indicating that sealants will not stain or damage stone. A. Fabricator Qualifications: Shop that employs skilled workers who custom-fabricate stone countertops similar to that required for this Project, and whose products have a record of successful in-service performance. B. Installer Qualifications: Fabricator of stone countertops. |  | 02/08/2021 | Assigned to Sub |  | Connor Cooper | GLOBAL STONE & TILE LLC | 12/26/2020 | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  |  |  | 112 | 09/29/2020 | 12/26/2020 | 12/28/2020 | 01/07/2021 | 12/18/2020 | 12/01/2020 |  |  |  |  | 12/18/2019
4 |  | 0 | 123640 | Low | Samples | Submittal | STONE COUNTERTOPS GHID | C. Samples for Verification: For each stone type indicated, in sets of Samples not less than 12 inches (300 mm) square. 1. Include three or more Samples in each set and show the full range of variations in appearance characteristics expected in the completed Work. |  | 02/08/2021 | Closed | Approved |  |  |  | Connor Cooper | GLOBAL STONE & TILE LLC | Westland PE’s |  | Interior Designer |  | 112 | 09/29/2020 | 10/07/2020 | 12/03/2020 | 12/18/2020 | 12/19/2019 | 12/01/2020 | 12/08/2020 | 12/11/2020 |  | 12/17/2020 | 12/18/2019
3 |  | 1 | 123640 | High |  | Shop Drawing | STONE COUNTERTOPS GHID - Up to CCD_40R3 | Updated from CCD Revisions. B. .Shop Drawings: 1. Include plans, sections, details, and attachments to other work. 2. Show locations and details of joints. 3. Show direction of veining, grain, or other directional pattern. |  | 01/18/2021 | Closed | Make Corrections Noted |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | CRSA ARCHITECTURE |  | CRSA ARCHITECTURE |  | 84 | 10/06/2020 | 12/29/2020 | 12/24/2020 | 02/06/2021 | 12/21/2020 | 12/22/2020 | 01/27/2021 | 03/10/2021 |  | 03/15/2021 | 12/21/2020 |  | Interior Designer
5 |  | 0 | 123640 | Medium |  | Submittal | Costa Smeralda Countertop Programming |  |  |  | Closed | No Exception Taken |  |  |  | Jose Duron | GLOBAL STONE & TILE LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 07/07/2021 | 07/09/2021 | 07/02/2021 |  | 06/29/2021 | 06/29/2021 | 06/29/2021 |  | 06/29/2021 | 06/29/2021
1 |  | 0 | 124813 | Low |  | Product Data | ENTRANCE FLOOR MATS AND FRAMES GHID | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for floor mats and frames. B. Shop Drawings: 1. Items penetrating floor mats and frames, including door control devices. 2. Divisions between mat sections. 3. Perimeter floor frames. 4. Custom Graphics: Scale drawing indicating colors. C. Samples: For the following products, in manufacturer's standard sizes: 1. Floor Mat: Assembled sections of floor mat. 2. Frame Members: Sample of each type and color. |  |  | Assigned to Sub |  | Interior Designer |  | 12/15/2020 | Interior Designer |  | Westland PE’s | [5 empty] | 12/15/2020 |  |  | 11/30/2020 | [5 empty] | 12/18/2019
1 |  | 0 | 126700 | Low | Samples | Submittal | TEMPLE PEWS AND BENCHES GHID | A. Samples: 1. 6 inch square wood samples showing finishes of wood for each different finish required on pew specified in this section. 2. 12 inch square fabric sample showing texture, color, etc. |  |  | Closed | See Other |  |  |  | Ryan Haueter | AW Carter LLC | Westland PE’s | [5 empty] | 12/20/2019 |  |  | 12/19/2019 |  |  |  |  | 08/20/2020 | 12/18/2019
3 |  | 0 | 126700 | Low |  | Shop Drawing | TEMPLE PEWS AND BENCHES GHID | Shop Drawings Please confirm finished lengths of the benches. |  |  | Closed | No Exception Taken |  |  |  | Ryan Haueter | AW Carter LLC | Westland PE’s |  | Interior Designer |  |  |  | 01/08/2020 | 01/02/2020 | 01/11/2020 | 12/31/2019 | 12/31/2019 | 01/01/2020 | 04/15/2020 |  | 04/16/2020 | 12/31/2019
7 |  | 0 | 126700 | Medium |  | Submittal | TEMPLE PEWS AND BENCH - 0.5 Level GHID |  |  | 01/04/2021 | Closed |  |  |  |  | Steve Horst | New Holland Church Furniture | David Adams | Westland Construction, Inc. | Interior Designer |  | 0 | 12/15/2020 | 02/12/2021 | 02/14/2021 | 02/24/2021 | 02/04/2021 | 02/04/2021 | 10/13/2020 | 01/26/2021 | 02/04/2021 | 02/04/2021 | 10/13/2020
8 |  | 0 | 126700 | Low | Samples | Submittal | AUDIENCE SEATING GHID | A. Samples: 1. 6 inch square wood samples showing finishes of wood for each different finish required on pew specified in this section. 2. 12 inch square fabric sample showing texture, color, etc. |  |  | Assigned to Sub |  | Austin Gifford | Fetzer`s Inc. | 02/24/2021 | Austin Gifford | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. |  |  |  |  | 02/24/2021 | 02/27/2021 | 03/09/2021 | 03/09/2021 | 02/27/2021 |  |  |  | 08/20/2020 | 02/17/2021
9 |  | 0 | 126700 | Low |  | Shop Drawing | AUDIENCE SEATING GHID | Shop Drawings |  |  | Closed | Make Corrections Noted |  |  |  | Austin Gifford | Fetzer`s Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 02/24/2021 | 02/27/2021 | 03/23/2021 | 02/17/2021 | 02/27/2021 | 03/09/2021 | 03/23/2021 |  | 03/23/2021 | 02/17/2021 |  | Interior Designer
1 |  | 0 | 129300 | Low |  | Product Data | SITE FURNISHINGS | A. Product Data: Submit manufacturer's technical product data and installation instructions for specified materials and products. |  |  | Closed | Approved As Noted |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects | [5 empty] | 01/06/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 12/24/2019 |  | 12/31/2019 | 12/18/2019
4 |  | 0 | 129300 | High | Samples | Submittal | SITE FURNISHINGS | BENCHES AND TRASH RECEPTACLE: PLEASE PROVIDE BRONZE COLOR SAMPLE FOR REVIEW AND APPROVAL. Added per Submittal 1 response. |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 01/08/2020 | 03/07/2020 | 03/29/2020 | 12/31/2019 | 03/05/2020 | 03/19/2020 | 03/31/2020 |  | 04/01/2020 | 12/31/2019
5 |  | 0 | 129300 | Low |  | Product Data | SITE FURNISHINGS | REMAINING SITE FURNITURE: STILL NEED SUBMITTALS AND/OR SHOP DRAWINGS FOR: DRINKING FOUNTAIN, CURVED BENCH, NEW FENCE, AND ANY OTHER ITEMS AS INDICATED IN PLANS AND SPECS. Added per Submittal 1 response. |  |  | Closed | No Exception Taken |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/08/2020 | 01/17/2020 | 02/14/2020 | 12/31/2019 | 01/15/2020 | 02/05/2020 | 02/05/2020 |  | 02/10/2020 | 12/31/2019
6 |  | 0 | 129300 | Low |  | Product Data | SITE FURNISHINGS | Black Steel Edging. Submitted under site furnishings however no spec was provided. Product appears on LL501. Samples included as part of this submittal. |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 03/27/2020 | 03/21/2020 | 03/29/2020 | 12/19/2019 | 03/19/2020 | 03/19/2020 | 03/31/2020 |  | 04/01/2020 | 03/19/2020
7 |  | 0 | 129300 | High |  | Submittal | SITE FURNISHINGS - Valve Boxes Under Pots | Valve Boxes under Longshadow Pots |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 01/30/2021 | 02/01/2021 | 02/01/2021 | 12/19/2019 | 01/22/2021 | 01/22/2021 | 02/01/2021 |  | 02/04/2021 | 01/22/2021
3 |  | 0 | 131213 | Low | Samples | Submittal | SPECIAL CONSTRUCTION –Exterior Fountains | Custom Fountain Tile |  |  | Closed | Final |  |  |  | Bob Durrant | IMS Masonry Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 08/25/2020 | 08/27/2020 | 08/27/2020 | 08/17/2020 | 08/17/2020 | 08/17/2020 |  | 08/21/2020 | 08/21/2020 | 08/17/2020
2 |  | 2 | 131213 | Low | Samples | Submittal | SPECIAL CONSTRUCTION –Exterior Fountains | Samples Fountain Cobble & Fountain Grating |  |  | Closed | Make Corrections Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Melissa Fryer | CRSA ARCHITECTURE | Landscape Architects |  |  |  | 09/21/2020 | 06/26/2020 | 12/21/2020 |  |  | 12/11/2020 | 12/15/2020 |  | 02/02/2021 | 12/11/2020 | CRSA ARCHITECTURE
4 |  | 1 | 131213 | Medium | DWGS - Shop Drawings | Submittal | NORTH & EAST FOUNTAIN PRODUCTION DRAWINGS RFI_831 | Update Per RFI_831 Please review the included North (FP-0801-WESTLAND) and EAST (FP-0161-WESTLAND) FOUNTAIN production drawings. |  |  | Closed | Approved |  |  |  | Mark Gabriele | Artisan Granite, LLC | Camron Walker | Westland Construction, Inc. | Landscape Architects |  | 0 |  | 12/15/2020 | 11/15/2020 | 02/19/2021 | 12/14/2020 | 12/14/2020 | 02/09/2021 | 03/13/2021 |  | 03/23/2021 | 12/14/2020
1 |  | 3 | 131213 | High |  | Product Data | SPECIAL CONSTRUCTION –Exterior Fountains | Submit five (5) copies of manufacturer's performance data, specifications and installation instructions for each accessory and/or equipment specified. Submittal shall be made to the Architect for approval prior to beginning any work on the fountain. Submit for the following: 1. Pipe & Pipe Fittings 2. Fountain Fittings 3. Valves, each type 4. Filters 5. Pumps, each type 6. Pump strainers 7. Inlet fittings and outlet fittings, and diverter plates 8. Chemical Controller w/ sensors 9. Chemical Feeders & storage tanks 10. Instrumentation, controls, & sensors 11. Water Level Controls 12. Chemicals (MSDS Sheets) 13. Waterstops 14. Sealants & Caulking 15. Waterproofing materials 16. Veneer, Stones, Tiles, Finishes (if applicable) 17. False Floor System (if applicable) 18. Fountain lights and j-boxes 19. Cleaning and Testing Equipment 20. Flow Meters 21. Pipe Penetration Seals 22. Concrete Experience Data (If applicable) 23. Quality Assurance Information Submit five (5) samples of products for each accessory and/or equipment item specified. Samples shall be minimum 2” x 2”. Manufacturer’s catalogs or pictures are not acceptable as a substitute for sample submission. Submittal of samples shall be made to the Architect for approval prior to beginning any work on the fountain. Submit samples for the following: 1. Waterproofing Materials 2. Veneers, Stones, Tile, Finishes, Etc (if applicable) 3. False Floor System (if applicable) The system shall carry a 12-month warranty against defects in material and workmanship, all components in the system, including electronic, flow cell assembly, probes, and cabinets. 5.17 AUTOMATIC WATER LEVEL CONTROLLER: Provide a fully automatic dual-level electronic level control system designed to maintain precise water levels for fountain applications. The controller shall detect the level of the water in the fountain to within a fraction of an inch accurately. The controller shall include a time delay sequence to avoid water fill cycling. It shall also include an adjustable feed alarm timer to interrupt water flow in the event of a problem. Sensor located in housing at fountain. Provide a one year warranty. The controller shall activate a low-voltage supply (24 VAC) connected to a solenoid valve that controls flow into the fountain. The solenoid valve shall be supplied and installed by the Fountain Contractor. Install as per Manufacturer’s Instructions. 7.02 GUARANTEES AND WARRANTIES: Construction: The successful bidder shall guarantee the fountain to the Owner for the period of one (1) year from the date of final completion. The successful bidder shall guarantee the fittings and equipment to the Owner for the period of one year, or per the equipment manufacturer’s warranty, whichever is greater. A 24-hour response time is required for servicing warranty items. In the event that the fountain contractor fails to provide the required service within 24 hours, the fountain contractor is liable for any cost the owner incurs if the owner chooses to provide the service (assuming the fountain contractor’s 24-hour response time has lapsed). If parts are needed from out of state/country, they shall be expedited. Failure to respond within 24 hours may result in owner providing service from another source and the fountain contractor back charged. |  |  | Closed | Approved As Noted |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 03/26/2021 |  | 04/09/2021 | 03/31/2021 | 03/31/2021 | 03/31/2021 | 04/15/2021 |  | 04/15/2021 | 03/17/2021
1 |  | 0 | 142123 | Low |  | Product Data | MACHINE ROOM-LESS ELECTRIC TRACTION PASSENGE | A. Product Data: For each type of product. 1. Include capacities, sizes, performances, operations, safety features, finishes, and similar information. 2. Include Product Data for car enclosures, hoistway entrances, and operation, control, and signal systems. A. Qualification Data: For Installer. B. Seismic Qualification Certificates: For elevator equipment, accessories, and components, from manufacturer. 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. 2. Dimensioned Outline Drawings of Equipment Unit: Identify center of gravity and locate and describe mounting and anchorage provisions. 3. Detailed description of equipment anchorage devices on which the certification is based and their installation requirements. C. Sample Warranty: For special warranty. |  |  | Closed | Make Corrections Noted |  |  |  | Alan Sansom | Otis Elevator Company | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 08/26/2020 | 12/19/2019 | 08/04/2020 | 08/11/2020 | 12/01/2020 |  | 12/08/2020 | 12/18/2019 |  | Electrical Engineers
2 |  | 0 | 142123 | High |  | Shop Drawing | MACHINE ROOM-LESS ELECTRIC TRACTION PASSENGE | B. Shop Drawings: 1. Include plans, elevations, sections, and large-scale details indicating service at each landing, coordination with building structure, relationships with other construction, and locations of equipment. 2. Include large-scale layout of car-control station 3. Indicate maximum dynamic and static loads imposed on building structure at points of support, and maximum and average power demands. |  |  | Closed | Make Corrections Noted |  |  |  | Alan Sansom | Otis Elevator Company | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 01/02/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 04/29/2020 |  | 04/30/2020 | 12/18/2019
4 |  | 0 | 142123 | Low |  | Submittal | MACHINE ROOM-LESS ELECTRIC TRACTION PASSENGE (Elev 1 Resub) | Submittal for Elevator 1 Change. |  |  | Closed | No Exception Taken |  |  |  | Alan Sansom | Otis Elevator Company | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 08/28/2020 |  |  | 08/11/2020 | 08/04/2020 | 10/19/2020 | 12/04/2020 |  | 12/08/2020 | 08/11/2020
5 |  | 1 | 142123 | High | Samples | Submittal | MACHINE ROOM-LESS ELECTRIC TRACTION PASSENGE GHID | Bronze Sample - Elevator Doors: Medium Oxidized Bronze Sample - Car & Hall Fixture Faceplates: Medium Oxidized |  |  | Closed | Approved |  |  |  | Alan Sansom | Otis Elevator Company | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 12/24/2020 | 09/07/2020 | 03/19/2021 | 12/18/2020 | 03/09/2021 | 03/09/2021 | 03/18/2021 |  | 03/18/2021 | 12/18/2020
1 |  | 0 | 144216 | Low |  | Submittal | VERTICAL WHEELCHAIR LIFTS | 1. Product Data: a. Provide Manufacturer's product literature including the following: 1) Delivery, storage, and handling requirements. 2) Preparation requirements. 3) Installation instruction. b. Provide description of performance and operating characteristics. c. Provide electrical requirements.1. Qualification Statement: a. Installer: 1) Provide Qualification documentation if requested by Architect or Owner: 2. Shop Drawings: a. Show complete layout and location of equipment, including required clearances and coordination with vertical wheelchair lift. b. Provide accurate shop and erection drawings and diagrams showing deviations from Contract Drawings in ample time to make necessary adjustments in structural system of Project to fit particular equipment for Approved Equivalent. 1) Adjustments necessary due to failure to give proper information in sufficient time to make proper adjustments shall be made without any additional cost to Owner. c. Provide wiring diagrams. |  |  | Closed | Make Corrections Noted |  |  |  | Matt Aardema | Able Access Elevator & Lift Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/20/2019 |  | 09/18/2020 | 04/01/2020 | 08/12/2020 | 09/04/2020 | 12/01/2020 |  | 12/03/2020 | 12/18/2019
2 |  | 1 | 144216 | Medium |  | Submittal | Vertical Wheelchair Lift - Color Chart |  |  |  | Assigned to Sub |  | Matt Aardema | Able Access Elevator & Lift Inc. | 07/14/2021 | Matt Aardema | Able Access Elevator & Lift Inc. | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 07/14/2021 | 07/16/2021 | 07/20/2021 | 07/14/2021 | [5 empty] | 07/14/2021
1 |  | 0 | 149133 | High |  | Product Data | LAUNDRY AND LINEN CHUTES | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for chutes. A. Qualification Data: For fire-rated door inspector. 1. Fire-Rated Door Inspector: Submit documentation of compliance with NFPA 80, section 5.2.3.1. 2. Submit copy of DHI Fire and Egress Door Assembly Inspector (FDAI) certificate. C. Product Certificates: For each type of chute. D. Field quality control reports. |  |  | Assigned to Sub |  | Chris McCleery | Mountain Stainless, Inc. | 04/23/2021 | Chris McCleery | Mountain Stainless, Inc. | Westland PE’s |  |  |  |  | 04/23/2021 | 04/30/2021 |  |  | 04/22/2021 | 04/20/2021 |  |  |  |  | 12/18/2019
2 |  | 0 | 149133 | High |  | Shop Drawing | LAUNDRY AND LINEN CHUTES | B. Shop Drawings: 1. Include plans, elevations, sections, and mounting and attachment details. 2. Include dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection. 3. Include each type and location of intake, discharge, and access door. B. Coordination Drawings: Plan(s) and other details drawn to scale, on which the following items are shown and coordinated with each other, using input from installers of the items involved: 1. Size and construction of chase enclosing each chute; locations for power, signal, and control wiring; and sprinkler-piping and water-service connections. 2. Chute-discharge locations coordinated with compactor-intake or container locations. |  |  | Closed | Approved As Noted |  |  |  | Chris McCleery | Mountain Stainless, Inc. | Westland PE’s |  | CRSA ARCHITECTURE |  |  | 04/23/2021 | 04/23/2021 |  | 04/27/2021 | 11/30/2020 | 04/20/2021 | 04/20/2021 | 05/24/2021 |  | 06/02/2021 | 12/18/2019
1 |  | 2 | 211000 | Low |  | Product Data | WATER-BASED FIRE-SUPPRESSION SYSTEMS | A. Product Data: For the following: 1. Piping materials, including dielectric fittings, flexible connections, and sprinkler specialty fittings. 2. Pipe hangers and supports, including seismic restraints. 3. Valves, including listed fire-protection valves, unlisted general-duty valves, and specialty valves and trim. 4. Air compressors, including electrical data. 5. Sprinklers, escutcheons, and guards. Include sprinkler flow characteristics, mounting, finish, and other pertinent data. 6. Hose connections, including size, type, and finish. 7. Fire department connections, including type; number, size, and arrangement of inlets; caps and chains; size and direction of outlet; escutcheon and marking; and finish. 8. Alarm devices, including electrical data. D. Seismic Calculations. Material and Test Certificate for Aboveground Piping" and "Contractor's Material and Test Certificate for Underground Piping.A. Unless noted otherwise the following applies: 1. The maximum water velocity shall not exceed 32-fps. 2. Submit the calculations using the reduced flow data. 3. In the event of multiple (3) submittal rejections (including revise and resubmit) a meeting shall be held at the engineer’s office at the engineer time of choosing and the designer, fire sprinkler contractor, and general contractor shall be physically in attendance to discuss the required modifications to the design. G. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/02/2020 |  | 11/26/2020 | 07/22/2020 | 11/11/2020 | 11/12/2020 | 11/30/2020 |  | 11/30/2020 | 07/22/2020
2 |  | 4 | 211000 | High |  | Shop Drawing | WATER-BASED FIRE-SUPPRESSION SYSTEMS | B. Shop Drawings: Diagram power, signal, and control wiring. E. Approved Sprinkler Piping Drawings: Working plans, prepared according to NFPA 13, that have been approved by authorities having jurisdiction, including hydraulic calculations, if applicable. Drawings are to be approved by Engineer prior to submission to State Fire Marshal. Drawings are to be submitted to FM Global prior to submission to Engineer. |  |  | Closed | Approved As Noted |  |  |  | Brad Bartlett | Broken Arrow Inc | Westland PE’s |  | Jeff Adams | CRSA ARCHITECTURE |  |  | 11/13/2020 |  | 12/15/2020 |  | 11/30/2020 | 11/30/2020 | 12/10/2020 |  | 12/10/2020 | 11/30/2020
3 |  | 0 | 211000 | Medium | Samples | Submittal | WATER-BASED FIRE-SUPPRESSION SYSTEMS (Escutcheon Color Sample) | Escutcheon Color Sample |  |  | Closed | Approved |  |  |  | Brad Bartlett | Broken Arrow Inc | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 04/16/2021 | 04/18/2021 | 04/18/2021 | 07/22/2020 | 04/08/2021 | 04/08/2021 | 04/09/2021 |  | 04/09/2021 | 04/08/2021
1 |  | 0 | 220000 | Medium |  | Submittal | PLUMBING AND MECH PIPE DRAWINGS - MEZZANINE |  |  |  | Closed | No Exception Taken |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 10/22/2020 | 10/24/2020 | 10/24/2020 | 10/14/2020 |  | 10/14/2020 | 10/27/2020 |  | 10/28/2020 | 10/14/2020
1 |  | 0 | 220500 | Low |  | Product Data | COMMON WORK RESULTS FOR PLUMBING | A. Product Data: For the following: 1. Transition fittings. 2. Dielectric fittings. 3. Mechanical sleeve seals. 4. Escutcheons. B. Welding certificates. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 07/16/2020 | 12/18/2019
2 |  | 0 | 220500 | Low |  | Submittal | Vacuum Pump for Annex Mech Room 032 |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 02/02/2021 | 02/04/2021 | 02/04/2021 | 12/19/2019 | 01/25/2021 | 01/25/2021 | 02/08/2021 |  | 02/09/2021 | 01/25/2021
1 |  | 0 | 220516 | Low |  | Product Data | EXPANSION FITTINGS AND LOOPS FOR PLUMBING PIPIN | A. Product Data: For each type of product indicated. A. Welding certificates. B. Product certificates. A. Welding Qualifications: Qualify procedures and personnel according to the following: 1. AWS D1.1/D1.1M, "Structural Welding Code - Steel." 2. ASME Boiler and Pressure Vessel Code: Section IX. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/25/2020 | 12/19/2019 | 01/09/2020 | 01/10/2020 | 01/29/2020 |  | 01/29/2020 | 12/18/2019
1 |  | 1 | 220517 | Low |  | Product Data | SLEEVES AND SLEEVE SEALS FOR PLUMBING PIPING | A. Product Data: For each type of product indicated. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/31/2020 |  | 03/09/2020 | 01/28/2020 | 02/04/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 01/28/2020
1 |  | 0 | 220518 | Low |  | Product Data | ESCUTCHEONS FOR PLUMBING PIPING | A. Product Data: For each type of product indicated |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/25/2020 | 12/19/2019 | 01/09/2020 | 01/10/2020 | 02/13/2020 |  | 02/19/2020 | 12/18/2019
1 |  | 0 | 220519 | Low |  | Product Data | METERS AND GAGES FOR PLUMBING PIPING | Product Data: For each type of product indicated. A. Product certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/25/2020 | 12/19/2019 | 01/09/2020 | 01/10/2020 | 01/28/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 220523 | Low |  | Product Data | GENERAL-DUTY VALVES FOR PLUMBING PIPING | A. Product Data: For each type of valve indicated. |  |  | Closed | Rejected |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  |  | 12/19/2019 | 01/09/2020 | 01/10/2020 | 01/28/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 220529 | Low |  | Product Data | HANGERS AND SUPPORTS FOR PLUMBING PIPING AND | A. Product Data: For the following: 1. Steel pipe hangers and supports. 2. Thermal-hanger shield inserts. 3. Powder-actuated fastener systems. 4. Pipe positioning systems. 5. Mechanical Anchors: ICC-ES Evaluation Reports validating ‘Cracked Concrete’ testing per A.C. 193 must be provided for anchors resisting seismic loads and/or supporting life- safety systems including fire sprinkler systems. C. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/20/2020 | 12/19/2019 | 12/30/2019 | 01/02/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
3 |  | 0 | 220529 | Low |  | Product Data | HANGERS AND SUPPORTS FOR PLUMBING PIPING AND | Additional Anchors for Review Add Dewalt Wood Anchors Add Concrete Form Anchors A. Product Data: For the following: 1. Steel pipe hangers and supports. 2. Thermal-hanger shield inserts. 3. Powder-actuated fastener systems. 4. Pipe positioning systems. 5. Mechanical Anchors: ICC-ES Evaluation Reports validating ‘Cracked Concrete’ testing per A.C. 193 must be provided for anchors resisting seismic loads and/or supporting life- safety systems including fire sprinkler systems. C. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/03/2020 | 02/26/2020 | 03/09/2020 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 02/24/2020
1 |  | 0 | 220533 | Low |  | Product Data | HEAT TRACING FOR PLUMBING PIPING | A. Product Data: Include rated capacities, operating characteristics, furnished specialties, and accessories for each type of product indicated. 1. Schedule heating capacity, length of cable, spacing, and electrical power requirement for each electric heating cable required. C. Field quality-control test reports. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/25/2020 | 12/19/2019 | 01/09/2020 | 01/10/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 220548 | High |  | Submittal | Vibration and Seismic Controls For Plumbing |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 08/22/2020 | 08/24/2020 | 08/24/2020 | 08/14/2020 | 08/14/2020 | 08/14/2020 | 09/01/2020 |  | 09/14/2020 | 08/14/2020
1 |  | 0 | 220553 | Low |  | Product Data | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPME | A. Product Data: For each type of product indicated. C. Equipment Label Schedule: Include a listing of all equipment to be labeled with the proposed content for each label. D. Valve numbering scheme. E. Valve Schedules: For each piping system to include in maintenance manuals. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/28/2020 | 12/19/2019 | 01/10/2020 | 01/13/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
2 |  | 0 | 220553 | Low | Samples | Submittal | IDENTIFICATION FOR PLUMBING PIPING AND EQUIPME | B. Samples: For color, letter style, and graphic representation required for each identification material and device. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 09/03/2020 | 12/19/2019 | 08/19/2020 | 08/19/2020 | 09/16/2020 |  | 09/18/2020 | 12/18/2019
1 |  | 0 | 220716 | Low |  | Product Data | PLUMBING EQUIPMENT INSULATION | A. Product Data: For each type of product indicated. |  |  | Closed | Approved |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 11/25/2019 | 10/23/2019 | 11/13/2019 | 12/03/2019 | 12/03/2019 | 11/27/2019 | 12/21/2019 | 09/10/2019 |  | Mechanical Engineers
2 |  | 0 | 220719 | Low |  | Product Data | PLUMBING PIPING INSULATION | A. Product Data: For each type of product indicated. Include thermal conductivity, water-vapor permeance thickness, and jackets (both factory- and field-applied, if any). (data may have been submitted previously)A. Qualification Data: For qualified Installer. B. Material Test Reports: From a qualified testing agency acceptable to authorities having jurisdiction indicating, interpreting, and certifying test results for compliance of insulation materials, sealers, attachments, cements, and jackets, with requirements indicated. Include dates of tests and test methods employed. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
1 |  | 1 | 220719 | Low |  | Product Data | PLUMBING PIPING INSULATION | A. Product Data: For each type of product indicated. Include thermal conductivity, water-vapor permeance thickness, and jackets (both factory- and field-applied, if any). |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 03/09/2020 |  | 02/24/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 02/24/2020
1 |  | 1 | 221116 | Low |  | Product Data | DOMESTIC WATER PIPING | Includes changes in RFI 41 and updates per revise resubmit instructions. A. Product Data: For transition fittings and dielectric fittings. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/17/2020 |  | 01/02/2020 | 01/02/2020 | 01/02/2020 |  | 01/02/2020 | 01/02/2020
1 |  | 0 | 221119 | Low |  | Product Data | DOMESTIC WATER PIPING SPECIALTIES | A. Product Data: For each type of product indicated. |  |  | Closed | Rejected |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/25/2020 | 12/19/2019 | 01/09/2020 | 01/10/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
4 |  | 0 | 221119 | Low |  | Product Data | DOMESTIC WATER PIPING SPECIALTIES | Resubmittal for Trap seal primers. Provide elastomeric trap seal per schedule on P601. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/05/2020 | 01/31/2020 | 02/14/2020 | 01/28/2020 | 01/29/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 01/28/2020
5 |  | 0 | 221119 | High |  | Submittal | DOMESTIC WATER PIPING SPECIALTIES – Layout Annex Baxter BIM | This is the updated layout resulting from BIM Coordination. |  |  | Closed | Make Corrections Noted |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 09/08/2020 | 09/08/2020 | 09/15/2020 | 09/08/2020 | 09/08/2020 | 09/08/2020 | 09/16/2020 |  | 09/30/2020 | 09/08/2020
1 |  | 1 | 221123 | Low |  | Product Data | DOMESTIC WATER PUMPS | A. Product Data: For each type and size of domestic water pump specified. Include certified performance curves with operating points plotted on curves; and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 03/09/2020 |  | 02/24/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 02/24/2020
2 |  | 0 | 221316 | High |  | Product Data | SANITARY WASTE AND VENTING PIPING | A. Product Data: For each type of product indicated. A. Seismic Qualification Certificates: For waste and vent piping, accessories, and components, from manufacturer. 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. 2. Detailed description of piping anchorage devices on which the certification is based and their installation requirements. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/10/2020 | 12/19/2019 | 12/31/2019 | 01/01/2020 | 01/02/2020 |  | 01/02/2020 | 12/18/2019
1 |  | 1 | 221316 | Low |  | Product Data | SANITARY WASTE AND VENTING PIPING | A. Product Data: For each type of product indicated. A. Seismic Qualification Certificates: For waste and vent piping, accessories, and components, from manufacturer. 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. 2. Detailed description of piping anchorage devices on which the certification is based and their installation requirements. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 01/02/2020 | 12/21/2019 |  |  |  |  | 11/23/2020 | 12/21/2019
1 |  | 0 | 221319 | High |  | Product Data | SANITARY WASTE PIPING SPECIALTIES | A. Product Data: For each type of product indicated. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 02/21/2020 | 12/19/2019 | 02/07/2020 | 02/10/2020 | 02/18/2020 |  | 02/20/2020 | 12/18/2019
3 |  | 0 | 221319 | High |  | Product Data | SANITARY WASTE PIPING SPECIALTIES | Added items for Backwater Valves |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/03/2020 | 03/05/2020 | 03/05/2020 | 12/19/2019 | 02/24/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 02/24/2020
4 |  | 0 | 221319 | High |  | Submittal | SANITARY WASTE PIPING SPECIALTIES - Annex Baxter BIM |  |  |  | Closed | No Exception Taken |  |  |  | Justun Bylund | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  | 0 |  | 09/08/2020 | 09/08/2020 | 09/18/2020 | 09/08/2020 | 09/08/2020 | 09/08/2020 | 09/16/2020 |  | 09/18/2020 | 09/08/2020
1 |  | 0 | 221323 | High |  | Product Data | SANITARY WASTE INTERCEPTORS | A. Product Data: For each type of interceptor indicated. Include materials of fabrication, dimensions, rated capacities, retention capacities, operating characteristics, size and location of each pipe connection, furnished specialties, and accessories. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 02/14/2020 | 12/19/2019 | 01/23/2020 | 01/30/2020 | 02/18/2020 |  | 02/18/2020 | 12/18/2019
3 |  | 0 | 221323 | High |  | Product Data | SANITARY WASTE INTERCEPTORS (Round) | A. Product Data: For each type of interceptor indicated. Include materials of fabrication, dimensions, rated capacities, retention capacities, operating characteristics, size and location of each pipe connection, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 02/29/2020 | 02/18/2020 | 02/18/2020 | 02/18/2020 | 03/18/2020 |  | 03/26/2020 | 02/18/2020
1 |  | 1 | 221413 | High |  | Product Data | STORM DRAINAGE PIPING | Corrected to PVC Solid Wall. Add Epoxy-coated Cast Iron per RFI#30. A. Product Data: For pipe, tube, fittings, and couplings |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/10/2020 |  | 01/02/2020 | 01/02/2020 | 01/02/2020 |  | 01/02/2020 | 01/02/2020
1 |  | 0 | 221423 | Low |  | Product Data | STORM DRAINAGE PIPING SPECIALTIES | A. Product Data: For each type of product indicated. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 07/16/2020 | 12/18/2019
1 |  | 0 | 221429 | Low |  | Product Data | SUMP PUMPS | A. Product Data: For each type and size of sump pump specified. Include certified performance curves with operating points plotted on curves, and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 11/15/2019 | 12/17/2019 | 12/17/2019 | 10/28/2019 |  | 12/17/2019 | 12/17/2019 | 09/10/2019
4 |  | 0 | 221429 | High |  | Product Data | SUMP PUMPS (Ground Water) | DeWatering Pipe for Ground Water Sump Pumps A. Product Data: For each type and size of sump pump specified. Include certified performance curves with operating points plotted on curves, and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/08/2020 | 01/02/2020 | 01/10/2020 | 12/31/2019 | 12/31/2019 | 01/02/2020 | 01/14/2020 | 12/17/2019 | 01/23/2020 | 12/31/2019
5 |  | 0 | 221429 | Low |  | Product Data | SUMP PUMPS (Grease Waste) | Sump pump for Grease Waste A. Product Data: For each type and size of sump pump specified. Include certified performance curves with operating points plotted on curves, and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/08/2020 | 01/02/2020 | 01/20/2020 | 12/31/2019 | 12/31/2019 | 01/02/2020 | 01/23/2020 | 12/17/2019 | 01/24/2020 | 12/31/2019
6 |  | 0 | 221429 | Low |  | Product Data | SUMP PUMPS (Water) | Submersible Sump Pumps for Water A. Product Data: For each type and size of sump pump specified. Include certified performance curves with operating points plotted on curves, and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/08/2020 | 01/02/2020 | 01/20/2020 | 12/31/2019 | 12/31/2019 | 01/02/2020 | 01/23/2020 | 12/17/2019 | 01/24/2020 | 12/31/2019
7 |  | 0 | 221429 | Low |  | Product Data | SUMP PUMPS (Perforated Pipe) | Revised De-Watering Pipe and Fittings Pipe for SP-5A, 5B, 6A & 6B A. Product Data: For each type and size of sump pump specified. Include certified performance curves with operating points plotted on curves, and rated capacities of selected models, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/21/2020 | 01/15/2020 | 01/23/2020 | 01/13/2020 | 01/13/2020 | 01/13/2020 | 01/23/2020 | 12/17/2019 | 01/24/2020 | 01/13/2020
1 |  | 0 | 224000 | Low |  | Product Data | PLUMBING FIXTURES | A. Product Data: For each type of plumbing fixture indicated. Include selected fixture and trim, fittings, accessories, appliances, appurtenances, equipment, and supports. Indicate materials and finishes, dimensions, construction details, and flow-control rates. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Jeff Adams | CRSA ARCHITECTURE |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/26/2019 | 11/26/2019 | 01/07/2020 |  | 01/08/2020 | 09/10/2019
4 |  | 0 | 224000 | Low |  | Product Data | PLUMBING FIXTURES | Additional Item Per P701 Schedule |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/03/2020 | 03/05/2020 | 03/09/2020 | 02/24/2020 | 02/24/2020 | 02/24/2020 | 02/28/2020 |  | 03/02/2020 | 02/24/2020
5 |  | 0 | 224000 | High |  | Product Data | PLUMBING FIXTURES (CCD_54.4R1) | Zurn Trench Drain substitution in lieu of the custom stainless steel trench drain TD-1 from P601 in CCD_54.4 Ref CCD_54.4R1 A. Product Data: For each type of plumbing fixture indicated. Include selected fixture and trim, fittings, accessories, appliances, appurtenances, equipment, and supports. Indicate materials and finishes, dimensions, construction details, and flow-control rates. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 07/28/2020 | 07/22/2020 | 07/30/2020 | 07/20/2020 | 07/20/2020 | 07/20/2020 | 07/29/2020 |  | 07/30/2020 | 07/20/2020
6 |  | 0 | 224000 | Medium |  | Product Data | PLUMBING FIXTURES (Moen Faucet) |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 12/23/2020 | 12/25/2020 | 12/25/2020 | 12/15/2020 | 12/15/2020 | 12/15/2020 | 12/17/2020 |  | 12/18/2020 | 12/15/2020 | CRSA ARCHITECTURE
7 |  | 0 | 224000 | Medium |  | Submittal | PLUMBING FIXTURES - Faucet Finish |  |  |  | Closed | Approved |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | Interior Designer |  | 0 |  | 05/20/2021 | 05/22/2021 | 06/01/2021 | 05/12/2021 | 05/12/2021 | 05/12/2021 | 05/25/2021 |  | 06/02/2021 | 05/12/2021
1 |  | 0 | 224500 | Low |  | Product Data | EMERGENCY PLUMBING FIXTURES | A. Product Data: For each type of product indicated. Include flow rates and capacities, furnished specialties, and accessories. C. Product Certificates: Submit certificates of performance testing specified in "Source Quality Control" Article. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 | 02/04/2020 |  |  |  | 02/24/2020 | 12/18/2019
1 |  | 0 | 224716 | Low |  | Product Data | PRESSURE WATER COOLERS | A. Product Data: For each type of pressure water cooler. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes. 2. Include rated capacities, operating characteristics, electrical characteristics, and furnished specialties and accessories. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 | 02/04/2020 |  |  |  | 02/24/2020 | 12/18/2019
1 |  | 0 | 224813 | Low |  | Shop Drawing | FONT PLUMBING SYSTEM | A. Submit shop drawings for the Packaged Skid Mounted Baptismal Font System. 1. Diagram for electrical control system showing related electrical control items. Include on drawings electrical power requirements and connection locations. 2. Diagram for electrical wiring. 3. Drawing with dimensioned skid with skid mounted equipment. Include equipment schedule and material list. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/26/2019 | 11/26/2019 | 12/11/2019 |  | 12/18/2019 | 09/10/2019
1 |  | 0 | 226701 | High |  | Product Data | DEIONIZED PURE WATER SYSTEM | A. Submit product data: 1. Manufacturer’s Literature and Data: a. Thermostatic Mixing Valve b. Activated Carbon Filter c. Reverse Osmosis Systems d. Storage Tank with Breather Filters e. Level Controls f. Repressure Pumps g. Ultraviolet Sterilizer h. Ultraviolet Sterilizer i. 0.2 Sub-micron Final Post Filter j. Water Quality Resistivity Control/Monitor & Alarm k. Pressure Sustaining Valve 2. The equipment shall be installed under the supervision of a manufacturer’s representative who will place the equipment in service and instruct the owner’s personnel in its operation, care, and maintenance. 3. All brackets, hangers, supports, unions, valves, drains, controls etc. necessary for a complete and operating system shall be provided and installed by this section. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 03/06/2020 | 10/23/2019 | 11/26/2019 | 02/25/2020 | 02/25/2020 |  | 02/25/2020 | 09/10/2019
1 |  | 1 | 226710 | Low |  | Product Data | PURE WATER PIPING | A. Product Data: For each type of pipe and fitting indicated. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/30/2019 | 12/18/2019 | 12/18/2019 | 12/20/2019 | 12/31/2019 |  | 01/02/2020 | 12/18/2019
2 |  | 0 | 226710 | Low |  | Product Data | PURE WATER PIPING | A. Product Data: For each type of pipe and fitting indicated. B. Welding certificates. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
1 |  | 1 | 230000 | High | Samples | Submittal | CD-6 CEILING DIFFUSER FINISH TYPE | HVAC ceiling diffuser CD-6 located at the level 4 barrel ceiling assembly room, approved submittal indicates finish to be 26-White. |  |  | Assigned to Sub |  | Justun Bylund | US Mechanical LLC | 03/31/2021 | Justun Bylund | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 03/31/2021 | 03/13/2021 | 03/13/2021 | 03/23/2021 | [5 empty] | 03/23/2021
1 |  | 0 | 230150 | Low |  | Submittal Register | TEMPORARY USE OF EQUIPMENT AND SYSTEMS | A. If it is determined by the owner that equipment or systems are needed to operate to provide heating, cooling or other needed services this division shall submit a document indicating what measures will be taken to insure the safe and proper operation of the equipment, systems and personal associated with the operation, this document shall be submitted to the engineer for approval. This plan shall show connections of equipment, utility hookups (if required) staging areas etc. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  |  | 10/23/2019 | 10/31/2019 |  |  | 11/06/2019 | 11/06/2019 | 09/10/2019
1 |  | 0 | 230500 | Low |  | Product Data | COMMON WORK RESULTS FOR HVAC | A. Product Data: For the following: 1. Transition fittings. 2. Dielectric fittings. 3. Mechanical sleeve seals. 4. Escutcheons. B. Welding certificates. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 07/16/2020 | 12/18/2019
1 |  | 0 | 230516 | Low |  | Product Data | EXPANSION FITTINGS AND LOOPS FOR HVAC PIPING | A. Product Data: For each type of product indicated. A. Welding certificates. B. Product Certificates: For each type of expansion joint, from manufacturer. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 03/09/2020 | 12/19/2019 | 02/04/2020 | 02/24/2020 | 03/14/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 0 | 230517 | Low |  | Product Data | SLEEVES AND SLEEVE SEALS FOR HVAC PIPING | A. Product Data: For each type of product indicated. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 03/09/2020 | 12/19/2019 | 02/04/2020 | 02/24/2020 | 03/14/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 0 | 230518 | Low |  | Product Data | ESCUTCHEONS FOR HVAC PIPING | A. Product Data: For each type of product indicated |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 04/03/2020 | 12/19/2019 | 02/04/2020 | 03/26/2020 | 04/16/2020 |  | 04/30/2020 | 12/18/2019 |  | Interior Designer
1 |  | 0 | 230519 | Low |  | Product Data | METERS AND GAGES FOR HVAC PIPING | A. Product Data: For each type of product indicated. A. Product Certificates: For each type of meter and gage, from manufacturer. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 230523 | Low |  | Product Data | GENERAL-DUTY VALVES FOR HVAC PIPING | A. Product Data: For each type of valve indicated. Body material, valve design, pressure and temperature classification, end connection details, seating materials, trim material and arrangement, dimensions and required clearances, and installation instructions. Include list indicating valve and its application. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 230529 | Low |  | Product Data | HANGERS AND SUPPORTS FOR HVAC PIPING AND EQUIP | A. Product Data: For each type of product indicated. A. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/20/2020 | 12/19/2019 | 12/30/2019 | 01/02/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
3 |  | 0 | 230529 | Low |  | Product Data | HANGERS AND SUPPORTS FOR HVAC PIPING AND EQUIP | Add Additional Anchors Dewalt Wood Anchors Dewalt Concrete Form Anchors A. Product Data: For each type of product indicated. A. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 03/03/2020 | 02/26/2020 | 03/09/2020 | 02/24/2020 | 02/24/2020 | 02/25/2020 | 03/14/2020 |  | 03/26/2020 | 02/24/2020
1 |  | 0 | 230533 | Low |  | Product Data | IDENTIFICATION FOR HVAC PIPING AND EQUIPMENT | A. Product Data: For each type of product indicated. B. Equipment Label Schedule: Include a listing of all equipment to be labeled with the proposed content for each label. C. Valve numbering scheme. D. Valve Schedules: For each piping system to include in maintenance manuals. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/28/2020 | 12/19/2019 | 01/10/2020 | 01/13/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
2 |  | 0 | 230533 | Medium |  | Submittal | Equipment Tagging (Updated 2021-05-24) |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  |  |  | 06/07/2021 |  | 05/24/2021 | 05/24/2021 | 06/03/2021 |  | 06/22/2021 | 05/24/2021
1 |  | 0 | 230548 | High |  | Product Data | Vibration and Seismic Controls For HVAC | A. Product Data: For the following: 1. Submittals shall include catalog cut sheets and installation instructions for each type of anchor and seismic restraint used on equipment or components being isolated and/or restrained. 2. Submittals for mountings and hangers incorporating springs shall include spring diameter and free height, rated load, rated deflection, and overload capacity for each vibration isolation device. 3. Illustrate and indicate style, material, strength, fastening provision, and finish for each type and size of seismic-restraint component used. a. Tabulate types and sizes of seismic restraints, complete with report numbers and rated strength in tension and shear as evaluated by an evaluation service member of ICC-ES. b. Annotate to indicate application of each product submitted and compliance with requirements. 4. Interlocking Snubbers: Include ratings for horizontal, vertical, and combined loads. B. Qualification Data: For professional engineer and testing agency. C. Welding certificates. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 07/23/2020 | 12/19/2019 | 06/08/2020 | 07/09/2020 | 08/13/2020 |  | 08/14/2020 | 12/18/2019
1 |  | 0 | 230550 | Low |  | Product Data | OPERATION AND MAINTENANCE OF HVAC SYSTEMS | A. Submit product data in accordance with Division 1 and Section 230100. Submit the following: 1. Sample of O and M manual outline. |  |  | Closed | On Hold |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
2 |  | 0 | 230594 | Low |  | Submittal Register | GENERAL TESTING, ADJUSTING, BALANCING AND COM | B. Strategies and Procedures Plan: Within 120 days from the Contractor's Notice to Proceed, submit 2 copies of the testing, adjusting, and balancing strategies and step-by-step procedures as specified in Part 3 "Preparation" Article below. Include a complete set of report forms intended for use on this Project. |  |  | Closed | Approved |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 11/15/2019 | 10/23/2019 | 10/25/2019 | 10/28/2019 | 11/18/2019 |  | 11/19/2019 | 09/10/2019
1 |  | 0 | 230713 | Low |  | Product Data | DUCT INSULATION | A. Product Data: For each type of product indicated. Include thermal conductivity, water-vapor permeance thickness, and jackets (both factory- and field-applied if any). |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/02/2019 | 10/23/2019 | 11/13/2019 | 12/03/2019 | 12/03/2019 | 12/02/2019 | 12/03/2019 | 09/10/2019 |  | Mechanical Engineers
2 |  | 0 | 230713 | Low |  | Submittal Register | DUCT INSULATION | B. LEED Submittals: 1. Product Data for Credit IEQ 4.1: For adhesives and sealants, documentation including printed statement of VOC content. 2. Laboratory Test Reports for Credit IEQ 4: For adhesives and sealants, documentation indicating that products comply with the testing and product requirements of the California Department of Health Services' "Standard Practice for the Testing of Volatile Organic Emissions from Various Sources Using Small-Scale Environmental Chambers." |  |  | Closed | Rejected |  |  |  | Jeff Adams | CRSA ARCHITECTURE | Westland PE’s |  | CRSA ARCHITECTURE | [6 empty] | 09/19/2019 | 09/19/2019 | 09/19/2019 | 10/23/2019 |  | 10/24/2019 | 09/10/2019 |  | Mechanical Engineers
1 |  | 0 | 230716 | Low |  | Product Data | HVAC EQUIPMENT INSULATION | A. Product Data: For each type of product indicated. Include thermal conductivity, water-vapor permeance, thickness, and jackets (both factory- and field-applied if any). |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/02/2019 | 10/23/2019 | 11/13/2019 | 12/03/2019 | 12/03/2019 | 11/27/2019 | 12/03/2019 | 09/10/2019 |  | Mechanical Engineers
1 |  | 0 | 230719 | Low |  | Product Data | HVAC PIPING INSULATION | A. Product Data: For each type of product indicated. Include thermal conductivity, water-vapor permeance thickness, and jackets (both factory and field applied if any). |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/02/2019 | 10/23/2019 | 11/13/2019 | 12/03/2019 | 12/03/2019 | 11/27/2019 | 12/03/2019 | 09/10/2019 |  | Mechanical Engineers
1 |  | 0 | 231123 | Low |  | Product Data | FACILITY NATURAL-GAS PIPING | A. Product Data: For each type of the following: 1. Piping specialties. 2. Valves. Include pressure rating, capacity, settings, and electrical connection data of selected models. 3. Pressure regulators. Indicate pressure ratings and capacities. 4. Dielectric fittings. 5. Dielectric fittings. 6. Mechanical sleeve seals. 7. Escutcheons. F. Qualification Data: For qualified professional engineer. G. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/08/2020 | 01/09/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 232113 | Low |  | Product Data | HYDRONIC PIPING | A. Product Data: For each type of the following: 1. Steel pipe and fittings. 2. Copper pipe, tubing and fittings. 3. Dielectric fittings.B. Qualification Data: For Installer. C. Welding certificatesD. Grooved joint couplings and fittings shall be shown on drawings and product submittals, and be specifically identified with the applicable Victaulic style number. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/07/2020 | 01/09/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 232116 | Low |  | Product Data | HYDRONIC PIPING SPECIALTIES | A. Product Data: For each type of the following: 1. Valves: Include flow and pressure drop curves based on manufacturer's testing for calibrated-orifice balancing valves and automatic flow-control valves. 2. Air-control devices. 3. Hydronic specialties. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/07/2020 | 01/09/2020 | 01/28/2020 |  | 01/28/2020 | 12/18/2019
1 |  | 0 | 232123 | Medium |  | Product Data | HYDRONIC PUMPS |  |  |  | Closed | Revise and Resubmit |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 12/04/2019 | 11/28/2019 | 12/10/2019 | 11/26/2019 | 11/26/2019 | 11/26/2019 | 01/08/2020 |  | 01/09/2020 | 11/26/2019
4 |  | 0 | 232123 | Medium |  | Product Data | HYDRONIC PUMPS | Revise/Resubmit items from Submittal 1: BCP-1 BCP-2 BCP-3 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  | 0 |  | 01/16/2020 | 02/26/2020 | 03/09/2020 | 01/09/2020 | 02/24/2020 | 02/25/2020 | 03/17/2020 |  | 03/26/2020 | 01/09/2020
5 |  | 0 | 232123 | Medium |  | Product Data | HYDRONIC PUMPS | Resubmittal for discontinued item. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  | 05/15/2020 | 05/09/2020 | 08/02/2020 | 11/26/2019 | 05/07/2020 | 07/23/2020 | 07/23/2020 |  | 07/23/2020 | 05/07/2020 |  | Mechanical Engineers
6 |  | 0 | 232123 | High |  | Product Data | HYDRONIC PUMPS - CCD 28 R3 | Changes associated with CCD 28 R3 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | David Adams | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 11/18/2020 | 11/20/2020 | 11/20/2020 | 11/10/2020 | 05/07/2020 | 11/10/2020 | 12/09/2020 |  | 12/10/2020 | 11/10/2020 | Mechanical Engineers
2 |  | 1 | 232300 | Low |  | Submittal | REFRIGERANT PIPING | CCD 66 LANDSCAPING SHED B. Quality Assurance / Control: Technician certificate for use of CFC and HCFC refrigerants. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 12/02/2020 | 11/18/2020 | 11/18/2020 | 11/18/2020 | 11/18/2020 |  | 11/22/2020 | 11/18/2020
4 |  | 0 | 232513 | Low |  | Submittal Register | WATER TREATMENT FOR CLOSED-LOOP HYDRONIC SYSTEM | B. Water Analysis Provider Qualifications: Verification of experience and capability of HVAC water-treatment service provider. |  |  | Closed | Approved |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 11/15/2019 | 10/23/2019 | 10/25/2019 | 10/28/2019 | 11/18/2019 |  | 11/19/2019 | 09/10/2019
5 |  | 0 | 232513 | Low |  | Product Data | WATER TREATMENT FOR CLOSED-LOOP HYDRONIC SYSTEMS | A. Product Data: Include rated capacities, operating characteristics, and furnished specialties and accessories for the following products: 1. Bypass feeders. 2. Water meters. 3. Chemical solution tanks. 4. Chemical material safety data sheets. A. Seismic Qualification Certificates: For components, from manufacturer. 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. 2. Dimensioned Outline Drawings of Equipment Unit: Identify center of gravity and locate and describe mounting and anchorage provisions. 3. Detailed description of equipment anchorage devices on which the certification is based and their installation requirements. B. Water Analysis Provider Qualifications: (Submitted Previously)C. Field quality-control reports. D. Other Informational Submittals: 1. Water-Treatment Program: Written sequence of operation on an annual basis for the application equipment required to achieve water quality defined in "Performance Requirements" Article. 2. Water Analysis: Illustrate water quality available at Project site. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
3 |  | 0 | 232516 | Medium |  | Submittal Register | WATER TREATMENT FOR OPEN-LOOP HYDRONIC SYSTEMS | C. Other Informational Submittals: 1. Water-Treatment Program: Written sequence of operation on an annual basis for the application equipment required to achieve water quality defined in "Performance Requirements" Article. 2. Water Analysis: Illustrate water quality available at Project site. 3. Passivation Confirmation Report: Verify passivation of galvanized-steel surfaces, and confirm this observation in a letter to Architect. |  |  | Closed | Approved |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  | 0 |  | 12/03/2019 | 10/27/2019 | 11/07/2019 | 10/23/2019 | 10/25/2019 | 10/28/2019 | 11/08/2019 |  | 11/10/2019 | 09/11/2019
4 |  | 0 | 232516 | Low |  | Product Data | WATER TREATMENT FOR OPEN-LOOP HYDRONIC SYSTEMS | A. Product Data: Include rated capacities, operating characteristics, and furnished specialties and accessories for the following products: 1. Bypass feeders. 2. Water meters. 3. Chemical solution tanks. 4. Injection pumps. 5. Chemical test equipment. 6. Chemical material safety data sheets. A. Water Analysis Provider Qualifications: Verification of experience and capability of HVAC water-treatment service provider. B. Field quality-control reports. C. Other Informational Submittals: (Submitted Previously) |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
1 |  | 1 | 232533 | High |  | Product Data | HVAC MAKEUP-WATER FILTRATION (Rev1 - CCD_120) | A. Product Data: Include rated capacities, operating characteristics, and furnished specialties and accessories for the following products: 1. Centrifugal separators. A. Seismic Qualification Certificates: For water filtration units and components, from manufacturer. 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. 2. Dimensioned Outline Drawings of Equipment Unit: Identify center of gravity and locate and describe mounting and anchorage provisions. 3. Detailed description of equipment anchorage devices on which the certification is based and their installation requirements. B. Water Analysis Provider Qualifications: Verification of experience and capability of HVAC water-treatment service provider. C. Field quality-control reports. D. Other Informational Submittals: 1. Water Analysis: Illustrate water quality available at Project site. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 04/09/2021 |  | 03/26/2021 | 03/26/2021 | 04/05/2021 |  | 04/09/2021 | 03/26/2021
1 |  | 0 | 232600 | Low |  | Product Data | CONDENSATE DRAIN PIPING |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 01/16/2020 | 01/10/2020 | 01/19/2020 | 01/08/2020 | 01/08/2020 | 01/09/2020 | 01/20/2020 |  | 01/23/2020 | 01/08/2020
1 |  | 0 | 233001 | Low | Samples | Submittal | COMMON DUCT REQUIREMENTS | A. Samples: Sealer and gauze proposed for sealing ductwork. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
2 |  | 0 | 233001 | Low |  | Product Data | COMMON DUCT REQUIREMENTS | B. Quality Assurance / Control: 1. Manufacturer’s installation manuals providing detailed instructions on assembly, joint sealing, and system pressure testing for leaks. 2. Specification data on sealer and gauze proposed for sealing ductwork. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/02/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 01/02/2020 |  | 01/09/2020 | 12/18/2019
1 |  | 0 | 233113 | High |  | Product Data | METAL DUCTS | A. Product Data: For each type of the following products: 1. Liners and adhesives. 2. Sealants and gaskets. 3. Seismic-restraint devices. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/17/2020 | 12/19/2019 | 01/07/2020 | 01/09/2020 | 01/21/2020 |  | 01/23/2020 | 12/18/2019
4 |  | 0 | 233113 | High |  | Shop Drawing | METAL DUCTS | Annex L1 HVAC Concrete Penetrations |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Structural Engineers |  |  |  | 02/29/2020 | 07/02/2020 | 07/10/2020 | 02/21/2020 | 06/30/2020 | 06/30/2020 | 06/30/2020 |  | 07/16/2020 | 02/21/2020
2 |  | 2 | 233113 | High |  | Shop Drawing | METAL DUCTS (Level 5) | Historic Level 5 Metal Duct Shop Drawings *Revised per added VAV's in CCD38R1 |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 07/15/2020 | 06/30/2020 | 06/30/2020 | 06/30/2020 | 07/02/2020 |  | 07/02/2020 | 06/30/2020
6 |  | 0 | 233113 | High | DWGS - Shop Drawings | Submittal | METAL DUCTS (Annex L0 Shops) | Annex L0 HVAC Coordination Drawings |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 09/08/2020 | 09/10/2020 | 09/10/2020 | 08/31/2020 | 08/31/2020 | 08/31/2020 | 09/16/2020 | 12/14/2020 | 12/14/2020 | 08/31/2020
7 |  | 0 | 233113 | High | DWGS - Shop Drawings | Submittal | METAL DUCTS (HVAC RCP Revised CCD_73) | Annex Level 0 HVAC RCP revised per CCD_73. This was originally submitted as part of submittal 6 but was revised before review was complete. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 09/18/2020 | 09/20/2020 | 09/21/2020 | 09/11/2020 | 09/11/2020 | 09/11/2020 | 09/16/2020 |  | 09/18/2020 | 09/11/2020
8 |  | 0 | 233113 | High | DWGS - Shop Drawings | Submittal | METAL DUCTS (Annex L1 Shops) | Annex L1 HVAC Coordination Drawings |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 09/22/2020 | 09/24/2020 | 09/24/2020 | 09/14/2020 | 09/14/2020 | 09/14/2020 | 09/18/2020 |  | 09/18/2020 | 09/14/2020
9 |  | 0 | 233113 | High |  | Submittal | METAL DUCTS - Historic West Stone Wall Penetration Drawing |  |  |  | Closed | Make Corrections Noted |  |  |  | Justun Bylund | US Mechanical LLC | David Adams | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 10/16/2020 | 10/18/2020 | 10/18/2020 | 10/08/2020 | 10/08/2020 | 10/08/2020 | 10/13/2020 |  | 10/28/2020 | 10/08/2020 |  | Structural Engineers
11 |  | 0 | 233113 | High | DWGS - Shop Drawings | Submittal | METAL DUCTS (Annex L0 Shops) - Updated RCP | Annex L0 HVAC Coordination Drawings Revised RCP Plan |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 12/22/2020 | 12/24/2020 | 12/24/2020 | 08/31/2020 | 12/14/2020 | 12/14/2020 | 12/16/2020 | 12/14/2020 | 12/18/2020 | 12/14/2020 |  | Mechanical Engineers
12 |  | 0 | 233113 | High | DWGS - Shop Drawings | Submittal | Coordinated Ductwork - Historic Lv 0 Shop Drawings |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 02/02/2021 | 02/04/2021 | 02/04/2021 | 08/31/2020 | 01/25/2021 | 01/25/2021 | 01/26/2021 | 12/14/2020 | 02/09/2021 | 01/25/2021
13 |  | 0 | 233113 | Medium | DWGS - Shop Drawings | Submittal | Coordinated Ductwork - Historic Lv 0.5 Shop Drawings |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 02/02/2021 | 02/04/2021 | 02/04/2021 | 08/31/2020 | 01/25/2021 | 01/25/2021 | 02/08/2021 | 12/14/2020 | 02/09/2021 | 01/25/2021
14 |  | 0 | 233113 | Low | DWGS - Shop Drawings | Submittal | Coordinated Ductwork - Historic Lv 2 Shop Drawings |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 02/02/2021 | 02/04/2021 | 02/04/2021 | 08/31/2020 | 01/25/2021 | 01/25/2021 | 02/08/2021 | 12/14/2020 | 02/09/2021 | 01/25/2021
15 |  | 0 | 233113 | Low | DWGS - Shop Drawings | Submittal | Ductwork Penetrations - Historic Lv 0 Shop Drawings |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 02/02/2021 | 02/04/2021 | 02/04/2021 | 08/31/2020 | 01/25/2021 | 01/25/2021 | 01/26/2021 | 12/14/2020 | 02/09/2021 | 01/25/2021
10 |  | 1 | 233113 | High |  | Shop Drawing | METAL DUCTS (Level 3) | Historic Level 3 Metal Duct Shop Drawings |  |  | Assigned to Sub |  | John DeRosa | US Mechanical LLC | 01/29/2021 | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 01/29/2021 |  | 11/24/2020 | 01/26/2021 | [5 empty] | 01/26/2021
16 |  | 0 | 233113 | High |  | Submittal | COORDINATED DUCTWORK - West Tower complete |  |  |  | Closed | Make Corrections Noted |  |  |  | Justun Bylund | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 04/22/2021 | 04/24/2021 | 04/24/2021 |  | 04/14/2021 | 04/14/2021 | 05/07/2021 |  | 05/07/2021 | 04/14/2021
1 |  | 0 | 233300 | High |  | Product Data | AIR DUCT ACCESSORIES | A. Product Data: For each type of product. 1. For duct silencers, include pressure drop and dynamic insertion loss data. Include breakout noise calculations for high transmission loss casings. B. Source quality-control reports. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 02/07/2020 | 12/19/2019 | 01/21/2020 | 01/24/2020 | 01/27/2020 |  | 01/28/2020 | 12/18/2019
2 |  | 0 | 233300 | Low |  | Submittal | AIR DUCT ACCESSORIES | Fire smoke dampers per RFI_327 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  |  | 12/19/2019 | 04/21/2020 | 08/12/2020 | 08/28/2020 |  | 08/28/2020 | 12/18/2019
1 |  | 1 | 233413 | High |  | Product Data | AXIAL HVAC FANS | A. Product Data: For each type of product. 1. Include rated capacities, furnished specialties, and accessories for each fan. 2. Certified fan performance curves with system operating conditions indicated. 3. Certified fan sound-power ratings. 4. Motor ratings and electrical characteristics, plus motor and electrical accessories. 5. Material thickness and finishes, including color charts. 6. Dampers, including housings, linkages, and operators. 7. Fan speed controllers. B. Field quality-control reports. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/17/2020 |  | 02/14/2020 | 01/13/2020 | 01/22/2020 | 01/30/2020 | 02/18/2020 |  | 02/19/2020 | 01/13/2020
1 |  | 0 | 233423 | High |  | Product Data | POWER VENTILATORS | A. Product Data: For each type of product indicated. Include rated capacities, shipping weights, operating weights, operating characteristics, and furnished specialties and accessories. Also include the following: 1. Certified fan performance curves with system operating conditions indicated. 2. Certified fan sound-power ratings. 3. Motor ratings and electrical characteristics, plus motor and electrical accessories. 4. Material thickness and finishes, including color charts. 5. Dampers, including housings, linkages, and operators. 6. Roof curbs. 7. Fan speed controllers. B. Field quality-control Reports |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/10/2020 | 12/19/2019 | 01/02/2020 | 01/02/2020 | 01/14/2020 |  | 01/14/2020 | 12/18/2019
4 |  | 0 | 233423 | High |  | Product Data | POWER VENTILATORS (EF-1-02 & EF-1-06 Resubmittal) | EF-1-02 & EF-1-06 Resubmittal from Submittal 1. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/21/2020 | 01/16/2020 | 02/14/2020 | 01/14/2020 | 01/14/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 01/14/2020
5 |  | 0 | 233423 | High |  | Product Data | POWER VENTILATORS | Updated submittal items. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 03/03/2020 | 03/05/2020 | 03/09/2020 | 01/14/2020 | 02/24/2020 | 02/25/2020 | 03/17/2020 |  | 03/26/2020 | 02/24/2020
1 |  | 0 | 233519 | Low |  | Product Data | DRYER EXHAUST DUCTS |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 02/14/2020 | 12/19/2019 | 01/15/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 12/18/2019
2 |  | 0 | 233519 | Low |  | Product Data | DRYER EXHAUST DUCTS | Updates Per RFI 141 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 03/03/2020 | 03/05/2020 | 03/06/2020 | 12/19/2019 | 02/24/2020 | 02/25/2020 | 03/14/2020 |  | 03/26/2020 | 02/24/2020
3 |  | 0 | 233519 | Low |  | Product Data | DRYER EXHAUST DUCTS - RFI_615 | 233519_DryerVentDuct_AddSealant_FireWrap_St.GeorgeTempleRenovation_11202020 2.2.E – Adhesive Coating for Dryer Vent (3M 740UV) 2.2.E – 3" Fiberglass Strips for Dryer Vent (GAF Model FGW3) 2.2.F – 2 Hour 3M Fire Barrier Duct Wrap 615 Referencing RFI#615. (Submitting 3M 740UV per Ben at VBFA's recommendation. Thank you. USM.) |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 12/01/2020 | 12/03/2020 | 12/03/2020 | 11/23/2020 | 11/23/2020 | 11/23/2020 | 12/01/2020 |  | 12/03/2020 | 11/23/2020
4 |  | 0 | 233519 | Low |  | Product Data | DRYER EXHAUST DUCTS - CCD_28R4 |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 12/02/2020 | 12/04/2020 | 12/04/2020 | 11/24/2020 | 11/24/2020 | 11/24/2020 | 11/30/2020 |  | 12/03/2020 | 11/24/2020
1 |  | 0 | 233533 | Low |  | Product Data | LISTED KITCHEN VENTILATION SYSTEM EXHAUST DUCT | A. Product Data: For each type of product. 1. Include construction details, material descriptions, dimensions of individual components and profiles, and finishes for listed grease ductsA. Welding certificates. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 03/09/2020 | 12/19/2019 | 02/20/2020 | 02/25/2020 | 03/17/2020 |  | 03/26/2020 | 12/18/2019
1 |  | 0 | 233600 | High |  | Product Data | AIR TERMINAL UNITS | A. Product Data: For each type of the following products, including rated capacities, furnished specialties, sound-power ratings, and accessories. 1. Air terminal units. 2. Liners and adhesives. 3. Sealants and gaskets. 4. Seismic-restraint devices. E. Airborne noise data for terminal units serving Patient Rooms: 1. Declared discharge and radiated sound power levels by octave band covering a minimum range of 63 to 4000 hertz 2. Method of determining declared sound power levels. B. Field quality-control reports. A. Seismic Performance: Air terminal units shall withstand the effects of earthquake motions determined according to SEI/ASCE 7. 1. The term "withstand" means "the unit will remain in place without separation of any parts from the device when subjected to the seismic forces specified and the unit will be fully operational after the seismic event." |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/20/2020 | 10/23/2019 | 01/13/2020 | 01/13/2020 | 01/22/2020 |  | 01/23/2020 | 09/10/2019
2 |  | 0 | 233600 | Low |  | Shop Drawing | AIR TERMINAL UNITS | C. Shop Drawings: For air terminal units. Include plans, elevations, sections, details, and attachments to other work. 1. Detail equipment assemblies and indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection. 2. Wiring Diagrams: a. For power, signal, and control wiring. b. Differentiate between manufacturer-installed and field-installed wiring. 3. Hangers and supports, including methods for duct and building attachment, seismic restraints, and vibration isolation. D. Delegated-Design Submittal: 1. Materials, fabrication, assembly, and spacing of hangers and supports. 2. Design Calculations: Calculations, including analysis data signed and sealed by the qualified professional engineer responsible for their preparation for selecting hangers and supports. A. Coordination Drawings: Reflected ceiling plans, drawn to scale, on which the following items are shown and coordinated with each other, using input from Installers of the items involved: 1. Ceiling suspension assembly members. 2. Size and location of initial access modules for acoustic tile. 3. Ceiling-mounted items including lighting fixtures, diffusers, grilles, speakers, sprinklers, access panels, and special moldings. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 | 06/03/2020 |  |  |  | 06/04/2020 | 12/18/2019
4 |  | 0 | 233600 | High |  | Submittal | AIR TERMINAL UNITS | CCD 38R1 A. Product Data: For each type of the following products, including rated capacities, furnished specialties, sound-power ratings, and accessories. 1. Air terminal units. 2. Liners and adhesives. 3. Sealants and gaskets. 4. Seismic-restraint devices. E. Airborne noise data for terminal units serving Patient Rooms: 1. Declared discharge and radiated sound power levels by octave band covering a minimum range of 63 to 4000 hertz 2. Method of determining declared sound power levels. B. Field quality-control reports. A. Seismic Performance: Air terminal units shall withstand the effects of earthquake motions determined according to SEI/ASCE 7. 1. The term "withstand" means "the unit will remain in place without separation of any parts from the device when subjected to the seismic forces specified and the unit will be fully operational after the seismic event." |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 06/12/2020 | 06/06/2020 | 06/14/2020 | 10/23/2019 | 06/04/2020 | 06/04/2020 | 06/05/2020 |  | 06/09/2020 | 06/04/2020
5 |  | 0 | 233600 | High |  | Submittal | AIR TERMINAL UNITS (CCD_54.4) | VAV Changes per CCD_54.4 A. Product Data: For each type of the following products, including rated capacities, furnished specialties, sound-power ratings, and accessories. 1. Air terminal units. 2. Liners and adhesives. 3. Sealants and gaskets. 4. Seismic-restraint devices. E. Airborne noise data for terminal units serving Patient Rooms: 1. Declared discharge and radiated sound power levels by octave band covering a minimum range of 63 to 4000 hertz 2. Method of determining declared sound power levels. B. Field quality-control reports. A. Seismic Performance: Air terminal units shall withstand the effects of earthquake motions determined according to SEI/ASCE 7. 1. The term "withstand" means "the unit will remain in place without separation of any parts from the device when subjected to the seismic forces specified and the unit will be fully operational after the seismic event." |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 08/12/2020 | 08/06/2020 | 08/14/2020 | 08/04/2020 | 08/04/2020 | 08/04/2020 | 08/17/2020 |  | 08/18/2020 | 08/04/2020 | CRSA ARCHITECTURE
1 |  | 0 | 233713 | Low |  | Product Data | DIFFUSERS, REGISTERS, AND GRILLES | A. Product Data: For each type of product indicated, include the following: 1. Data Sheet: Indicate materials of construction, finish, and mounting details; and performance data including throw and drop, static-pressure drop, and noise ratings. 2. Diffuser, Register, and Grille Schedule: Indicate drawing designation, room location, quantity, model number, size, and accessories furnished. |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/17/2019 | 10/23/2019 | 11/26/2019 | 12/03/2019 | 12/31/2019 |  | 01/02/2020 | 09/10/2019
4 |  | 0 | 233713 | Low |  | Product Data | DIFFUSERS, REGISTERS, AND GRILLES | Update to Submittal 1 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 03/03/2020 | 03/05/2020 | 03/06/2020 | 10/23/2019 | 02/24/2020 | 02/25/2020 | 03/18/2020 |  | 03/26/2020 | 02/24/2020
5 |  | 0 | 233713 | High |  | Product Data | DIFFUSERS, REGISTERS, AND GRILLES | Add - Plenum Submittal for Tag CD-9 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/24/2020 | 03/18/2020 | 03/26/2020 | 10/23/2019 | 03/16/2020 | 03/16/2020 | 03/27/2020 |  | 03/30/2020 | 03/16/2020 |  | Ben Davis, Brian Oswald, Levis Wiggins
3 |  | 2 | 233713 | High |  | Product Data | DRG - Color Samples RFI_1022 | A. Product Data: For each type of product indicated, include the following: 1. Data Sheet: Indicate materials of construction, finish, and mounting details; and performance data including throw and drop, static-pressure drop, and noise ratings. 2. Diffuser, Register, and Grille Schedule: Indicate drawing designation, room location, quantity, model number, size, and accessories furnished. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 11/25/2020 | 04/01/2021 | 04/11/2021 | 11/22/2020 | 04/01/2021 | 04/01/2021 | 04/16/2021 |  | 04/22/2021 | 11/22/2020 |  | Interior Designer
6 |  | 0 | 233713 | Low | Samples | Product Data | DRG (ARCHITECTURAL GRILLES) |  |  |  | Draft |  |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/09/2021 | 04/11/2021 | 04/21/2021 | 11/22/2020 | [5 empty] | 04/01/2021
7 |  | 0 | 233713 | Medium |  | Submittal | DIFFUSERS, REGISTERS, AND GRILLES - CCD_138 |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 04/15/2021 | 04/17/2021 | 04/17/2021 | 04/07/2021 | 04/07/2021 | 04/07/2021 | 04/29/2021 |  | 04/29/2021 | 04/07/2021
8 |  | 0 | 233713 | High |  | Submittal | Kees Grill Color Selection |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 06/22/2021 | 06/24/2021 | 06/15/2021 |  | 06/14/2021 | 06/14/2021 | 06/17/2021 |  | 06/22/2021 | 06/14/2021 | Ryan Thomas, Scott Gilberg, Brian Oswald, Eric Jamison
9 |  | 0 | 233713 | Medium |  | Submittal | Architectural GRD Updated CCD138 |  |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  | 0 |  | 06/24/2021 | 06/26/2021 | 07/06/2021 |  | 06/16/2021 | 06/16/2021 | 07/06/2021 |  | 07/08/2021 | 06/16/2021
10 |  | 0 | 233713 | Medium |  | Submittal | Titus Grill Color Selection |  |  |  | Closed | Approved As Noted |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 07/02/2021 | 07/04/2021 | 07/09/2021 |  | 06/24/2021 | 06/24/2021 | 07/13/2021 |  | 07/14/2021 | 06/24/2021
11 |  | 0 | 233713 | High |  | Submittal | Mech Grill Color Schedule |  |  |  | Design Review |  | Interior Designer |  | 07/20/2021 | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  |  |  | 07/20/2021 |  | 07/06/2021 | 07/06/2021 |  |  |  | 07/06/2021
3 |  | 0 | 233714 | High | Samples | Submittal | FIXED LOUVERS | C. Samples: For each type of metal finish required. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 04/17/2020 | 12/19/2019 | 03/26/2020 | 04/28/2020 | 04/29/2020 |  | 04/30/2020 | 12/18/2019 |  | Mechanical Engineers, Interior Designer
1 |  | 1 | 233714 | Low |  | Product Data | FIXED LOUVERS | A. Product Data: For each type of product. 1. For louvers specified to bear AMCA seal, include printed catalog pages showing specified models with appropriate AMCA Certified Ratings Seals. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 01/10/2020 |  | 03/09/2020 | 01/02/2020 | 02/03/2020 | 02/25/2020 | 03/14/2020 |  | 03/26/2020 | 01/02/2020
1 |  | 0 | 233723 | Low |  | Product Data | HVAC GRAVITY VENTILATORS | A. Product Data: 1. For each type of product indicated.[ For louvered-penthouse ventilators specified to bear AMCA seal, include printed catalog pages showing specified models with appropriate AMCA Certified Ratings Seals. 2. Drawings from each manufacturer detailing equipment assemblies. Indications of dimensions, loadings, required clearances, method of field assembly, components and location and size of each field connection. 3. Rated capacities of each unit, weights (shipping, installed and operating), furnished specialties, accessories and the following: a. Material gages and finishes, including color charts. b. Dampers, including housings, linkages and operators. 4. LEED Submittals: a. Prerequisite IEQ 1: Documentation indicating that units comply with ASHRAE 62.1, Section 5 - "Systems and Equipment." |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/17/2019 | 10/23/2019 | 11/26/2019 | 12/03/2019 | 12/31/2019 |  | 01/02/2020 | 09/10/2019
1 |  | 0 | 235215 | Low |  | Product Data | FLUES | A. Product Data: For the following: 1. Type B and BW vents. 2. Type L vents. 3. Special gas vents. 4. Grease ducts. 5. Guy wires and connectors. C. Welding certificates. D. Manufacturer Seismic Qualification Certification: Submit certification that factory-fabricated breeching, chimneys, and stacks; accessories; and components will withstand seismic forces defined in Division 23 Section "Vibration and Isolation and Seismic Restraints." Include the following: 1. Basis for Certification: Indicate whether withstand certification is based on actual test of assembled components or on calculation. a. The term "withstand" means "the unit will remain in place without separation of any parts from the device when subjected to the seismic forces specified." b. The term "withstand" means "the unit will remain in place without separation of any parts from the device when subjected to the seismic forces specified and the unit will be fully operational after the seismic event." 2. Dimensioned Outline Drawings of Breeching, Chimneys, and Stacks: Identify center of gravity and locate and describe mounting and anchorage provisions. 3. Detailed description of anchorage devices on which the certification is based and their installation requirements |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 01/24/2020 | 12/19/2019 | 01/03/2020 | 01/09/2020 | 02/14/2020 |  | 02/19/2020 | 12/18/2019
1 |  | 0 | 235216 | Low |  | Product Data | CONDENSING BOILERS | A. Product Data: Include performance data, operating characteristics, furnished specialties and accessories. 1. Prior to flue vent installation, engineered calculations and drawings must be submitted to Architect/Engineer to thoroughly demonstrate that size and config |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/21/2019 | 11/22/2019 | 12/05/2019 |  | 12/05/2019 | 09/10/2019
1 |  | 0 | 235700 | Low |  | Product Data | HEAT EXCHANGERS FOR HVAC | A. Product Data: For each type of product. 1. Include rated capacities, operating characteristics, and furnished specialties and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/17/2019 | 10/23/2019 | 11/26/2019 | 12/03/2019 | 01/08/2020 |  | 01/08/2020 | 09/10/2019
1 |  | 0 | 236423 | Low |  | Product Data | AIR COOLED WATER CHILLERS | A. Product Data: Include refrigerant, rated capacities, operating characteristics, furnished specialties, and accessories. 1. Performance at ARI standard conditions and at conditions indicated. 2. Performance at ARI standard unloading conditions. 3. Minimum evaporator flow rate. 4. Refrigerant capacity of water chiller. 5. Oil capacity of water chiller. 6. Fluid capacity of evaporator. 7. Fluid capacity of condenser. 8. Characteristics of safety relief valves. 9. Minimum entering condenser-water temperature. 10. Minimum entering condenser-air temperature |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/21/2019 | 11/22/2019 | 12/06/2019 |  | 12/06/2019 | 09/10/2019
1 |  | 1 | 236500 | Low |  | Shop Drawing | COOLING TOWERS | A. Shop Drawings: Complete set of manufacturer's prints of cooling tower assemblies, control panels, sections and elevations, and unit isolation. Include the following: 1. Assembled unit dimensions. 2. Shipping and Operations Weights. 3. Required clearances for maintenance and operation. 4. Sizes and locations of piping and wiring connections. 5. Wiring Diagrams: For power, signal, and control wiring. 6. Sound Data 7. Structural Support |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 01/24/2020 | 12/21/2019 | 01/06/2020 | 01/09/2020 | 01/23/2020 |  | 01/24/2020 | 12/21/2019
1 |  | 0 | 237313 | High |  | Product Data | CUSTOM FANWALL AIR-HANDLING UNITS | B. Product Data for each central-station air-handling unit specified, including the following: 1. Certified fan-performance curves with system operating conditions indicated. 2. Certified fan-sound power ratings. 3. Certified coil-performance ratings with system operating conditions indicated. 4. Motor ratings and electrical characteristics plus motor and fan accessories. 5. Material gages and finishes. 6. Filters with performance characteristics. 7. Dampers, including housings, linkages, and operators. 8. Humidifiers 9. Evaporative media. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/22/2019 | 11/22/2019 | 12/06/2019 |  | 12/06/2019 | 09/10/2019
4 |  | 0 | 237313 | Low |  | Product Data | CUSTOM FANWALL AIR-HANDLING UNITS (Air Filters) | B. Product Data for each central-station air-handling unit specified, including the following: 1. Certified fan-performance curves with system operating conditions indicated. 2. Certified fan-sound power ratings. 3. Certified coil-performance ratings with system operating conditions indicated. 4. Motor ratings and electrical characteristics plus motor and fan accessories. 5. Material gages and finishes. 6. Filters with performance characteristics. 7. Dampers, including housings, linkages, and operators. 8. Humidifiers 9. Evaporative media. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/24/2020 | 01/18/2020 | 02/14/2020 | 01/16/2020 | 01/16/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 01/16/2020
1 |  | 0 | 238219 | Low |  | Product Data | FAN-COIL UNITS | A. Product Data: Include specialties and accessories for each unit type and configuration |  |  | Closed | Make Corrections Noted |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 12/10/2019 | 10/23/2019 | 11/21/2019 | 11/22/2019 | 01/07/2020 |  | 01/08/2020 | 09/10/2019
2 |  | 0 | 238219 | Low |  | Submittal | FAN-COIL UNITS |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/03/2019 |  | 07/06/2020 | 12/19/2019 | 05/12/2020 | 06/22/2020 | 07/02/2020 |  | 07/09/2020 | 12/18/2019
3 |  | 0 | 238219 | Low | Samples | Submittal | FAN-COIL UNITS | D. Samples for Initial Selection: Manufacturer's color charts showing the full range of colors available for units with factory-applied color finishes. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 12/03/2019 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
4 |  | 0 | 238219 | Low |  | Report | FAN-COIL UNITS | E. Field Test Reports: Written reports of tests specified in Part 3 of this Section. |  |  | Closed | See Other |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s | [5 empty] | 05/02/2022 |  |  | 12/19/2019 |  |  |  |  | 11/23/2020 | 12/18/2019
6 |  | 0 | 238219 | Low |  | Product Data | FAN-COIL UNITS | Corrections to submittal 1 and condensate pumps for all fan-coil units. |  |  | Closed | Approved |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 03/03/2020 | 03/05/2020 | 03/09/2020 | 10/23/2019 | 02/24/2020 | 02/28/2020 | 03/30/2020 |  | 03/30/2020 | 02/24/2020 | Ben Davis, Brian Oswald, Spencer Landeen
1 |  | 1 | 238240 | Low |  | Product Data | PROPELLER UNIT HEATERS | A. Product Data: For each type of product. 1. Include rated capacities, operating characteristics, furnished specialties, and accessories. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 12/03/2019 |  | 03/16/2020 |  | 02/24/2020 | 03/02/2020 | 03/17/2020 |  | 03/26/2020 | 02/24/2020
1 |  | 1 | 238414 | High |  | Product Data | HUMIDIFIERS | A. Product Data: Include rated capacities, operating characteristics, furnished specialties, and accessories. |  |  | Closed |  |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/10/2020 |  | 03/13/2020 | 01/06/2020 | 02/24/2020 | 03/02/2020 | 03/18/2020 |  | 03/26/2020 | 01/06/2020 |  | Mechanical Engineers
3 |  | 0 | 255100 | Low |  | Product Data | BUILDING ENERGY MANAGEMENT AND TEMPERATURE |  |  |  | Closed | Revise and Resubmit |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 02/06/2020 | 01/31/2020 | 02/14/2020 | 01/29/2020 | 01/29/2020 | 01/30/2020 |  | 03/18/2020 | 03/26/2020 | 01/29/2020
4 |  | 0 | 255100 | Low |  | Product Data | BUILDING ENERGY MANAGEMENT AND TEMPERATURE |  |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/17/2020 | 03/11/2020 | 03/23/2020 | 03/09/2020 | 03/09/2020 | 03/09/2020 | 03/26/2020 |  | 03/30/2020 | 03/09/2020 |  | Scott Hardy, Jessica Blundell, Ben Davis, Brian Oswald
5 |  | 1 | 255100 | Low |  | Product Data | BUILDING ENERGY MANAGEMENT AND TEMPERATURE | PICV Valves Including CCD_38R1 |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Camron Walker | Westland Construction, Inc. | Mechanical Engineers |  |  |  | 04/14/2020 | 08/14/2020 | 08/22/2020 |  | 08/12/2020 | 08/12/2020 | 08/25/2020 |  | 08/26/2020 | 08/12/2020
1 |  | 0 | 260000 | High |  | Submittal | North Mechanical Electrical Penetrations | Structural Review for Concrete Penetrations per structural notes. |  |  | Closed | Make Corrections Noted |  |  |  | Trask Johnson | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Structural Engineers |  | 0 |  | 01/22/2021 | 01/24/2021 | 01/24/2021 |  | 01/14/2021 | 01/14/2021 | 01/15/2021 |  | 02/09/2021 | 01/14/2021 | CRSA ARCHITECTURE
1 |  | 0 | 260519 | Low |  | Product Data | Conductors and Cables | 1. (600V and Below) 1. Submit megohmmeter test data for circuits under 600 volts. Megger all circuits of 100 amp and greater rating. |  |  | Closed | Revise and Resubmit |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/02/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 01/02/2020 |  | 01/09/2020 | 12/18/2019
2 |  | 0 | 260519 | Low |  | Product Data | Conductors and Cables | Additional Required Items From Review of Submittal 1. THHN / THWN-2 Copper Submit all conductor types to be used. Are there Aluminum feeders to be installed also? THWN-2 is required in wet locations, exterior, below slab, etc. Meggar tests and submitted reports showing cables passing, will be required per 260519, 3.3,A. Conductors will need to be sized per voltage drop per 260519, 3.2. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/16/2020 | 01/12/2020 | 01/23/2020 | 01/09/2020 | 01/10/2020 | 01/13/2020 | 02/13/2020 |  | 02/19/2020 | 01/09/2020
1 |  | 0 | 260529 | Low |  | Product Data | Supporting Devices | 1. Submit manufacturer’s data for conduit and cabling supporting systems. The design team and owner can reject proposed supporting material at any time and request other options to be provided with no additional cost. |  |  | Closed | Revise and Resubmit |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/02/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/02/2020 |  | 01/09/2020 | 12/18/2019
1 |  | 0 | 260532 | Low |  | Product Data | Conduit Raceway | 1. Submit manufacturer’s data on MC-PCS Power & Control/Signal Cable. |  |  | Closed | Revise and Resubmit |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/07/2020 |  | 01/09/2020 | 12/18/2019
2 |  | 2 | 260532 | Low |  | Product Data | Conduit Raceway | Additional unspecified items requested in the review of Submittal 1: All conduit raceway products to be used in project |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/03/2020 | 03/27/2020 | 04/11/2020 | 03/02/2020 | 03/25/2020 | 04/01/2020 | 04/03/2020 |  | 04/06/2020 | 03/02/2020
1 |  | 1 | 260533 | Low |  | Product Data | Electrical Boxes and Fittings | 1. Submit manufacturer’s data including specifications, installation instruction and general recommendations for each type of floor box used on project. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 04/24/2020 |  | 06/30/2020 | 04/16/2020 | 04/29/2020 | 06/11/2020 | 07/08/2020 |  | 07/09/2020 | 04/16/2020 |  | Electrical Engineers
1 |  | 0 | 260536 | Low |  | Product Data | Raceway Systems | 1. Submit manufacturer's data including specifications, installation instructions and general recommendations, for each type of raceway as follows: Ladder Tray for MC Cabling Systems, Wire basket cable tray systems |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/07/2020 |  | 01/09/2020 | 12/18/2019
2 |  | 0 | 260536 | Low |  | Shop Drawing | Raceway Systems | 2. Submit dimensioned drawings of raceway systems showing layout of raceways and fittings, spatial relationships to associated equipment, and adjoining raceways, for each type of raceway as follows: Cable Tray Systems, Wire basket cable tray systems |  |  | Closed | Approved As Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | Electrical Engineers | [6 empty] | 12/19/2019 | 09/04/2020 | 09/08/2020 | 09/21/2020 |  | 10/28/2020 | 12/18/2019
2 |  | 0 | 260548 | Low |  | Product Data | Electrical Seismic Control | 1. A single submittal shall be provided for all seismic anchorage and restraints for all Division 26 equipment and systems provided as part of this project. Individual submittals for specific systems will not be accepted. |  |  | Closed | See Other |  |  |  | Trask Johnson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 01/29/2021 |  |  |  | 02/05/2021 | 12/18/2019
3 |  | 0 | 260548 | Low |  | Shop Drawing | Electrical Seismic Control | 2. Submit shop drawings, calculations, and printed data for the following items under provisions of the General Conditions of the Contract: 1. Complete engineering calculations and shop drawings for all seismic requirements for all equipment to be restrained as outlined in Section 26 0548 Specification, and as detailed on drawings. 2. The professional seal of the engineer who is responsible for the design of the Seismic Restraint System. 3. Details for all seismic bracing. 4. Details for steel frames, concrete inertia bases, and housekeeping pads. Include dimensions, embed depths, dowelling details, and concrete reinforcing requirements. 5. Clearly outlined procedures for installing and adjusting the isolators, seismic bracing anchors, snubbers, cables, and bolt connections. 6. Floor plan noting the locations, size, and type of anchorage and restraint to be used. 7. Include confirmation that all calculations are based on the design criteria listed in appropriate Section. 8. Certificate of Compliance. 9. Where equipment is exempt per this specification provide a written certificate of compliance for each of the systems noted with the professional seal of engineer who has reviewed the electrical system. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Electrical Engineers |  | CRSA ARCHITECTURE | [6 empty] | 12/19/2019 | 01/29/2021 | 02/10/2021 | 02/19/2021 |  | 02/22/2021 | 12/18/2019
1 |  | 0 | 260553 | Low |  | Product Data | Electrical Identification | 1. Submit manufacturer’s data on each type of electrical identification products 1. Submit one sample of each component of the electrical identification system as follows: Wire/cable tape marker, Tags, Engraved, plastic laminate labels, Arc-flash hazard labels |  |  | Closed | Pending Approval |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/08/2020 |  | 01/09/2020 | 12/18/2019
2 |  | 0 | 260553 | Low |  | Product Data | Electrical Identification | Additional items requested from Submittal 1 Review: Buried Electrical line warnings Arc Flash Labels |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/16/2020 | 01/19/2020 | 02/14/2020 | 01/08/2020 | 01/17/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 01/08/2020
2 |  | 0 | 260561 | Low |  | Product Data | POWER MODULE PANEL | Product Data: Provide manufacturer’s catalog information showing dimensions, configurations, and methods of mounting and installation.C. Submit listing of all types, sizes and quantity of fuses which will be installed including the location of each. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
1 |  | 1 | 260561 | Low |  | Shop Drawing | POWER MODULE PANEL | A. Submit shop drawings and product data under the provisions of the General Conditions.Equipment Room Layouts: Submit dimensioned drawings of all equipment rooms indicating spatial relationships to other proximate equipment. Insure that all code required clearances are maintained. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 01/25/2020 | 12/20/2019 | 01/03/2020 | 01/10/2020 | 02/13/2020 |  | 02/19/2020 | 12/20/2019
2 |  | 0 | 260562 | Low |  | Product Data | POWER MODULE SWITCHES | B. Product Data: Provide manufacturer’s catalog information showing dimensions, configurations, and methods of mounting and installation.C. Submit listing of all types, sizes and quantity of fuses which will be installed including the location of each. |  |  | Closed | Approved As Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
1 |  | 1 | 260562 | Low |  | Shop Drawing | POWER MODULE SWITCHES | A. Submit shop drawings and product data under the provisions of the General Conditions.E. Equipment Room Layouts: Submit dimensioned drawings of all equipment rooms indicating spacial relationships to other proximate equipment. Insure that all code required clearances are maintained. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 01/03/2020 |  |  | 12/20/2019 | 01/03/2020 |  |  |  | 01/10/2020 | 12/20/2019
3 |  | 0 | 260573 | Low |  | Product Data | Protective Device Study | 2. Construction Period Submittal: During the construction period but prior to application of utility power to the electrical distribution system, submit an indexed copy of the complete protective device study based on actual field values. Include the following: 1. Introductory section with basic formulas, pertinent data, and rationale employed in the study. |  |  | Assigned to Sub |  | Buck Wilkinson | Wilkinson Electric Inc |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
1 |  | 2 | 260573 | High |  | Product Data | Protective Device Study | 1. Submit partial study that includes the calculated values for short circuit current availability and arc flash levels for each switchgear bus, medium voltage controller, switchboard, low voltage motor control center, distribution panelboard, automatic transfer switch, and branch circuit panelboard. This data shall be submitted prior to, or at the same time as, submitting the entire electrical gear package. If partial study is not received prior to other submittals, the associated submittal will be rejected and not reviewed. Contractor shall utilize construction drawings to estimate approximate feeder lengths for this preliminary submittal. Submitted data shall include equipment/panel designations, feeder conductor sizes, feeder lengths, and calculated short circuit values and arc flash levels. Include the utility transformer ratings and transformer impedances used for the preparation of the short circuit calculations. 1. Partial study shall be submitted prior to switchboards, switchgear, panelboards, transformers, etc. 2. One-line diagram for that portion of the system included in the study. 3. Calculations section showing tabulated calculations. 4. Results, recommendations, settings, etc. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 04/24/2020 |  | 06/23/2020 | 04/09/2020 | 05/14/2020 | 06/09/2020 | 07/16/2020 |  | 07/16/2020 | 04/09/2020
1 |  | 0 | 260585 | Low |  | Shop Drawing | QUICK-CONNECT PANELBOARDS | 1. Shop Drawings: Submit dimensioned drawings of quick-connect panelboards and enclosures showing accurately scaled layouts of enclosures. Include schedule and ratings of devices, including, but not necessarily limited to, circuit breakers, Kirk Key interlocks, hardware lugs, cam locks, fuse holders, phase rotation monitors, interconnecting wiring and bussing, auto start terminals, breaker status relays, and accessories.2. Equipment Room Layouts: Submit dimensioned drawings of all equipment rooms indicating spatial relationships to other proximate equipment. Insure that all code required clearances are maintained. |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/09/2020 |  | 01/09/2020 | 12/18/2019
2 |  | 0 | 260923 | Low |  | Shop Drawing | Occupancy Sensors | 2. Submit scaled drawings with lighting fixtures shown and sensor equipment/devices clearly marked by manufacturer showing proper product, location, coverage pattern and orientation of each sensor. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 02/03/2020 |  |  |  | 03/02/2020 | 12/18/2019
1 |  | 1 | 260923 | Low |  | Product Data | Occupancy Sensors | 1. Submit manufacturer's data on occupancy sensors, control modules, wiring diagrams, instructions for installation, interconnection diagrams and any related accessories. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 03/16/2020 | 02/19/2020 | 02/24/2020 | 03/02/2020 | 04/02/2020 |  | 04/09/2020 | 02/19/2020 |  | Electrical Engineers
1 |  | 1 | 260943 | Low |  | Product Data | Lighting Control Equipment | 1. Submit manufacturer’s data on lighting control equipment including, but not limited to published catalog data sheets, rough-in diagrams and instructions for installation, operating and maintenance, suitable for inclusion in maintenance manuals. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 03/16/2020 | 02/19/2020 | 03/02/2020 | 03/02/2020 | 04/15/2020 |  | 04/16/2020 | 02/19/2020 |  | Jessica Blundell, Scott Hardy
2 |  | 1 | 260943 | Low |  | Shop Drawing | Lighting Control Equipment | 2. Submit detailed drawings and documentation of lighting control components and interconnection including, but not necessarily limited to: 1. Electronic controllers 2. Control stations 3. Photo sensors 4. Occupancy sensors 5. Network wiring details 6. Input and output wiring details 7. Lighting control panel load schedules 8. Accurately scaled equipment layouts, wire/cable routing and connections to control wiring and electrical power feeders. 9. Submit scaled drawings/floor plans with locations of all equipment and devices clearly shown for installation purposes. 260923 - Occupancy Sensors 2. Submit scaled drawings with lighting fixtures shown and sensor equipment/devices clearly marked by manufacturer showing proper product, location, coverage pattern and orientation of each sensor. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 05/01/2020 |  | 10/06/2020 | 04/16/2020 | 09/17/2020 | 09/21/2020 | 11/09/2020 |  | 11/10/2020 | 04/16/2020
2 |  | 0 | 262200 | Low |  | Shop Drawing | Transformers | 2. Submit dimensioned drawings of transformer installations, showing layout, mountings and supports, and spatial relationship to proximate walls and equipment. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/24/2019 |  |  |  | 01/02/2020 | 12/18/2019
1 |  | 1 | 262200 | Low |  | Product Data | Transformers | 1. Submit manufacturer's data on transformers, including certification of transformer performance efficiency, percentage regulation at 100 percent and 80 percent power factor, no-load and full load losses in watts, percent impedance at 75 degrees C, hot-spot and average temperature rise above 40 degrees C ambient, sound level in decibels, and standard published data. Before submitting product data, verify that dimensions of units to be supplied allow proper code required clearances adjacent to unit. 2. Submit dimensioned drawings of transformer installations, showing layout, mountings and supports, and spatial relationship to proximate walls and equipment. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  | 02/07/2020 |  |  | 03/16/2020 | 01/31/2020 | 01/31/2020 | 03/02/2020 | 03/24/2020 |  | 03/26/2020 | 01/31/2020 |  | Jessica Blundell, Scott Hardy
2 |  | 0 | 262413 | Low |  | Shop Drawing | Switchgear and Switchboards | 3. Submit dimensioned drawings of switchgear and switchboards showing accurately scaled basic sections including, but not necessarily limited to, auxiliary compartments, section components, and combination sections. Show plan view of equipment with dimensioned clearances to proximate equipment. Failure to submit said plan view shall not relieve contractor of responsibility to verify required clearances before release of equipment for fabrication. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/24/2019 |  |  |  | 01/02/2020 | 12/18/2019
1 |  | 1 | 262413 | Low |  | Product Data | Switchgear and Switchboards | 262413 - Switchgear and Switchboards 2. Submit manufacturer's data on switchgear and switchboards. 3. Submit dimensioned drawings of switchgear and switchboards showing accurately scaled basic sections including, but not necessarily limited to, auxiliary compartments, section components, and combination sections. Show plan view of equipment with dimensioned clearances to proximate equipment. Failure to submit said plan view shall not relieve contractor of responsibility to verify required clearances before release of equipment for fabrication. 262713 - Service Entrance 1. Submit manufacturer's data on service-entrance equipment and accessories. 3. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2713 submittals received prior to submission of the preliminary protective device study will be REJECTED. 2. Submit dimensioned layouts of service-entrance equipment and spatial relationships to proximate equipment. Failure to submit said layouts shall not relieve contractor of responsibility to verify required clearances before release of equipment to fabrication. 3. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2713 submittals received prior to submission of the preliminary protective device study will be REJECTED. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 03/16/2020 |  | 03/02/2020 | 03/02/2020 | 03/18/2020 |  | 03/26/2020 | 03/02/2020
1 |  | 0 | 262416 | Low |  | Shop Drawing | Panelboards | 2. Submit dimensioned drawings of panelboards and enclosures showing accurately scaled layouts of enclosures and required individual panelboard devices, including but not necessarily limited to, circuit breakers, fusible switches, fuses, ground-fault circuit interrupters, and accessories. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/24/2019 |  |  |  | 01/02/2020 | 12/18/2019
2 |  | 1 | 262416 | Low |  | Product Data | Panelboards | 3. Submit manufacturer data including specifications, installation instructions and general recommendations, for each type of panelboard required. 2. Submit dimensioned drawings of panelboards and enclosures showing accurately scaled layouts of enclosures and required individual panelboard devices, including but not necessarily limited to, circuit breakers, fusible switches, fuses, ground-fault circuit interrupters, and accessories. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/29/2020 |  | 04/17/2020 | 02/19/2020 | 03/04/2020 | 04/01/2020 | 04/03/2020 |  | 04/09/2020 | 02/19/2020
2 |  | 0 | 262713 | Low |  | Shop Drawing | Service Entrance | 2. Submit dimensioned layouts of service-entrance equipment and spatial relationships to proximate equipment. Failure to submit said layouts shall not relieve contractor of responsibility to verify required clearances before release of equipment to fabrication. 3. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2713 submittals received prior to submission of the preliminary protective device study will be REJECTED. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/24/2019 |  |  |  | 01/02/2020 | 12/18/2019
1 |  | 1 | 262713 | Low |  | Product Data | Service Entrance | 1. Submit manufacturer's data on service-entrance equipment and accessories. 3. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2713 submittals received prior to submission of the preliminary protective device study will be REJECTED. 2. Submit dimensioned layouts of service-entrance equipment and spatial relationships to proximate equipment. Failure to submit said layouts shall not relieve contractor of responsibility to verify required clearances before release of equipment to fabrication. 3. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2713 submittals received prior to submission of the preliminary protective device study will be REJECTED. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/29/2020 |  | 01/20/2020 | 02/19/2020 | 03/02/2020 |  |  |  | 03/02/2020 | 02/19/2020
1 |  | 0 | 262726 | Low | Samples | Submittal | Wiring Devices | 1. Submit manufacturer's data and color samples on electrical wiring devices. |  |  | Closed | Revise and Resubmit |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | Interior Designer | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 |  | 04/15/2020 | 04/16/2020 | 12/18/2019
2 |  | 0 | 262773 | Low |  | Shop Drawing | CHIME SYSTEM | B. Shop Drawings: Location of transformer, push button and bell. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
1 |  | 1 | 262773 | Low |  | Product Data | CHIME SYSTEM | A. Product Data: For each type of product. B. Shop Drawings: Location of transformer, push button and bell. |  |  | Closed | Not Applicable |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/07/2020 |  | 01/06/2020 | 03/13/2020 | 04/13/2020 |  |  |  | 08/12/2020 | 02/05/2020 |  | Scott Hardy, Jessica Blundell
1 |  | 0 | 262815 | Low |  | Product Data | Overcurrent Protective Devices | 1. Submit manufacturer’s data and shop drawings only after completion of the preliminary protective device study (see Section 26 0573 as applicable). Any Section 26 2815 submittals received prior to submission of the preliminary protective device study will be REJECTED. 2. Submit manufacturer's data on overcurrent protective devices, including catalog cuts, time-current trip characteristic curves, and mounting requirements.4. Submit time-current trip curves (in log-log format) and trip setting parameter/range information (for each trip function) for all solid-state circuit breakers. 6. Where the Protective Device Study specification section 260573 is included in the project, the time-current curves and recommended trip settings for all solid-state circuit breakers shall be submitted as part of the protective device study. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 11/23/2020 |  |  |  | 11/23/2020 | 12/18/2019
2 |  | 0 | 262815 | Low |  | Shop Drawing | Overcurrent Protective Devices | 3. Submit layout drawings of overcurrent protective devices, with layouts of circuit breakers, including spatial relationships to proximate equipment. Failure to submit said spatial layouts does not relieve contractor of responsibility to verify all required clearances before release of equipment for fabrication. 5. Manufacturer shall also provide recommended trip settings with the shop drawing submittal (including ground fault settings) for coordination with downstream overcurrent devices. Manufacturer shall base recommendations on the AIC rating of the electrical equipment. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | Electrical Engineers | [6 empty] | 12/19/2019 | 09/04/2020 |  | 09/08/2020 |  | 09/08/2020 | 12/18/2019
1 |  | 0 | 262816 | Low |  | Product Data | Motor and Circuit Disconnects | 1. Submit manufacturer's data including specifications, installation and general recommendations, for each type of motor and circuit disconnect switch required. 2. Submit dimensioned drawings of electrical motor and circuit disconnect switches that have rating of 100 amperes and larger. |  |  | Closed | Approved As Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/14/2020 |  | 01/14/2020 | 12/18/2019
2 |  | 0 | 262816 | Low |  | Shop Drawing | Motor and Circuit Disconnects | 2. Submit dimensioned drawings of electrical motor and circuit disconnect switches that have rating of 100 amperes and larger. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
1 |  | 0 | 262913 | Low |  | Product Data | Motor Starters | 1. Submit manufacturer's data on motor starters. |  |  | Closed | Approved As Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/13/2020 |  | 01/13/2020 | 12/18/2019
2 |  | 0 | 262913 | Low |  | Shop Drawing | Motor Starters | 2. Submit dimensioned drawings of motor starters showing accurately scaled equipment layouts. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
1 |  | 0 | 262923 | Low |  | Product Data | Variable Frequency Drives | 1. Submit manufacturer's data on variable frequency drives. |  |  | Closed | No Exception Taken |  |  |  | John DeRosa | US Mechanical LLC | Westland PE’s |  | Mechanical Engineers |  |  |  | 01/03/2020 |  | 04/03/2020 | 12/20/2019 | 02/20/2020 | 03/25/2020 | 04/07/2020 |  | 04/09/2020 | 12/18/2019 |  | Jessica Blundell, Scott Hardy
2 |  | 0 | 263213 | Low |  | Shop Drawing | Emergency Electrical Systems | 1. Dimensioned drawings of emergency electrical system components and accessories including, but not necessarily limited to generator sets, day tanks, transfer switches, instruments and accessories, (and) annunciator panels, (and fuel line and exhaust piping). Show accurately scaled layouts of system components; indicate their spatial relationship to associated equipment; show connections to normal and emergency power feeders. Failure to submit said scaled lay-outs does not relieve contractor of responsibility to verify all required clearances before release of equipment for fabrication.3. Drawings depicting each of the following: 1. Base mounted equipment, with base and all attachments including anchor bolt template and recommended clearances for maintenance and operation. 2. Complete starting system, fuel system, cooling system, and exhaust system. 3. Electric wiring of relays, breakers, and switches with applicable single line and wiring diagrams and written description of operation and the instrumentation provided. 4. Tank size with run time at rated load. 5. Enclosure (if applicable). |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
3 |  | 1 | 263213 | Low |  | Product Data | Emergency Electrical Systems | 2. Manufacturer’s standard catalog data describing and depicting each engine-generator set, batteries, charger, tanks, and all ancillary equipment in sufficient detail to demonstrate complete specification compliance. 4. Manufacturer’s standard catalog data describing and depicting each transfer switch along with all ancillary equipment in sufficient detail to demonstrate complete specification compliance. In addition provide the following: 1. One-line diagram of each switch assembly and wiring diagram of each unit. 2. A complete list of equipment and material to be provided, containing an adequate description of each separate item of equipment. |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/24/2020 |  | 02/14/2020 | 01/14/2020 | 01/27/2020 | 01/30/2020 | 02/24/2020 |  | 02/26/2020 | 01/14/2020
1 |  | 0 | 264113 | Low |  | Product Data | LIGHTNING PROTECTION FOR STRUCTURES | A. Product Data: For each type of product indicated.A. Qualification Data: For qualified Installer and manufacturer. Include data on listing or certification by UL.B. Field quality-control reports.C. Comply with recommendations in NFPA 780, Annex D, "Inspection and Maintenance of Lightning Protection Systems," for maintenance of the lightning protection system.D. Other Informational Submittals: Plans showing dimensioned as-built locations of grounding features, including the following: 1. Ground rods. 2. Ground loop conductor. B. Shop Drawings: For air terminals and mounting accessories. 1. Layout of the lightning protection system, along with details of the components to be used in the installation. 2. Include indications for use of raceway, data on how concealment requirements will be met, and calculations required by NFPA 780 for bonding of grounded and isolated metal bodies. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/22/2020 |  | 01/28/2020 | 12/18/2019
2 |  | 0 | 264113 | Low |  | Shop Drawing | LIGHTNING PROTECTION FOR STRUCTURES | B. Shop Drawings: For air terminals and mounting accessories. 1. Layout of the lightning protection system, along with details of the components to be used in the installation. 2. Include indications for use of raceway, data on how concealment requirements will be met, and calculations required by NFPA 780 for bonding of grounded and isolated metal bodies. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
1 |  | 0 | 264313 | Low |  | Product Data | Surge Protective Devices (SPD) | 1. Submit manufacturer's data on SPD’s listing all performance ratings specified or required herein. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/23/2020 |  | 01/23/2020 | 12/18/2019
2 |  | 0 | 264313 | Low |  | Shop Drawing | Surge Protective Devices (SPD) | 2. Submit dimensioned drawings of SPD’s including, but not necessarily limited to, the following. 1. Complete data sheet. 2. Set of outline drawings giving complete mounting information, conduit entry and exit locations and dimensions, overall unit dimensions, weights, physical characteristics, etc. 3. Set of complete electrical drawings for power and control wiring. 4. Manufacturer's literature giving detailed information of equipment including parts numbers, model numbers and ratings. 5. UL 1449 suppressed voltage rating documentation. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
2 |  | 0 | 265100 | Low |  | Shop Drawing | Interior and Exterior Building Lighting | 3. Submit dimensioned drawings of lighting fixtures. Submit fixture shop drawings in PDF format with separate sheet for each fixture, assembled in luminaire "type" alphabetical order, with each “type” individually bookmarked, with proposed fixture catalog number and accessories clearly indicated on each sheet. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 01/03/2020 |  |  |  | 01/10/2020 | 12/18/2019
6 |  | 0 | 265100 | High |  | Shop Drawing | Deco Lighting (Schonbek B & C Globes) GHID | Family C Globe on Family D (Celestial Room Side fixtures) Family B Globe |  |  | Closed | See Other |  |  |  | Claudia Hawkins | Swarovski Lighting Ltd. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 09/29/2020 | 09/30/2020 | 09/30/2020 | 09/21/2020 | 09/21/2020 | 09/21/2020 | 10/12/2020 |  | 10/28/2020 | 09/21/2020
7 |  | 0 | 265100 | High |  | Submittal | Deco Lighting (Schonbek Complete) GHID | Schonbek Fixtures complete |  |  | Closed | Make Corrections Noted |  |  |  | Claudia Hawkins | Swarovski Lighting Ltd. | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 10/08/2020 | 10/08/2020 | 10/08/2020 | 10/06/2020 | 10/06/2020 | 10/06/2020 | 10/08/2020 |  | 10/08/2020 | 10/06/2020 | Paul Monson, Eric Jamison, Ryan Thomas, Scott Gilberg
5 |  | 1 | 265100 | High |  | Product Data | Urgent Can Lights | The is a breakout of the urgent items that were approved conditionally by envision for CRSA and the Interior Designer to review. These items are already delaying the install on the 5th floor. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 04/03/2020 |  |  | 01/05/2021 | 02/10/2021 |  | 02/11/2021 | 10/12/2020 |  | Jessica Blundell, Scott Hardy, Interior Designer
1 |  | 2 | 265100 | High |  | Product Data | 265100 & 265600 Lighting GHID | The Electrical Engineer already reviewed this submittal. Their review said, "* Architect & Interior Designer must also review and approve submittal." We are still waiting for this to be stamped by the Architect & Interior Designer. |  | 01/04/2021 | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  | 12/15/2020 | 12/23/2020 | 12/25/2020 | 11/26/2020 |  |  | 11/16/2020 | 12/21/2020 |  | 12/22/2020 | 11/16/2020 |  | Gloria Kummer
8 |  | 0 | 265100 | Medium |  | Submittal | Can Lights Resubmittal (AA6D & AA6E) |  |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | David Tibbitts | ENVISION ENGINEERING |  |  | 11/29/2020 | 12/01/2020 | 12/18/2020 | 11/22/2020 | 12/04/2020 | 12/08/2020 | 12/16/2020 |  | 12/18/2020 | 11/22/2020
10 |  | 0 | 265100 | Medium |  | Submittal | Back-lit Window Lighting CCD_69R1 |  |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | David Tibbitts | ENVISION ENGINEERING |  |  | 12/08/2020 | 12/17/2020 | 12/28/2020 | 12/07/2020 | 12/07/2020 | 12/18/2020 | 12/21/2020 |  | 01/11/2021 | 12/07/2020
11 |  | 0 | 265100 | High |  | Submittal | Deco Lighting Two-Tone I-1 Pendants |  |  |  | Closed | Make Corrections Noted |  |  |  | Leeann Latsch | Remains Lighting | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 01/20/2021 | 01/22/2021 | 01/22/2021 |  | 01/12/2021 | 01/12/2021 | 02/22/2021 |  | 03/23/2021 | 01/12/2021
3 |  | 1 | 265100 | Low | Samples | Submittal | Interior and Exterior Building Lighting | 4. When applicable submit standard color samples with the shop drawings. If standard colors are not acceptable, a color sample will be provided to the fixture manufacturer. Return of the shop drawings will be delayed until color samples are provided. |  |  | Assigned to Sub |  | David Barney | Wilkinson Electric Inc | 12/18/2019 | David Barney | Wilkinson Electric Inc | Westland PE’s |  | Landscape Architects |  |  |  | 12/18/2019 |  | 03/19/2020 | 02/23/2021 | [5 empty] | 02/23/2021 |  | Kelly Gillman, Melissa Fryer, Electrical Engineers, Interior Designer
12 |  | 0 | 265100 | Medium | Samples | Submittal | Can Light Sample (DR3A) | Something weird happened with the first version of this submittal. This is me reposting it with the color selection attached. This is an updated version of 265100.09 where I combine the review from Envision and GHID. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Electrical Engineers |  |  |  | 04/13/2021 | 04/15/2021 | 04/15/2021 | 11/22/2020 | 04/05/2021 | 04/05/2021 | 04/05/2021 | 03/17/2021 | 04/05/2021 | 04/05/2021 | David Tibbitts
13 |  | 0 | 265100 | High |  | Submittal | INTERIOR AND EXTERIOR BUILDING LIGHTING – LS4C |  |  |  | Closed | Approved As Noted |  |  |  | David Barney | Wilkinson Electric Inc | David Tibbitts | ENVISION ENGINEERING | Electrical Engineers |  | 0 |  | 04/22/2021 | 05/07/2021 | 05/03/2021 | 04/23/2021 | 04/23/2021 | 04/23/2021 | 04/26/2021 |  | 04/27/2021 | 04/23/2021
14 |  | 0 | 265100 | High |  | Submittal | Custom Lighting |  |  |  | Closed |  |  |  |  | Claudia Hawkins | Swarovski Lighting Ltd. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  | 0 |  |  |  | 05/21/2021 |  | 05/13/2021 | 05/13/2021 | 06/07/2021 |  | 06/07/2021 | 05/13/2021 |  | David Tibbitts
15 |  | 0 | 265100 | High |  | Submittal | New Light Type LS4C (ASI 120) |  |  |  | Closed |  |  |  |  | David Barney | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Electrical Engineers |  | 0 |  |  |  | 05/21/2021 |  | 05/13/2021 | 05/13/2021 | 05/24/2021 |  | 06/22/2021 | 05/13/2021
1 |  | 0 | 265101 | Low |  | Product Data | Chandeliers and Pendants | 1. Product Data: For each type of lighting fixture, arranged in order of fixture designation. Include data on features, accessories, and finishes. i. Physical description of lighting fixture including dimensions. ii. Materials and Finishes iii. Sockets with max wattage labels iv. Recommended lamp wattage v. Maximum lamp wattage vi. Fixture electrical load vii. Voltage viii. Mounting ix. Weight 3. Detail equipment assemblies and indicate dimensions, weights, loads, required clearances, method of field assembly, components, and location and size of each field connection, and any other information essential for a complete installation per the manufacturers and NEC description. 4. Provide an approval letter from the manufacturer stating the fixture connections are per their instruction. 2. Shop Drawings: For nonstandard or custom lighting fixtures. Include plans, elevations, sections, details, |  |  | Closed | Not Applicable |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 03/02/2020 | 03/04/2020 |  |  |  | 08/12/2020 | 12/18/2019
3 |  | 0 | 265101 | Low | Mock-up - Mock-ups use this package. | Mock-Up | CHANDELIERS AND PENDANTS | C. Mockups: Provide interior lighting fixtures for room or module mockups, complete with power and control connections.1. Obtain Lighting Designer’s and Architect’s approval of fixtures for mockups prior to starting installation.2. Maintain mockups during construction in an undisturbed condition as a standard for judging the completed work.3. Remove mockups as directed.4. Mockups evaluated on the project site may become part of the completed Work with the approval of the Owner, Lighting Designer/Engineer, and Architect if the mockup is undisturbed at the time of substantial completion. |  |  | Assigned to Sub |  | Buck Wilkinson | Wilkinson Electric Inc | 07/31/2020 | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 07/31/2020 |  |  | 12/19/2019 | 01/03/2020 |  |  |  |  | 12/18/2019
2 |  | 2 | 265101 | Medium |  | Shop Drawing | Chandeliers and Pendants - Remains | 2. Shop Drawings: For nonstandard or custom lighting fixtures. Include plans, elevations, sections, details, |  |  | Assigned to Sub |  | Leeann Latsch | Remains Lighting | 12/18/2019 | Leeann Latsch | Remains Lighting | Westland PE’s |  | Interior Designer |  |  |  | 12/18/2019 |  | 08/18/2020 | 09/04/2020 | [5 empty] | 09/04/2020 |  | Electrical Engineers
4 |  | 0 | 265101 | Medium |  | Shop Drawing | Chandeliers and Pendants - Remains Brass Color | Brass Color Shop Drawing |  |  | Closed | See Other |  |  |  | Leeann Latsch | Remains Lighting | Camron Walker | Westland Construction, Inc. | Interior Designer |  |  |  | 01/30/2021 | 02/01/2021 | 02/11/2021 | 09/04/2020 |  |  | 01/22/2021 |  | 01/22/2021 | 01/22/2021 |  | Electrical Engineers
5 |  | 0 | 265101 | Medium |  | Submittal | Remains Globe Sample |  |  |  | Closed | Make Corrections Noted |  |  |  | Leeann Latsch | Remains Lighting | Camron Walker | Westland Construction, Inc. | Interior Designer |  | 0 |  | 06/26/2021 | 06/28/2021 | 07/02/2021 |  | 06/18/2021 | 06/23/2021 | 06/29/2021 |  | 06/29/2021 | 06/18/2021 | Leeann Latsch
2 |  | 0 | 265600 | High |  | Submittal | Exterior Area Lighting | Samples: BL42A Bollard LF3A Lumiere Swivel Spot IR7A/B Vista In-Ground Light SL9X3A Vista Step Light |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | Electrical Engineers |  |  |  | 06/19/2020 | 06/13/2020 | 06/21/2020 | 06/11/2020 | 06/11/2020 | 06/11/2020 | 09/01/2020 |  | 09/04/2020 | 06/11/2020 |  | Landscape Architects
1 |  | 2 | 265600 | High |  | Product Data | Exterior Area Lighting | 1. Submit manufacturer's data on lighting units, including certified dimension drawings of components including, but not necessarily limited to, poles and standards, mast arms, brackets, hardware and fixtures. |  |  | Closed | Approved As Noted |  |  |  | Trask Johnson | Wilkinson Electric Inc | David Tibbitts | ENVISION ENGINEERING | Electrical Engineers | [5 empty] | 04/06/2021 | 01/27/2021 | 04/22/2021 | 04/22/2021 | 04/24/2021 |  | 04/24/2021 | 01/27/2021 |  | Landscape Architects
3 |  | 0 | 265600 | High |  | Product Data | Exterior Area Lighting (Bronze Sconce) | Bronze Sconce from Historical Arts. |  |  | Closed | Make Corrections Noted |  |  |  | Steve Brown | Historical Arts & Casting Inc. | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 04/13/2021 | 04/15/2021 | 04/15/2021 | 01/27/2021 | 04/05/2021 | 04/05/2021 | 04/23/2021 |  | 04/26/2021 | 04/05/2021
4 |  | 0 | 265600 | Medium |  | Submittal | Exterior Lighting Color Selection LF3A |  |  |  | Closed | Approved As Noted |  |  |  | David Barney | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Landscape Architects |  | 0 |  |  |  | 06/01/2021 |  | 05/18/2021 | 05/18/2021 | 05/26/2021 |  | 06/22/2021 | 05/18/2021
5 |  | 0 | 265600 | Medium |  | Submittal | BL42A Bollard Light Update |  |  |  | Closed | Approved As Noted |  |  |  | David Barney | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Landscape Architects |  | 0 |  |  |  | 06/02/2021 |  | 05/19/2021 | 05/19/2021 | 06/07/2021 |  | 06/22/2021 | 05/19/2021 |  | David Tibbitts
6 |  | 0 | 265600 | Medium |  | Submittal | TLC Ground Box & Driver RFI 1044 |  |  |  | Design Review |  | Electrical Engineers |  | 07/20/2021 | David Barney | Wilkinson Electric Inc | Camron Walker | Westland Construction, Inc. | Electrical Engineers |  | 0 |  | 07/14/2021 | 07/16/2021 | 07/20/2021 |  | 07/06/2021 | 07/06/2021 |  |  |  | 07/06/2021
1 |  | 1 | 269330 | Low |  | Shop Drawing | CENTRAL DIMMING CONTROL | A. Shop Drawings: 1. Include interconnection diagrams of each system. 2. Include dimming load schedule indicating circuit loads, zoning, and, where applicable, emergency power. 3. Equipment Dimensions. 4. Shall be prepared by manufacturer through their project engineering service and shall include interconnection diagram of entire system. 5. Contractor shall submit completion documentation once startup is completed |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/28/2020 | 12/17/2020 | 01/29/2021 |  |  |  | 02/09/2021 | 02/19/2020
1 |  | 0 | 271500 | Low |  | Product Data | DATA COMMUNICATIONS SYSTEMS | 1. Product Data: a. Provide Manufacturer’s documentation, installation instructions, and descriptive information on each piece of equipment to be used.1. Certificates: a. Provide Installer certificates of qualifications required.2. Design Data: a. Identification and labeling: 1) Provide labeling system for cable installation to be approved by ICS Layer One Cable Plant Engineer Layer1Engineering@churchofjesuschrist.org. a) Clearly identify all components of system: racks, cables, panels and outlets. b) Designate cables origin and destination and unique identifier for cable within facility by room number and port count. c) Racks and patch panels shall be labeled to identify location within cable system infrastructure. b. After system installation, provide three (3) full documentation sets to Consulting Engineer/Architect for approval.5. Qualification Statements: a. Letter from Manufacturer certifying level of training and experience of Installer. |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/23/2020 |  | 01/23/2020 | 12/18/2019
2 |  | 0 | 271500 | Low |  | Shop Drawing | DATA COMMUNICATIONS SYSTEMS | 2. Shop Drawings: a. Provide submittal drawings, telecommunication rooms, and rack elevations schemes for engineering approval before project installation begins outlets. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 02/14/2020 | 12/19/2019 | 01/21/2020 | 01/30/2020 | 02/18/2020 |  | 02/20/2020 | 12/18/2019
5 |  | 0 | 271500 | Low |  | Product Data | DATA COMMUNICATIONS SYSTEMS | Please provide the following per the review of submittal 1: Scneider AR3140W is not an approved cabinet per specifications for MDF room. Provide cabinet per specifications. Provide (2) Clik-Nut Hardware kits per rack. For IDF/Remote TRs provide adjustable version of the 4 post, open rack. CPI 1521-3-7-03. Adjusted to at least 33” depth. Provide (2) Clik-Nut Hardware kits per rack CAT 5e is not acceptable cable type for horizontal cabling per specification. Provide CAT6e product as submitted above. Can be acceptable for backbone cabling in lieu of 25 pair backbone. Provide wet location listed cable at all outdoor and under slab locations. Ditek Surge protection for exterior cable runs Not yet submitted. These are contractor required for each data cable that is for exterior security cameras and other data cable ran exterior to the building. To be provided on a shelf at the rack. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/06/2020 | 03/13/2020 | 04/11/2020 | 01/30/2020 | 03/11/2020 | 04/01/2020 | 04/16/2020 |  | 04/30/2020 | 01/30/2020
1 |  | 0 | 273216 | Low |  | Shop Drawing | WIRELESS TRANSCEIVERS RADIO SYSTEM | A. Shop Drawings: 1. Prepared by authorized factory representative and including: a. Single line diagram of actual system. b. Complete wiring diagrams. (These are included in operator and owners manuals and can be found on line as well.) |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/23/2020 |  | 01/28/2020 | 12/18/2019
3 |  | 0 | 273216 | Low |  | Shop Drawing | WIRELESS TRANSCEIVERS RADIO SYSTEM | Other requested items during the review of submittal 1: Prepare schedule of all alarm points to submit with resubmittal for review and approval. Coordinate with fire alarm and security system installers as well as controls contractor, and electrician to confirm that all alarm points are accounted and planned for and necessary dry contacts, control modules and other interface devices and wiring is provide for a complete system installation. Additional cabinets containing contacts/relays/control modules will be necessary and should be located adjacent to Zetron panel in MDF room Coordinate with owner for voice recording of alarm points per their preferences. This submittal is to be sent to Brian Chandler brian.chandler@churchofjesuschrist.org and Kory Wood Talbot Kory.Talbot@churchofjesuschrist.org for their review and comment prior to approval. Other "Missing" items: Provide battery backup of system per specifications, complete with charger, cables, etc. Provide power strips as required for equipment. Provide installer qualification data and experience with installation of similar system. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/05/2020 | 04/01/2020 | 04/09/2020 | 01/28/2020 | 03/30/2020 | 03/30/2020 | 04/03/2020 | 03/30/2020 | 04/09/2020 | 01/28/2020 |  | Scott Hardy, Jessica Blundell
2 |  | 0 | 273244 | Low |  | Product Data | Two-Way Communication | 1. Data sheets on all equipment being provided as well as recommended cable types. Internal control cabinet drawings showing internal block diagram connections shall be provided. Wiring diagrams showing typical field wiring connections as well as single line floor plan indicating equipment locations as well as cable routings and quantities. 2. Submit product data, including manufacturer's (Specifications Data) product sheet, for specified products. 3. Submit shop drawings showing layout, profiles, and product components, including anchorage and accessories. Include cabling diagrams, wiring diagrams, station installation details, and equipment cabinet details. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/18/2019 |  | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/20/2019 | 01/23/2020 |  | 01/24/2020 | 12/18/2019
3 |  | 0 | 273244 | Low |  | Shop Drawing | Two-Way Communication | 3. Submit shop drawings showing layout, profiles, and product components, including anchorage and accessories. Include cabling diagrams, wiring diagrams, station installation details, and equipment cabinet details. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [5 empty] | 12/18/2019 |  |  | 12/19/2019 | 12/19/2019 |  |  |  | 12/20/2019 | 12/18/2019
3 |  | 0 | 281601 | Low |  | Product Data | Intrusion Detection System | Submit manufacturer's data sheets including specifications, installation instructions, and general recommendation for each type of equipment specified. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 01/06/2020 | 12/19/2019 | 12/19/2019 | 12/21/2019 | 01/23/2020 |  | 01/23/2020 | 12/18/2019
2 |  | 0 | 281601 | Low |  | Shop Drawing | Intrusion Detection System | A. Shop Drawings: 1. Prepared by authorized factory representative and including: a. Single line diagram of actual system. Typical riser diagrams are not acceptable. b. Complete panel wiring diagrams. c. Detailed Description of Surge Protection Methods/Devices for System d. Manufacturer's current catalog data and descriptive information on each piece of equipment to be used. 2. Submit dimensioned drawings and schematics for design of system. Submit actual riser diagrams of complete system and elevations of required equipment. Typical risers are not acceptable. |  |  | Closed |  |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 01/28/2020 | 12/19/2019 | 01/03/2020 | 01/13/2020 | 02/13/2020 | 02/19/2020 | 02/19/2020 | 12/18/2019
1 |  | 1 | 282300 | Low |  | Product Data | VIDEO SURVEILLANCE | A. Equipment List: Include every piece of equipment by manufacturer, model number, brief description and location.B. Product Data: For each type of product indicated. Include manufacturers current catalog sheets indicating dimensions and data on features, performance, electrical characteristics, ratings, and finishes. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/31/2020 |  | 03/16/2020 | 01/28/2020 | 03/02/2020 | 03/02/2020 |  |  | 03/02/2020 | 01/28/2020
2 |  | 1 | 282300 | Low |  | Shop Drawing | VIDEO SURVEILLANCE | C. Shop Drawings: Prepared by a factory authorized representative including the following: 1. Provide dimensioned plan and elevations of equipment racks showing all video surveillance components including but not limited to patch panels, and provisions for owner provided equipment. Show rack space, access and workspace requirements. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/06/2020 |  | 04/17/2020 | 03/02/2020 | 03/04/2020 | 04/01/2020 | 04/16/2020 |  | 04/30/2020 | 03/02/2020
2 |  | 0 | 283111 | Low |  | Shop Drawing | Fire Alarm and Detection System | 2. Provide shop drawings showing equipment/device locations and connecting wiring of entire fire alarm and detection system. Include wiring diagrams and riser diagrams of panel. Provide dimensioned drawing of Fire Alarm Control Panel and Building Graphic. Shop drawings shall be prepared by an individual with a minimum NICET III (Fire Protection Engineering Technology/Fire Alarm Systems) certification. The individual’s name and certification number shall be shown on the submittal design drawings. 4. A complete set of shop drawings indicating: a. Location of all alarm-initiating and alarm-signaling devices. b. Point-to-point wiring diagrams for all alarm-initiating and alarm-signaling devices. c. Standby battery calculations, including voltage drop calculation. |  |  | Closed | See Other |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | 12/19/2019 |  |  |  | 12/21/2019 | 12/18/2019
3 |  | 0 | 283111 | Low |  | Submittal Certificate | Fire Alarm and Detection System | 8. Submit to State and Local Fire Marshall, a complete Certificate of Compliance |  |  | Assigned to Sub |  | Buck Wilkinson | Wilkinson Electric Inc |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 283111 | Low |  | Product Data | Fire Alarm and Detection System | Resubmittal for the Annunciator This large version of the remote annunciator will not be acceptable at the front entry/vestibule. If required it would need to be located at the administration office, receiving area or alternate back of house location as approved by AHJ, Owner and architect. Provide smaller, recessed, white version or remote annunciator for entry vestibule as required by local AHJ/Fire Marshal. Coordinate location of fire alarm remote |  |  | Closed | Make Corrections Noted |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 02/05/2020 | 02/08/2020 | 03/13/2020 | 01/28/2020 | 02/06/2020 | 03/02/2020 | 03/18/2020 |  | 03/26/2020 | 01/28/2020 |  | Scott Hardy, Jessica Blundell
1 |  | 1 | 283111 | High |  | Product Data | Fire Alarm and Detection System | Rev 1: Includes changes through CCD_54.4 1. Submit manufacturer's data on fire alarm and detection systems including, but not limited to, roughing-in diagrams and instructions for installation, operating and maintenance, suitable for inclusion in maintenance manuals. 3. Submit a written statement to the Architect and the state and local Fire Marshal's Office that each device of the fire alarm system will be installed, inspected and tested in accordance with applicable requirements of NFPA Standard 72. 5. Wiring diagrams for: a. Alarm control panels. b. Auxiliary function relays and solenoids. c. Remote signaling equipment. 6. A complete equipment list identifying: a. Type b. Model c. Manufacturer d. Manufacturer catalog data sheets e. UL Listing and/or FM approval showing compatibility of device with Fire Alarm Control Panel (FACP) 7. A complete zone list identifying all: a. Alarm-initiating and alarm-signaling devices. b. Remote signaling and auxiliary function zones. c. Specific devices associated with each zone. |  |  | Closed | No Exception Taken |  |  |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 08/27/2020 | 08/07/2020 | 08/07/2020 | 08/12/2020 | 10/09/2020 |  | 10/09/2020 | 08/07/2020 |  | Mechanical Engineers, Electrical Engineers, Structural Engineers
1 |  | 0 | 283113 | Low |  | Product Data | Fire Alarm and Detection System | a. Manual Requirements i. Operating and maintenance manuals shall be submitted prior to testing of the system. Manuals shall include all service, installation, and programming information. |  |  | Assigned to Sub |  | Buck Wilkinson | Wilkinson Electric Inc |  | Buck Wilkinson | Wilkinson Electric Inc | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 312000 | Low |  | Product Data | EARTH MOVING |  |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | CRSA ARCHITECTURE | [5 empty] | 11/15/2019 |  |  | 12/03/2019 | 12/03/2019 | 11/27/2019 | 12/03/2019 | 11/01/2019 |  | Civil Engineers
3 |  | 0 | 312000 | Low |  | Product Data | EARTH MOVING |  |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | Civil Engineers | [5 empty] | 11/15/2019 |  |  | 11/22/2019 | 11/27/2019 |  | 12/03/2019 | 11/01/2019
4 |  | 0 | 312000 | Low |  | Product Data | EARTH MOVING | Imported structural fill Brad Pierce Pit |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | Civil Engineers |  |  |  | 02/06/2020 | 01/31/2020 | 02/09/2020 | 01/29/2020 | 01/29/2020 | 01/30/2020 | 02/10/2020 | 11/27/2019 | 02/19/2020 | 01/29/2020
5 |  | 1 | 312000 | High |  | Shop Drawing | Shoring |  |  |  | Closed | No Exception Taken |  |  |  | Matt Madsen | Malcolm Drilling Co Inc | Westland PE’s |  | CRSA ARCHITECTURE |  | 0 |  | 03/31/2020 | 05/03/2020 | 05/11/2020 |  | 05/01/2020 | 05/01/2020 | 05/14/2020 |  | 05/14/2020 | 05/01/2020
6 |  | 0 | 312000 | High |  | Product Data | EARTH MOVING | Gradation report for a Pea gravel material we would like to use between the two concrete slabs in the Annex |  |  | Closed | No Exception Taken |  |  |  | Clint Foster | Sunroc Corporation | Camron Walker | Westland Construction, Inc. | CRSA ARCHITECTURE |  |  |  | 05/15/2020 | 05/09/2020 | 05/19/2020 | 01/29/2020 | 05/07/2020 | 05/12/2020 | 05/12/2020 | 11/27/2019 | 05/12/2020 | 05/07/2020 |  | Zach Hansen
1 |  | 0 | 313100 | High |  | Product Data | SOIL TREATMENT | A. Submit product data under provision that indicate toxicants to be used, composition by percentage, dilution schedule, and intended application rate. B. Certification that products comply with U.S. Environmental Protective Agency (EPA) regulations for termiticides. 1. Include the EPA-Registered Label for termiticide and borate products. |  |  | Closed | No Exception Taken |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 10/24/2019 |  | 03/16/2020 | 12/19/2019 | 02/21/2020 | 03/02/2020 | 03/04/2020 |  | 03/05/2020 | 12/18/2019
3 |  | 1 | 316330 | High |  | Shop Drawing | DRILLED MICROPILES | 3. Micropile Shop Drawings: Show sizes and grades of steel, splicing details, splice locations, corrosion protection system, casing and accessories such as grout tubes and rebar centering devices. 4. Plan describing how surface water, drill flush, and excess grout will be controlled and disposed of. 5. Proposed Grouting Plan: a. Grout tube placement. b. Grout mix design and materials to be used. c. Test results showing that the mix design meets the strength criteria. d. Methods and equipment to monitor and record grout depth, grout volume, and grout pressure as grout is placed. e. Method for field measuring grout consistency, and plan for assuring constant grout consistency. f. Grouting rate calculations. g. Estimated curing time. h. Procedure and equipment for contractor monitoring of grout quality. i. Post-grouting procedures. 6. Description of proposed micropile load test equipment and procedures. 7. Verification pile test results, including measured load/deformation curves compared against acceptance criteria. 8. Production pile test results, including measured deformation under load compared against acceptance criteria. |  |  | Closed | No Exception Taken |  |  |  | Matt Madsen | Malcolm Drilling Co Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/03/2020 |  | 01/18/2020 | 12/30/2019 | 01/07/2020 | 01/09/2020 | 01/10/2020 |  | 01/10/2020 | 12/30/2019
4 |  | 2 | 316330 | Low |  | Product Data | DRILLED MICROPILES | 1. Mill Certificates: Submit steel producer's certificates of mill analysis, including steel source, description, heat number, yield stress, ultimate tensile strength, elongation and chemical composition of each heat as determined by ladle analysis, before delivery of steel to site. a. For casing, two coupon tests per truckload delivered to the fabricator, may be submitted in lieu of Mill Certificates. Coupon test results shall indicate yield stress, ultimate tensile strength, elongation and chemical composition. 2. Manufacturer’s Certification: Furnish manufacturer’s certificates of compliance for all steel materials, including threadbar, mechanical couplers, terminators, deformed bar anchors and casing. 3. Calibration reports and data for each test jack, pressure gauge, master pressure gauge, and electronic load cell. a. Calibration to have been performed by an independent testing laboratory. b. Calibration tests to have been performed within 90 calendar days of the submittal date. 2. Design calculations prepared by a California-licensed civil or structural engineer, based on micropile design shown in the structural drawings, to: a. Meet load/deflection requirements shown of the drawings. b. Estimate deformation of pile in tension and compression based on load, pile length, threadbar, grout, casing, soil properties and other factors as appropriate. 6. Description of proposed micropile load test equipment and procedures. 7. Verification pile test results, including measured load/deformation curves compared against acceptance criteria. 8. Production pile test results, including measured deformation under load compared against acceptance criteria. |  |  | Closed | No Exception Taken |  |  |  | Matt Madsen | Malcolm Drilling Co Inc | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/08/2019 |  | 03/02/2020 | 02/19/2020 | 02/19/2020 | 02/19/2020 | 02/24/2020 |  | 02/26/2020 | 02/19/2020
1 |  | 0 | 320000 | Medium |  | Submittal | EXTERIOR IMPROVEMENT - Fountain |  |  |  | Closed | Approved |  |  |  | Mark Gabriele | Artisan Granite, LLC | David Adams | Westland Construction, Inc. | Landscape Architects |  | 0 |  | 12/18/2020 | 12/20/2020 | 12/20/2020 | 12/10/2020 |  | 12/10/2020 | 12/22/2020 |  | 12/22/2020 | 12/10/2020
1 |  | 0 | 321216 | Low |  | Product Data | ASPHALT PAVING | A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Product Data: For each product specified include technical data and tested physical performance properties. 2. Job Mix Designs: For each job mix proposed for the work. 3. Material Certificates: Provide copies of materials certificates signed by material producer and Contractor certifying that each material item complies with, or exceeds, specified requirements, including job mix design. |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | Civil Engineers |  |  |  | 11/01/2019 |  | 11/16/2019 | 10/15/2019 | 11/01/2019 | 11/22/2019 | 11/26/2019 |  | 12/03/2019 | 09/10/2019 | CRSA ARCHITECTURE
2 |  | 2 | 321216 | Low |  | Product Data | ASPHALT PAVING (Paint) | Clarification from the different asphalt paint Submittals. A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Product Data: For each product specified include technical data and tested physical performance properties. 2. Job Mix Designs: For each job mix proposed for the work. 3. Material Certificates: Provide copies of materials certificates signed by material producer and Contractor certifying that each material item complies with, or exceeds, specified requirements, including job mix design. |  |  | Closed | No Exception Taken |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 10/24/2019 | 02/23/2020 | 03/12/2020 | 10/23/2019 | 02/21/2020 | 03/02/2020 | 03/18/2020 |  | 03/24/2020 | 10/23/2019 |  | Civil Engineers
1 |  | 0 | 321313 | Low |  | Product Data | CONCRETE PAVING | 1. Provide samples, manufacturer's product data, test reports, and materials' certifications as required in referenced Section 03 30 00 for concrete, joint fillers and sealers. |  |  | Closed | Approved |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | Civil Engineers |  |  |  | 12/05/2019 |  | 01/20/2020 | 12/19/2019 | 12/31/2019 | 01/02/2020 | 01/20/2020 |  | 01/23/2020 | 12/18/2019
2 |  | 0 | 321313 | High | Samples | Submittal | CONCRETE PAVING | Aggregate samples for sidewalks |  |  | Closed | Not Applicable |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 03/13/2020 | 03/07/2020 | 03/17/2020 | 03/05/2020 | 03/05/2020 | 01/02/2020 | 01/20/2020 |  | 04/01/2020 | 03/05/2020
3 |  | 0 | 321313 | High |  | Product Data | CONCRETE PAVING | Pea Gravel Mix for Side Walks 1. Provide samples, manufacturer's product data, test reports, and materials' certifications as required in referenced Section 03 30 00 for concrete, joint fillers and sealers. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 03/21/2020 | 03/15/2020 | 04/10/2020 | 03/13/2020 | 03/13/2020 | 03/31/2020 | 04/03/2020 |  | 04/09/2020 | 03/13/2020
2 |  | 0 | 321413 | High | Samples | Submittal | PRECAST CONCRETE UNIT PAVING | B. Samples for Initial Selection: Manufacturer's color charts consisting of units or sections of units showing the full range of colors, textures, and patterns available for each type of unit paver indicated. 1. Include similar Samples of material for joints and accessories involving color selection. C. Samples for Verification: Full-size units of each type of unit paver indicated; in sets for each color, texture, and pattern specified, showing the full range of variations expected in these characteristics. 1. Provide Samples showing the full range of colors to be expected in the completed Work. 2. Include Samples of exposed edge restraints. |  |  | Closed | Approved |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 12/19/2019 |  | 04/03/2020 | 12/19/2019 | 03/23/2020 | 03/30/2020 | 04/03/2020 |  | 04/09/2020 | 12/18/2019
3 |  | 0 | 321413 | Low | Samples | Submittal | PRECAST CONCRETE UNIT PAVING | C. Samples for Verification: Full-size units of each type of unit paver indicated; in sets for each color, texture, and pattern specified, showing the full range of variations expected in these characteristics. 1. Provide Samples showing the full range of colors to be expected in the completed Work. 2. Include Samples of exposed edge restraints. |  |  | Closed | See Other |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s | [5 empty] | 12/19/2019 |  |  | 12/19/2019 |  |  |  |  | 02/28/2020 | 12/18/2019
1 |  | 1 | 321413 | High |  | Product Data | PRECAST CONCRETE UNIT PAVING | A. Product Data: For the following: 1. Concrete pavers. D. Qualification Data: For firms and persons specified in "Quality Assurance" Article to demonstrate their capabilities and experience. Include lists of completed projects with project names and addresses, names and addresses of architects and owners, and other information specified. A. Installer qualification: Submit proof of the following. 1. Installer shall have a minimum of 5 years successful experience in the installation of unit pavers, similar to the pavers required for this project. 2. Installer shall have suitably experienced personnel and a management capability sufficient to execute the work shown on the Drawing and specified herein. 3. The installer’s supervisor shall have a minimum of 10 years experience in the installation of unit paver systems similar in nature to this project. The installer shall ensure that the supervisor is on site for the entire duration of the project. |  |  | Closed | Approved As Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 03/06/2020 |  | 04/10/2020 | 03/05/2020 | 03/05/2020 | 03/30/2020 | 04/09/2020 |  | 04/14/2020 | 03/05/2020
5 |  | 0 | 321413 | High | Mock-up - Mock-ups use this package. | Submittal | PRECAST CONCRETE UNIT PAVING | Mock-up per related submittal. |  |  | Closed | Make Corrections Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 07/01/2020 | 06/25/2020 | 07/13/2020 | 06/23/2020 | 06/23/2020 | 06/23/2020 | 07/07/2020 |  | 07/16/2020 | 06/23/2020
4 |  | 1 | 321413 | Medium |  | Shop Drawing | PRECAST CONCRETE UNIT PAVING (Shop Drawings pt 1) |  |  |  | Closed | See Other |  |  |  | Bob Durrant | IMS Masonry Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 07/13/2020 |  | 05/04/2020 | 06/29/2020 | 09/03/2020 |  |  |  | 10/26/2020 | 06/29/2020
7 |  | 0 | 321413 | High |  | Submittal | PRECAST CONCRETE UNIT PAVING - Shop Drawings CCD_88 | Shop Drawings for CCD_88 from IMS Masonry |  |  | Closed | Revise and Resubmit |  |  |  | Bob Durrant | IMS Masonry Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 12/08/2020 | 12/10/2020 | 12/10/2020 | 08/31/2020 | 11/30/2020 | 11/30/2020 |  | 12/24/2020 | 01/11/2021 | 11/30/2020
6 |  | 2 | 321413 | High |  | Submittal | PRECAST CONCRETE UNIT PAVING - Shop Drawings | Shop Drawings Complete from IMS Masonry for paving, fountains, and stone. |  |  | Closed | Make Corrections Noted |  |  |  | Bob Durrant | IMS Masonry Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 01/15/2021 | 07/31/2020 | 02/05/2021 | 01/11/2021 | 01/27/2021 | 01/29/2021 | 02/05/2021 |  | 02/09/2021 | 01/11/2021
1 |  | 0 | 323119 | High |  | Product Data | DECORATIVE METAL FENCES AND GATES | A. Product Data: For each type of product.B. Product Test Reports: For decorative metallic-coated-steel tubular picket fences, including finish, indicating compliance with referenced standard and other specified requirements. |  |  | Closed | Make Corrections Noted |  |  |  | Jeremy Drake | Ducworks Inc. | Westland PE’s |  | Landscape Architects | [5 empty] | 12/22/2020 | 12/19/2019 | 12/07/2020 | 12/31/2020 | 01/04/2021 | 12/24/2020 | 01/05/2021 | 12/18/2019
3 |  | 0 | 323119 | Low | Samples | Submittal | DECORATIVE METAL FENCES AND GATES | C. Samples: For each fence material and for each color specified. 1. Provide Samples 12 inches in length for linear materials. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. |  | Jeremy Drake | Ducworks Inc. | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
5 |  | 0 | 323119 | Low | Mock-up - Mock-ups use this package. | Mock-Up | DECORATIVE METAL FENCES AND GATES | B. Mockups: Build mockups to verify selections made under Sample submittals, to demonstrate aesthetic effects, and to set quality standards for fabrication and installation. 1. Include 10-foot (3-m) length of fence complying with requirements. 2. Subject to compliance with requirements, approved mockups may become part of the completed Work if undisturbed at time of Substantial Completion. |  |  | Assigned to Sub |  | Jeremy Drake | Ducworks Inc. |  | Jeremy Drake | Ducworks Inc. | Westland PE’s | [8 empty] | 12/19/2019 | [5 empty] | 12/18/2019
2 |  | 2 | 323119 | High |  | Shop Drawing | DECORATIVE METAL FENCES AND GATES | B. Shop Drawings: For gates. Include plans, elevations, sections, details, and attachments to other work. 1. Include diagrams for power, signal, and control wiring. |  |  | Closed | Approved |  |  |  | Jeremy Drake | Ducworks Inc. | Westland PE’s |  | Landscape Architects |  |  |  | 12/21/2020 |  | 12/22/2020 | 12/17/2020 | 01/28/2021 | 03/15/2021 | 03/15/2021 |  | 03/22/2021 | 12/17/2020
6 |  | 0 | 323119 | High | DWGS - Shop Drawings | Submittal | DECORATIVE METAL FENCES AND GATES (Rolling Gate) | B. Shop Drawings: For gates. Include plans, elevations, sections, details, and attachments to other work. 1. Include diagrams for power, signal, and control wiring. |  |  | Closed | Approved |  |  |  | Jeremy Drake | Ducworks Inc. | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 03/03/2021 | 03/05/2021 | 03/11/2021 | 12/17/2020 | 02/24/2021 | 02/24/2021 | 03/12/2021 |  | 03/15/2021 | 02/23/2021
1 |  | 0 | 323213 | Low |  | Product Data | CAST IN PLACE CONCRETE RETAINING WALL | A. Product Data: Submit manufacturer's technical product data and installation instructions for concrete materials and products. |  |  | Closed | No Exception Taken |  |  |  | Judd Bundy | Innovative Concrete LLC | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/05/2019 |  | 01/20/2020 | 12/19/2019 | 12/31/2019 | 01/02/2020 | 01/10/2020 |  | 01/13/2020 | 12/18/2019
1 |  | 1 | 328400 | Medium |  | Product Data | Irrigation System |  |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  | 0 |  | 12/27/2019 |  | 01/24/2020 | 12/20/2019 | 01/03/2020 | 01/09/2020 | 01/09/2020 |  | 01/09/2020 | 12/20/2019
1 |  | 0 | 329113 | Low |  | Product Data | SOIL PREPARATION | A. Product Data: Product literature and chemical / nutrient analysis of soil amendments and fertilizers. |  |  | Closed | Approved As Noted |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 01/02/2020 |  | 01/06/2020 | 12/19/2019 | 12/20/2019 | 12/20/2019 | 12/24/2019 |  | 12/30/2019 | 12/18/2019
2 |  | 0 | 329113 | Low | Samples | Submittal | SOIL PREPARATION | B. Samples: Sample of soil conditioner and topsoil for approval before delivery to site. Include product analysis list and topsoil test report. |  |  | Closed | No Exception Taken |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/02/2020 |  | 02/14/2020 | 12/19/2019 | 01/29/2020 | 02/05/2020 | 02/05/2020 |  | 02/10/2020 | 12/18/2019
4 |  | 1 | 329113 | Low |  | Product Data | SOIL PREPARATION (MYCORRHIZAE SUPPLEMENT) | A. Product Data: Product literature and chemical / nutrient analysis of soil amendments and fertilizers. |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 01/22/2020 | 03/07/2020 | 04/05/2020 | 01/17/2020 | 03/05/2020 | 03/26/2020 | 03/31/2020 |  | 04/01/2020 | 01/17/2020
1 |  | 2 | 329116 | Low |  | Product Data | MULCHING | 1. Stabilizer: TechniSoil TSC5 G3 Commercial Surface Stabilizer (or approved equal). Submit product info/sample for approval prior to procurement. |  |  | Assigned to Sub |  | Jenn Lovell | Stratton & Bratt Landscaping | 06/15/2020 | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 06/15/2020 |  | 04/17/2020 | 06/09/2020 | [5 empty] | 06/09/2020 |  | Landscape Architects
1 |  | 0 | 329120 | Low |  | Product Data | EXCAVATION, GRADING & FILLING | A. Product Data: Contractor shall furnish sample of topsoil to Landscape Architect prior to placing. |  |  | Closed | Not Applicable |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s | [5 empty] | 12/23/2019 |  |  | 12/19/2019 |  |  |  |  | 07/29/2020 | 12/18/2019
1 |  | 0 | 329223 | Low |  | Product Data | SODDING | A. Quality Assurance / Control: 1. Written certification confirming lawn seed quality and mix. |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | Landscape Architects |  |  |  | 01/02/2020 |  | 01/20/2020 | 12/19/2019 | 12/31/2019 | 01/02/2020 |  | 01/14/2020 | 01/14/2020 | 12/18/2019 | Melissa Fryer
1 |  | 0 | 329300 | Low | Samples | Submittal | PLANTS | A. Samples: Top dressing mulch for approval before delivery to site. |  |  | Assigned to Sub |  | Jenn Lovell | Stratton & Bratt Landscaping | 01/03/2020 | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s | [5 empty] | 01/03/2020 |  |  | 12/20/2019 | [5 empty] | 12/18/2019
2 |  | 0 | 329300 | Low |  | Product Data | PLANTS | B. Photos: Provide photos of plant materials for approval prior to purchase and installation. |  |  | Assigned to Sub |  | Jenn Lovell | Stratton & Bratt Landscaping | 01/03/2020 | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s | [5 empty] | 01/03/2020 |  |  | 12/20/2019 | [5 empty] | 12/18/2019
4 |  | 0 | 329300 | Low |  | Product Data | PLANTS | 3.B. Planting: 3.C. Supports for New Trees: |  |  | Closed | Approved |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 12/28/2019 | 12/22/2019 | 01/06/2020 | 12/20/2019 | 12/20/2019 | 12/31/2019 | 12/31/2019 |  | 01/02/2020 | 12/20/2019
5 |  | 0 | 329300 | High | Samples | Submittal | Boulders |  |  |  | Closed | Final |  |  |  | Jenn Lovell | Stratton & Bratt Landscaping | Camron Walker | Westland Construction, Inc. | Landscape Architects |  |  |  | 05/01/2020 | 04/25/2020 | 05/03/2020 | 12/20/2019 | 04/23/2020 | 04/23/2020 |  | 04/23/2020 | 04/27/2020 | 04/23/2020 | CRSA ARCHITECTURE
1 |  | 0 | 330000 | High |  | Submittal Register | UTILITIES (Offsite) | A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Submit supporting catalog materials indicating pipe, pipe accessories, and fittings. 2. Provide supporting data for manhole covers, manhole steps, component construction, features, configuration, and dimensions. 3. Manufacturer's Installation Instructions. a. Indicate special procedures required to install products specified. 4. Project Record Documents: Accurately record the following. a. Locations of piping mains, valves, connections, and top of pipe elevations. b. Actual locations of pipe runs, connections, manholes, cleanouts, piping with sizes, locations and elevations of penetrations, and invert elevations. c. Identify and describe unexpected variations to subsoil conditions and location of uncharted utilities. |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | Civil Engineers |  | 14 |  | 11/01/2019 |  | 10/29/2019 | 10/15/2019 | 10/15/2019 | 10/15/2019 | 10/24/2019 |  | 10/25/2019 | 09/10/2019 | Paul Mogle
2 |  | 0 | 330000 | Medium |  | Submittal Register | UTILITIES (Onsite) | A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Submit supporting catalog materials indicating pipe, pipe accessories, and fittings. 2. Provide supporting data for manhole covers, manhole steps, component construction, features, configuration, and dimensions. 3. Manufacturer's Installation Instructions. a. Indicate special procedures required to install products specified. 4. Project Record Documents: Accurately record the following. a. Locations of piping mains, valves, connections, and top of pipe elevations. b. Actual locations of pipe runs, connections, manholes, cleanouts, piping with sizes, locations and elevations of penetrations, and invert elevations. c. Identify and describe unexpected variations to subsoil conditions and location of uncharted utilities. |  | 01/22/2020 | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | Civil Engineers |  | 30 | 12/03/2019 | 12/11/2019 | 12/13/2019 | 12/23/2019 | 10/15/2019 | 12/09/2019 | 12/09/2019 | 12/23/2019 |  | 12/23/2019 | 10/15/2019
1 |  | 0 | 334600 | High |  | Product Data | SUBDRAINAGE (Offsite) | A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Product Data: Indicating pipe, pipe accessories, and fittings. 2. Manufacturer's Installation Instructions: Indicate special procedures required to install products specified. |  |  | Closed | Approved |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 11/01/2019 | 10/15/2019 | 10/29/2019 | 10/15/2019 | 10/15/2019 | 10/15/2019 | 10/23/2019 |  | 10/23/2019 | 09/10/2019 |  | Civil Engineers
3 |  | 0 | 334600 | High |  | Product Data | SUBDRAINAGE (Onsite) | A. General: Submit the following in accordance with Conditions of Contract and Division 01 Specification Sections. 1. Product Data: Indicating pipe, pipe accessories, and fittings. 2. Manufacturer's Installation Instructions: Indicate special procedures required to install products specified. |  |  | Closed | No Exception Taken |  |  |  | Clint Foster | Sunroc Corporation | Westland PE’s |  | CRSA ARCHITECTURE |  |  |  | 01/08/2020 | 01/02/2020 | 01/11/2020 | 12/31/2019 | 12/31/2019 | 01/13/2020 | 01/13/2020 |  | 01/13/2020 | 12/31/2019